## Description
Sheet | Description
T&M Project List | The sheet contains all projects and services classified as Projects - T&M and Service Agreement – T&M (SA - TM) in the Master Portfolio (1PMP) for which there is planned billing (BM) for the current, future, and/or previous month. The OTBM extract from 1PMP is used to ensure that all the projects and services on this list are active and have a billing milestone from X-1 months onwards. This list excludes SCPT projects and services.
Resource List | The sheet contains a list of resources who either (1) tracked to T&M projects and services or is (2) planned to T&M project and services. Time tracking data used in this report is extracted from official DXC systems (Horizon) while resource plan information is obtained from PPMC labor demand and supply (LDSM) reporting. This report details the resources' planned and actual hours, revenue, and their compliance based on their utilization rate.
Useful links for references | OTBM Extract
PPMC LDSM
Horizon
Resource List
Column | Description
Segment | Segment of the T&M project in the P&G Account
ADM | Account Delivery Manager of the T&M project
Project Name | Name of the T&M Project
Note: Project name should follow the Biz Ops project naming format and should not have a FIXB engagement type.
Project ID | DXC ID (e.g PGXXXXXXXX)
WBS | WBS of the T&M Project
Manager Name | Employee's supervisor name
Employee ID | Unique number for each DXC employee
Employee | Name of the Employee
Actual Job Level | Job Level in the latest Time Tracking Report
Actual DXC Job Level | DXC Job Level in the latest Time Tracking Report
Country | Resource Location
Sum of Actual FTE | Total FTE tracked by the resource in the latest Time Tracking Report
Sum of PPMC FTE | Total Planned FTE for the resource in the latest PPMC Report
FTE Variance | Difference between Sum of Actual and PPMC FTE
Utilization Rate | Percentage of an employee's billable working hours
Actual Hours | Amount of time tracked by the resource in the latest Time Tracking Report
Planned Hours | Amount of time planned for the resource in the latest PPMC Report
Hours Variance | Difference between Actual and Planned Hours
Hourly Revenue Rates (USD) | Latest T&M rates obtained from P&G Account PMO
Actual Revenue | Actual Hours multiplied by the Hourly Revenue Rates
Planned Revenue | Planned Hours multiplied by the Hourly Revenue Rates
Revenue Variance | Difference between Actual and Planned Revenue
Audit | Resource compliance based on the utilization rate (No Tracking, Undertracking, No Plan, On Track)
T&M Report Schedule
Date | Frequency
1st week of the month | Every Monday
2nd week of the month | Every Monday and Thursday
3rd week of the month | Monday, Wednesday, and Friday
4th week and final week of the month | Daily

## T&M Projects List
Segment | PG ID | Project Name | ADM | DXC Project Manager | Project Stage | Project Classification | COMPASS FMO WBS
Voice | PG20P23934 | AMA-East Network CaaS Technical Project Manager Delivery | Arevalo, Milton | Velarde, Lalaine (lalaine.velarde@dxc.com) | Backlog | Projects - T&M | SG1-PGTEU.05.01
Voice | PG20P25038 | AMA-West Network CaaS Technical Project Manager Delivery | Arevalo, Milton | Chouhan, Sadiq (schouhan@dxc.com) | Backlog | Projects - T&M | SG1-PGTVO.05.01
Infra | PG21P03659 | MEGA Application Manager | Manalac, Von Xavier | Gajaraj, Kumuda (kumuda.gajaraj@dxc.com) | Backlog | Projects - T&M | US1-PGTIN.05.01
Infra | PG22P05298 | ITSM Enhancements ServiceNow | Manalac, Von Xavier | Gonzales, Orange H (maria-rosario-jhoanna.gonzales@dxc.com) | Backlog | Projects - T&M | US1-PGTIN.05.01
FSC | PG22P05327 | JP Morgan Exit | Arias, Juan | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG21P03633 | Service Transition Manager for Brazil Legal Requirements Project | Arias, Juan | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04824 | OTC SA Attachment B-3 – 5 – STM - AR SAP Factory | Arias, Juan | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG22P04999 | B2G Service Transition Management & B2G Factory support for PO Dedicated Team (CCR-138) | Arias, Juan | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG23P05456 | NA PrIME Box Elder - combined alternative | Beeckman, Guido | Roldan, Melania de los Angeles (melania-de-los-angeles.roldan@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
CSD | PG22P04641 | Pace Development Team FY 2223 JAS | Brzeski, Pawel | Brzeski, Pawel (pawel.brzeski@dxc.com) | Backlog | Projects - T&M | CH1-PGDAT.05.02
FSC | PG23P05481 | Monorail Security Remediation in Louveira | Burgess, Darren | Quesada, Raul (raul.quesada@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05537 | China CSO Automation Enhancement FY23-24 | Burgess, Darren | LIU, LEI (lliu80@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05540 | HP Export Warehouse Move to LG | Burgess, Darren | Guevarra, Cobe Bryan (cobebryan.guevarra@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05547 | HGP Stabilization Project Manager | Burgess, Darren | Obiniana, Ma. Rhodora C (ria.obiniana@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05548 | Digital Go to Market | Burgess, Darren | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05551 | Manila PFinsol Web Development | Burgess, Darren | Mauleon, Giles Andrew (gilesandrew.mauleon@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05561 | CM India Softech T&M Project | Burgess, Darren | Mauleon, Giles Andrew (gilesandrew.mauleon@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05578 | PrIME WMS PP and SE Support | Burgess, Darren | Recondo Lopez, Eduardo (eduardo.recondo-lopez@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04605 | Project Management Support for SAP Security Cleanup – FY23 | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04782 | R2R SCA Application Manager Base CFAL | Burgess, Darren | Cruz, Paolo Raphael S.R. (paolo-raphael.cruz@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04783 | R2R SCA Application Manager Base Rev and COPA | Burgess, Darren | Cruz, Paolo Raphael S.R. (paolo-raphael.cruz@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04785 | R2R SCA Application Manager Base Cost Accounting | Burgess, Darren | Palomo, Romlyn (romlyn.palomo@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04948 | Connectivity Application Managers – FY23 | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04949 | Connectivity ABAP Developers – FY23 | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04968 | E2Open Sprint Team | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P05068 | Invoice Workflow Transformation - Incremental Resources | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P05322 | SPPO Massive Change Tool – Purch Consultant | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05420 | SCA Application Manager Turkey Variance Tools ABAP | Burgess, Darren | Palomo, Romlyn (romlyn.palomo@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05429 | P&G GBS University – Engagement Improvement | Burgess, Darren | Uy, Precious L (precious@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05513 | Group Reporting Change Owner | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04774 | MADF AppMan, SharePoint Development and Security Services | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.73
FSC | PG22P05089 | ER GPS TCO ABAP Developer (CCR-151-B) | Burgess, Darren | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG22P04808 | SPO Deployment & Operations Services FY22 | Capati, Alvin Joh | Capati, Alvin Joh (alvin.joh.capati@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04603 | GBW SRU Services FY22 | Capati, Alvin Joh | Burgess, Darren (darren.burgess@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.59
FSC | PG22P04807 | DXC KNIME – OM Application Project FY22-23 | Castillo, Andres | Castillo, Rodrigo Andres (rcastillo@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04821 | OTC SA Attachment B.2.3 C– 5– OTC ASIA RPA | Castillo, Andres | Castillo, Rodrigo Andres (rcastillo@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG22P04454 | SCV and VSA Service | Castillo, Andres | Castillo, Rodrigo Andres (rcastillo@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.89
FSC | PG23P05439 | H1P Version Upgrade | Chakkoria, Shibu | Chakkoria, Shibu (shibu.chakkoria@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.80
CSD | PG22P04876 | Ingestion Development | Czerwiec, Krzysztof | Czerwiec, Krzysztof (krzysztof.czerwiec@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.60
CSD | PG22P04878 | Rubik (MDM) Development | Czerwiec, Krzysztof | Czerwiec, Krzysztof (krzysztof.czerwiec@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.62
FSC | PG23P05459 | Service Management Support for ALOHA LIGHT | Desengano, Lester | Desengano, Lester (lester.desengano@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
CSD | PG22P04877 | Logging & Monitoring Development | Eslabra, Giovanna | Brzeski, Pawel (pawel.brzeski@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.61
CSD | PG23P05359 | DAP Core DH Development | Kalek, Maciej | Kalek, Maciej (maciej.kalek@dxc.com) | Backlog | Service Agreement | US1-PGDAT.05.02
CSD | PG22P04872 | EU Data Hub Development | Kalek, Maciej | Kalek, Maciej (maciej.kalek@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.57
CSD | PG22P04873 | LA Data Hub Development | Kalek, Maciej | Kalek, Maciej (maciej.kalek@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.58
CSD | PG22P04874 | JP-AMA Data Hub Development | Kalek, Maciej | Kalek, Maciej (maciej.kalek@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.70
FSC | PG22P05039 | SAP PO RFC support | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P05257 | Customs Digitization Wave 2 T&M | Kalinin, Sergey | Bitantes, Kristen-Ann (kristen.bitantes@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P05321 | Gen Lanes SME support | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04187 | TS Product Support - Atlas | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04195 | TS Product Support - TCF | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04199 | TS Product Support - TMS | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04202 | TS Product Support - Customs | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04640 | TS Product Support - Extreme | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04179 | TS Product Support OBLB | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.79
FSC | PG22P04188 | TS Product Support - LM | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.82
FSC | PG22P04653 | TS Product Support - SHX | Kalinin, Sergey | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.91
FSC | PG23P05428 | Rulex programming support | Lee, Graeme | Lee, Graeme (Graeme.lee@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04185 | MIO Consulting Service | Lee, Graeme | Lee, Graeme (Graeme.lee@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04839 | CS BW Consulting Service | Lee, Graeme | Lee, Graeme (Graeme.lee@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04840 | Wpi & DDSi Consulting Service | Lee, Graeme | Lee, Graeme (Graeme.lee@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04183 | Iplanning Rapid Response (CCR-124) | Lee, Graeme | Arroyo, Mary Grace Cimara (mary-grace-c.cimara@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.81
FSC | PG22P04196 | Supply Planning Consulting Service | Lee, Graeme | Yu, Brian (brian.yu@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.83
FSC | PG22P04198 | APO Demand Planning Consulting service | Lee, Graeme | Kraus, Rene (rene.kraus@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.85
FSC | PG22P04201 | OMP_Implementation_Application and Platform Service | Lee, Graeme | Gonzales, Freddie Lou Ann Matutes (freddie-lou-ann.matutes@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.86
CSD | PG23P05352 | IT Analytics Solution Architecture and Implementation | Losicki, Miroslaw | Rzepka, Monika (monika.rzepka@dxc.com) | Backlog | Projects - T&M | US1-PGTIN.05.02
Infra | PG23P05411 | IT Data Cataloging and Data Architecture | Manalac, Von Xavier | Rzepka, Monika (monika.rzepka@dxc.com) | Backlog | Projects - T&M | US1-PGTIN.05.02
FSC | PG21P03467 | FPSS STM Americas Product Teams Regional Projects | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG21P03576 | FPT FMR and OSCAR STM | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04899 | Veritas FY2223 | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04914 | BP&A CIs (Profit Forecasting/OSCAR) | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05445 | Russia New Bank Project | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04715 | Capital Systems Project - Twenty5 | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04802 | FMDS STM FY2223 | Obiniana, Ria | Tan, Keltine Crishia (keltinecrishia.tan@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04812 | Auto-post Continuous Improvement | Obiniana, Ria | Obiniana, Ma. Rhodora C (ria.obiniana@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04534 | SDM-SAP M&S Integration | Panaligan, Jezalin | Getalado, Reginald (reginald.getalado@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
CSD | PG22P04831 | AMA CCS D&A Services | Parcero-Ong, Jacqueline | Parcero-Ong, Jacqueline (jacque.ong@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02
FSC | PG23P05530 | MH Plant RPA (Bluezone) | Quesada, Raul | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05541 | GIA RPA Update 6.10 | Quesada, Raul | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P05300 | NA TMS CI FY22-23 | Quesada, Raul | Quesada, Raul (raul.quesada@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05394 | NA St Louis Park PrIME | Quesada, Raul | Redulla, Mary Aileen (maryaileen.redulla@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05417 | NA PrIME Andover Rhodonite FY2223 | Quesada, Raul | Jimenez, Carolina (APPS GD Costa Rica) (cjimenez@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04373 | Brantford PrIME | Quesada, Raul | David, Jay (jay.david@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.06.97
FSC | PG22P05085 | NA PrIME Boombox Greenfield | Quesada, Raul | Duarte, Alexander (alexander.duarte-molina@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.08.01
FSC | PG22P04819 | OTC SA Attachment B.2.3 C– 4 - NALA SAP CI | Quesada, Raul | Velez Paiz, Fernando Antonio (fvelezpaiz@dxc.com) | Backlog | Service Agreement | US1-PGFCS.06.69
FSC | PG22P04998 | Brazil Legal and Tax Dedicated Team (CCR-138) | Quesada, Raul | Artavia, Tracy (tracy.artavia@dxc.com) | Backlog | Service Agreement | US1-PGFCS.06.76
FSC | PG22P04714 | Brazil Compliance Modernization FY22/23 | Quesada, Raul - FPSS | Quesada, Raul (raul.quesada@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04909 | DXC Functional support for Brazil SATI/SPED FY 22 23 | Quesada, Raul - FPSS | Quesada, Raul (raul.quesada@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05410 | Azure Application Improvements | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04848 | Automation FactoryFY22-23 | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P05273 | RPA developer for NA | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG23P05350 | AR DevOps BluePrism | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG23P05374 | Singapore Pioneer Plant | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG23P05413 | dComm LA PHC | Quesada, Raul - RPA | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | PA1-PGPLA.05.01
FSC | PG22P04453 | RPA Core Service | Quesada, Raul - RPA | Quesada, Raul (raul.quesada@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.88
FSC | PG23P05369 | EAIMON DevOps 2023 | Quito, Nelson - Projects | Casareo, Mark (mark.casareo@dxc.com) | Backlog | Projects - T&M | US1-PGHRZ.05.01
FSC | PG22P04588 | SBM Jaggaer DevOps Resources | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04723 | FPSS Access Management BW Developer | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04753 | FPSS Regional Projects IT Delivery FY23 | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04768 | Brazil Localization Master Data Resource | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04800 | FPT External Reporting STM FY23 | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04838 | FAR OPEX Portfolio Resources | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04772 | DXC Global AP Application Management Team FY23 | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.62
FSC | PG22P04773 | IT Services for FPSS Banking Global Team FY23 | Radaza, Gerald | Radaza, Gerald Kinsky T (gerald.radaza@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.63
FSC | PG23P05488 | PrIME Zero Downtime | Regueiro Lozano, Ainhoa | Joson, May Fe (may-fe.joson@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05516 | Python Developer to support PrIME COE Team | Regueiro Lozano, Ainhoa | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04995 | PrIME custom mod upgrade | Regueiro, Ainhoa | Rodriguez, Yroe L (yroe.rodriguez@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.06.81
FSC | PG22P04895 | RTCIS and PrIME refresh management and Configuration Management | Regueiro, Ainhoa | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P05024 | Warehousing Wave RO FY2223 | Regueiro, Ainhoa | Capalad Tomagan, Rogene (r.capaladtomagan@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG23P05361 | ITC Rollout Support for Warehousing | Regueiro, Ainhoa | Kalinin, Sergey (sergey.kalinin@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P04679 | Warehousing Solution Team - Loftware | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04680 | Warehousing RTCIS Security Remediation | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04682 | ITS Warehousing Solution Team – Librarian | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.05.01
FSC | PG22P04178 | IT Warehousing Solution Team - SAP - 3PL Connect | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.78
FSC | PG22P04180 | PrIME Product Team | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.80
FSC | PG22P04197 | Warehousing Product Team for RTCIS | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.84
FSC | PG22P04203 | DXC PrIME Center of Excellence | Regueiro, Ainhoa | Co, Aldrick Dexter (aldrickdexter.co@dxc.com) | Backlog | Service Agreement | US1-PGPLA.06.87
CSD | PG21P03548 | CFM and CAS Security & Access Management Support | Rehman, Abdul | Mohan, Latha (latha.mohan@dxc.com) | Backlog | Projects - T&M | US1-PGEBU.05.02
CSD | PG21P03580 | Optima Sprint Support | Rehman, Abdul | Varadhappan, Venkatachalam (venkatv@dxc.com) | Backlog | Projects - T&M | US1-PGEBU.05.02
CSD | PG22P05232 | eBusiness Launchpad | Romeyns, Bert | Brzeski, Pawel (pawel.brzeski@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02
FSC | PG22P04618 | PS Projects T&M for Greater China FY22-23 | Tecson, Jacqueline | Rivera, Marco (Apps GD CR) (marco.rivera3@dxc.com) | Backlog | Projects - T&M | CH1-PGPLA.05.01
FSC | PG23P05345 | XiQing AGVs Implementation | Tecson, Jacqueline | Guevarra, Cobe Bryan (cobebryan.guevarra@dxc.com) | Backlog | Projects - T&M | CN1-PGPLA.05.01
FSC | PG21P04065 | P&G Schrems II Project | Tecson, Jacqueline | Dimapilis, Michael Andrei (m.dimapilis@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG22P04616 | PS Projects T&M for AMA and Europe FY22-23 | Tecson, Jacqueline | URCIA, JOANNA ISABELLE (joannaisabelle.urcia@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.02
FSC | PG23P05363 | Generic Lanes Support T&M Project | Tecson, Jacqueline | Dolot, Mary Faith A (mary-faith.a.dolot@dxc.com) | Backlog | Projects - T&M | US1-PGPLA.05.01
FSC | PG22P05047 | Adhoc security requests for RTCIS and PrIME systems (CCR-143) | Vargas, Claudia | Vargas, Claudia P (claudia.vargas@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG21P04082 | MES Connect Deployment Requests | Vermunicht, Guido - Projects | Ahuchogu, Chukwuma (DXC EAI ISC - P&G account) (chukwuma.ahuchogu@dxc.com) | Backlog | Projects - T&M | US1-PGFCS.05.03
FSC | PG22P04273 | Harmony Project | Vermunicht, Guido - Projects | Ahuchogu, Chukwuma (DXC EAI ISC - P&G account) (chukwuma.ahuchogu@dxc.com) | Backlog | Projects - T&M | US1-PGTAP.05.02
FSC | PG22P04820 | OTC SA Attachment B-3 – 1 – Accounts Receivables SAP Factory PG | Villuendas, Raul | Villuendas Bailera, Raul (villuendas.r@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
FSC | PG22P04822 | OTC SA Attachment B-3 – 2– Accounts Receivable Application Manager | Villuendas, Raul | Villuendas Bailera, Raul (villuendas.r@dxc.com) | Backlog | Service Agreement | US1-PGFCS.05.02
CSD | PG23P05549 | Payroll Error Dashboard | Waksmanska, Malgorzata | Tan-Teo, Jenny Anne (jenny@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02
CSD | PG22P05247 | EASE development FY2223 | Waksmanska, Malgorzata | Mishra, Sambit (sambit.mishra@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02
CSD | PG22P04871 | NA Data Hub Development | Waksmanska, Malgorzata | Velinova, Emilia (emilia.velinova@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.56
CSD | PG22P04875 | FastMart Development | Waksmanska, Malgorzata | Velinova, Emilia (emilia.velinova@dxc.com) | Backlog | Service Agreement | US1-PGDAT.06.59
CSD | PG23P05440 | P&G Cloud business analyst and documentation | Waksmanska, Malgorzata | Modlinska, Ewelina Anna (ewelina.modlinska@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02
CSD | PG23P05477 | Programmatic Shelf Analytics | Waksmanska, Malgorzata | Chmielewska, Karolina (karolina.szczaluba@dxc.com) | Backlog | Projects - T&M | US1-PGDAT.05.02

## Resources List
Segment | ADM | Project Name | Project ID | Manager Name | Employee ID | Employee | PG Job Level | DXC Job Level | Country | Sum of Actual FTE | Sum of PPMC FTE | FTE Variance | Utilization Rate | Actual Hours | Planned Hours | Hours Variance | Hourly Revenue Rates (USD) | Actual Revenue | Planned Revenue | Revenue Variance | Audit
CSD | Brzeski, Pawel | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04641_Pace Development Team FY 2223 JAS | PG22P04641 | Golawski, Michal M. | 11563748 | Michon, Lukasz | L9 | L6 | Poland | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 70.57 | 0 | 12984.88 | 12984.88 | No Tracking
CSD | Brzeski, Pawel | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04641_Pace Development Team FY 2223 JAS | PG22P04641 | Teo, Jenny Anne T. | 11715376 | Pallingayan, Glorianne | L9 | L6 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 48.19 | 8481.44 | 8866.96 | 385.52 | On Track
CSD | Brzeski, Pawel | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04641_Pace Development Team FY 2223 JAS | PG22P04641 | Kubijk-Koza, Ewelina | 21842764 | Miazek-Mioduszewski, Tomasz | L9 | L6 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 70.57 | 10162.08 | 12984.88 | 2822.8 | Undertracking
CSD | Brzeski, Pawel | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04641_Pace Development Team FY 2223 JAS | PG22P04641 | Bordey-Choi, Iris O. | 11568467 | Datuin, Van Raoul | L9 | L6 | Philippines | 0.71 | 1 | 0.29 | 70.65% | 130 | 184 | 54 | 48.19 | 6264.7 | 8866.96 | 2602.26 | Undertracking
CSD | Brzeski, Pawel | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04641_Pace Development Team FY 2223 JAS | PG22P04641 | Bordey-Choi, Iris O. | 11567355 | Sarmiento, Macy Geneth C. | L8 | L5 | Philippines | 0.58 | 1 | 0.42 | 58.15% | 107 | 184 | 77 | 33.58 | 3593.06 | 6178.72 | 2585.66 | Undertracking
CSD | Czerwiec, Krzysztof | Rubik (MDM) Development | PG22P04878 | Unmapped | 11740010 | Jaroslaw Gaze | L9 | L6 | Poland | 0.56522 | 0 | -0.56522 | 0% | 104 | 0 | -104 | 70.57 | 7339.28 | 0 | -7339.28 | No Plan
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 23217249 | Wydro, Damian | L0 | L1 | Poland | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 0 | 0 | 0 | 0 | No Tracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Makowska, Marta A. | 20075875 | Pliszka, Jacek | L9 | L6 | Poland | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 70.57 | 0 | 12984.88 | 12984.88 | No Tracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04876_Ingestion Development | PG22P04876 | Ediga, Chandra | 11745366 | Verma, Manisha | L7 | L4 | India | 0 | 0.35 | 0.35 | 0% | 0 | 72.45 | 72.45 | 17.33 | 0 | 1255.5585 | 1255.5585 | No Tracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11620590 | Dendek, Cezary | L9 | L6 | Poland | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 70.57 | 0 | 12984.88 | 12984.88 | No Tracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Fawzy Bayomie, Mohamed | 60065278 | Abdelgaleel, Ahmad | L9 | L6 | Egypt | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 |  | 0 | 0 | 0 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Ciesielska, Ewelina | 11763433 | Makula, Maciej | L8 | L5 | Poland | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 54.93 | 8349.36 | 10107.12 | 1757.76 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Ogoy, Rhodalie Kaye A. | 11762515 | Ensomo, Phillipp Vincent | L9 | L6 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 48.19 | 8095.92 | 8866.96 | 771.04 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Goel, Rajeev | 11741600 | Gottapu, Sai Avinash | L8 | L5 | India | 0.91 | 1 | 0.09 | 91.3% | 189 | 207 | 18 | 26.59 | 5025.51 | 5504.13 | 478.62 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11740840 | Cygon, Piotr | L8 | L5 | Poland | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 54.93 | 8788.8 | 10107.12 | 1318.32 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Fu, Rina Joyce | 11740371 | Bondoc, Judy Rose | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Bordey-Choi, Iris O. | 11738067 | Jumagdao, Carlo | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Marcelo, Cristy | 11737384 | Villanueva, Alvin | L7 | L4 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 20.51 | 3445.68 | 3773.84 | 328.16 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Goel, Rajeev | 11730964 | Kandaswamy, Amutha | L8 | L5 | India | 0.91 | 1 | 0.09 | 91.3% | 189 | 207 | 18 | 26.59 | 5025.51 | 5504.13 | 478.62 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Bordey-Choi, Iris O. | 11723047 | Saycon, Karl Joseph | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Goel, Rajeev | 11596787 | Chopra, Tarun | L9 | L6 | India | 0.96 | 1 | 0.04 | 95.65% | 198 | 207 | 9 | 38.22 | 7567.56 | 7911.54 | 343.98 | On Track
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Janek, Anna M. | 75013228 | Stolarek, Marcin | L9 | L6 | Poland | 0.4 | 1 | 0.6 | 40.33% | 74.2 | 184 | 109.8 | 70.57 | 5236.294 | 12984.88 | 7748.586 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Wenerski, Maciej | 60071615 | Robak, Tomasz | L9 | L6 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 70.57 | 10162.08 | 12984.88 | 2822.8 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 23213816 | Mielniczek, Miroslaw | L0 | L1 | Poland | 0.33 | 1 | 0.67 | 32.61% | 60 | 184 | 124 | 0 | 0 | 0 | 0 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04876_Ingestion Development | PG22P04876 | Kubijk-Koza, Ewelina | 20000481 | Lis, Wojciech | L9 | L6 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 70.57 | 10162.08 | 12984.88 | 2822.8 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Chorbanov, Nikolay | 11762380 | Penev, Plamen | L9 | L6 | Bulgaria | 0.35 | 1 | 0.65 | 34.78% | 64 | 184 | 120 | 59.71 | 3821.44 | 10986.64 | 7165.2 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Rubinkowska, Joanna | 11759941 | Oktaba, Klaudia | L6 | L3 | Poland | 0.48 | 1 | 0.52 | 47.83% | 88 | 184 | 96 | 28.11 | 2473.68 | 5172.24 | 2698.56 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11752765 | Yilmaz, Eray Tunç | L7 | L4 | Poland | 0.8 | 1 | 0.2 | 80.43% | 148 | 184 | 36 | 40.45 | 5986.6 | 7442.8 | 1456.2 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 11752764 | Wasik, Bartosz | L9 | L6 | Poland | 0.33 | 0.5 | 0.17 | 65.22% | 60 | 92 | 32 | 70.57 | 4234.2 | 6492.44 | 2258.24 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11752748 | Maiboroda, Yevheniia | L7 | L4 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 40.45 | 5824.8 | 7442.8 | 1618 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 11744901 | Mrdjan, Jovan | L7 | L4 | Poland | 0.09 | 1 | 0.91 | 8.696% | 16 | 184 | 168 | 40.45 | 647.2 | 7442.8 | 6795.6 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 11742691 | Lodkowski, Pawel | L7 | L4 | Poland | 0.7 | 1 | 0.3 | 69.57% | 128 | 184 | 56 | 40.45 | 5177.6 | 7442.8 | 2265.2 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11740039 | Pytel, Szymon | L6 | L3 | Poland | 0.52 | 1 | 0.48 | 52.17% | 96 | 184 | 88 | 28.11 | 2698.56 | 5172.24 | 2473.68 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11735426 | Pazowski, Marcin | L8 | L5 | Poland | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 54.93 | 5712.72 | 10107.12 | 4394.4 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Andreev, Anton | 11730154 | Zangarov, Denis | L6 | L3 | Bulgaria | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 30.94 | 4207.84 | 5692.96 | 1485.12 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Makowska, Marta A. | 11727432 | Nowak, Przemyslaw | L6 | L3 | Poland | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 28.11 | 3822.96 | 5172.24 | 1349.28 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Andreev, Anton | 11622122 | Kyuchukova, Zhiva | L7 | L4 | Bulgaria | 0.52 | 1 | 0.48 | 52.17% | 96 | 184 | 88 | 37.08 | 3559.68 | 6822.72 | 3263.04 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 11600631 | Maliszewski, Adam | L10 | L6 | Poland | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 70.57 | 7339.28 | 12984.88 | 5645.6 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Janek, Anna M. | 11588843 | Wozniak, Artur | L7 | L4 | Poland | 0.22 | 1 | 0.78 | 21.74% | 40 | 184 | 144 | 40.45 | 1618 | 7442.8 | 5824.8 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Kubijk-Koza, Ewelina | 11571587 | Szeptuch, Jacek | L9 | L6 | Poland | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 70.57 | 9597.52 | 12984.88 | 3387.36 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Golawski, Michal M. | 11561634 | Barcikowski, Wojciech | L10 | L6 | Poland | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 70.57 | 7339.28 | 12984.88 | 5645.6 | Undertracking
CSD | Czerwiec, Krzysztof | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04878_Rubik (MDM) Development | PG22P04878 | Torres, Von Russell | 11542217 | Mabini, Roberto Bano | L9 | L6 | Philippines | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 48.19 | 5397.28 | 8866.96 | 3469.68 | Undertracking
CSD | Eslabra, Giovanna | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04877_Logging & Monitoring Development | PG22P04877 | Bordey-Choi, Iris O. | 11732057 | Lopez, Earl Dean | L7 | L4 | Philippines | 0.91 | 0.9 | -0.01 | 101.4% | 168 | 165.6 | -2.4 | 20.51 | 3445.68 | 3396.456 | -49.224 | On Track
CSD | Eslabra, Giovanna | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04877_Logging & Monitoring Development | PG22P04877 | Tolentino, Ericka May Robles | 11595365 | Fernandez, Joshua John | L8 | L5 | Philippines | 0.35 | 0.75 | 0.4 | 46.38% | 64 | 138 | 74 | 33.58 | 2149.12 | 4634.04 | 2484.92 | Undertracking
CSD | Eslabra, Giovanna | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04877_Logging & Monitoring Development | PG22P04877 | Tolentino, Ericka May Robles | 11582268 | Phala, Jose Lito | L7 | L4 | Philippines | 0.43 | 0.75 | 0.32 | 57.97% | 80 | 138 | 58 | 20.51 | 1640.8 | 2830.38 | 1189.58 | Undertracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Chatterjee, Samyak | 21759927 | Salla, Sreenath Reddy | L7 | L4 | India | 0 | 0.2 | 0.2 | 0% | 0 | 41.4 | 41.4 | 17.33 | 0 | 717.462 | 717.462 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Kubijk-Koza, Ewelina | 21676841 | Taluc, Tomasz | L10 | L6 | Poland | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 70.57 | 0 | 1298.488 | 1298.488 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Radosz, Jacek T. | 20109114 | Kalek, Maciej D. | L9 | L6 | Poland | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 70.57 | 0 | 2596.976 | 2596.976 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04873_LA Data Hub Development | PG22P04873 | Radosz, Jacek T. | 20109114 | Kalek, Maciej D. | L9 | L6 | Poland | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 70.57 | 0 | 2596.976 | 2596.976 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Radosz, Jacek T. | 20109114 | Kalek, Maciej D. | L9 | L6 | Poland | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 70.57 | 0 | 6492.44 | 6492.44 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG23P05359_DAP Core DH Development | PG23P05359 | Radosz, Jacek T. | 20109114 | Kalek, Maciej D. | L9 | L6 | Poland | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 70.57 | 0 | 1298.488 | 1298.488 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Radosz, Jacek T. | 20000506 | Kulesza, Maciej F. | L9 | L6 | Poland | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 70.57 | 0 | 1298.488 | 1298.488 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Radosz, Jacek T. | 20000506 | Kulesza, Maciej F. | L9 | L6 | Poland | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 70.57 | 0 | 1298.488 | 1298.488 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Golawski, Michal M. | 11759884 | Serafin, Bartosz | L7 | L4 | Poland | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 40.45 | 0 | 1860.7 | 1860.7 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04873_LA Data Hub Development | PG22P04873 | Golawski, Michal M. | 11759884 | Serafin, Bartosz | L7 | L4 | Poland | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 40.45 | 0 | 3721.4 | 3721.4 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Golawski, Michal M. | 11759884 | Serafin, Bartosz | L7 | L4 | Poland | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 40.45 | 0 | 1860.7 | 1860.7 | No Tracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Golawski, Michal M. | 21857483 | Mackiewicz, Katarzyna A. | L8 | L5 | Poland | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 54.93 | 8349.36 | 10107.12 | 1757.76 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04873_LA Data Hub Development | PG22P04873 | Chatterjee, Samyak | 21759927 | Salla, Sreenath Reddy | L7 | L4 | India | 0.24 | 0.25 | 0.01 | 95.65% | 49.5 | 51.75 | 2.25 | 17.33 | 857.835 | 896.8275 | 38.9925 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04874_JP-AMA Data Hub Development | PG22P04874 | Chatterjee, Samyak | 21759927 | Salla, Sreenath Reddy | L7 | L4 | India | 0.24 | 0.25 | 0.01 | 95.65% | 49.5 | 51.75 | 2.25 | 17.33 | 857.835 | 896.8275 | 38.9925 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Kubijk-Koza, Ewelina | 21676841 | Taluc, Tomasz | L10 | L6 | Poland | 0.26 | 0.2 | -0.06 | 130.4% | 48 | 36.8 | -11.2 | 70.57 | 3387.36 | 2596.976 | -790.384 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG23P05359_DAP Core DH Development | PG23P05359 | Kubijk-Koza, Ewelina | 21676841 | Taluc, Tomasz | L10 | L6 | Poland | 0.61 | 0.7 | 0.09 | 86.96% | 112 | 128.8 | 16.8 | 70.57 | 7903.84 | 9089.416 | 1185.576 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG23P05359_DAP Core DH Development | PG23P05359 | Radosz, Jacek T. | 20000506 | Kulesza, Maciej F. | L9 | L6 | Poland | 0.83 | 0.8 | -0.03 | 103.3% | 152 | 147.2 | -4.8 | 70.57 | 10726.64 | 10387.904 | -338.736 | On Track
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04873_LA Data Hub Development | PG22P04873 | Golawski, Michal M. | 75010294 | Wierzchowski, Michal | L10 | L6 | Poland | 0.28 | 0.5 | 0.22 | 56.52% | 52 | 92 | 40 | 70.57 | 3669.64 | 6492.44 | 2822.8 | Undertracking
CSD | Kalek, Maciej | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04872_EU Data Hub Development | PG22P04872 | Andreev, Anton | 60061854 | Hadzhieva, Rossica | L8 | L5 | Bulgaria | 0.39 | 0.5 | 0.11 | 78.26% | 72 | 92 | 20 | 49.91 | 3593.52 | 4591.72 | 998.2 | Undertracking
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Radosz, Jacek T. | 75013236 | Rzepka, Monika | L8 | L5 | Poland | 0.43 | 0.25 | -0.18 | 173.9% | 80 | 46 | -34 | 54.93 | 4394.4 | 2526.78 | -1867.62 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Pena, Jacqueline Zoleta | 21893809 | Bascones, Wena Flor Ellivera | L8 | L5 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 33.58 | 5104.16 | 6178.72 | 1074.56 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Rubinkowska, Joanna | 11755633 | Nowakowski, Michal | L7 | L4 | Poland | 0.43 | 0.5 | 0.07 | 86.96% | 80 | 92 | 12 | 40.45 | 3236 | 3721.4 | 485.4 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Odulio, Andria | 11742401 | Eusebio, Monique | L7 | L4 | Philippines | 0.52 | 0.5 | -0.02 | 104.3% | 96 | 92 | -4 | 20.51 | 1968.96 | 1886.92 | -82.04 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Bordey-Choi, Iris O. | 11620653 | Diaz, Joanna Marie A. | L8 | L5 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 33.58 | 5372.8 | 6178.72 | 805.92 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Ong, Jacqueline P. | 11566274 | Arzadon, Andrian | L8 | L5 | Philippines | 0.87 | 0.5 | -0.37 | 173.9% | 160 | 92 | -68 | 33.58 | 5372.8 | 3089.36 | -2283.44 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Pena, Jacqueline Zoleta | 11562782 | Avenido, Julius Angelo | L7 | L4 | Philippines | 0.57 | 0.43 | -0.14 | 131.4% | 104 | 79.12 | -24.88 | 20.51 | 2133.04 | 1622.7512 | -510.2888 | On Track
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Alegre, Xylee | 11755277 | Estebal, Joanna Marie | L7 | L4 | Philippines | 0.17 | 0.22 | 0.05 | 79.05% | 32 | 40.48 | 8.48 | 20.51 | 656.32 | 830.2448 | 173.9248 | Undertracking
CSD | Losicki, Miroslaw | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05352_IT Analytics Solution Architecture and Implementation | PG23P05352 | Pena, Jacqueline Zoleta | 11741430 | Lopez, Deniz | L7 | L4 | Philippines | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 20.51 | 2297.12 | 3773.84 | 1476.72 | Undertracking
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Ong, Jacqueline P. | 11616425 | Gacute, Ma. Clarissa J. | L7 | L4 | Philippines | 0.96 | 0.35 | -0.61 | 273.3% | 176 | 64.4 | -111.6 | 20.51 | 3609.76 | 1320.844 | -2288.916 | On Track
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Ong, Jacqueline P. | 11570913 | Maling, Maria Kristina | L8 | L5 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 33.58 | 5104.16 | 6178.72 | 1074.56 | On Track
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Teo, Jenny Anne T. | 21678469 | Ong, Jacqueline P. | L14 | L6 | Philippines | 0.12 | 0.5 | 0.38 | 23.91% | 22 | 92 | 70 | 48.19 | 1060.18 | 4433.48 | 3373.3 | Undertracking
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Teo, Jenny Anne T. | 20430404 | Correa, Ann Margarette Almonia | L9 | L6 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 48.19 | 6939.36 | 8866.96 | 1927.6 | Undertracking
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Teo, Jenny Anne T. | 11708116 | Tondares, Monaliza M. | L8 | L5 | Philippines | 0.14 | 0.2 | 0.06 | 70.65% | 26 | 36.8 | 10.8 | 33.58 | 873.08 | 1235.744 | 362.664 | Undertracking
CSD | Parcero-Ong, Jacqueline | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P04831_AMA CCS D&A Services | PG22P04831 | Teo, Jenny Anne T. | 11617871 | Gozun, Katrina Camille | L10 | L6 | Philippines | 0.24 | 0.4 | 0.16 | 59.78% | 44 | 73.6 | 29.6 | 48.19 | 2120.36 | 3546.784 | 1426.424 | Undertracking
CSD | Rehman, Abdul | Deliver_AMS_PG_APP_TMTL_CSD_30_PG21P03580_Optima Sprint Support | PG21P03580 | Avudaiappan, Maiappan | 21931153 | Gupta, Vikash | L7 | L4 | India | 1 | 1 | 0 | 100% | 207 | 207 | 0 | 17.33 | 3587.31 | 3587.31 | 0 | On Track
CSD | Rehman, Abdul | Deliver_AMS_PG_APP_TMTL_CSD_30_PG21P03548_CFM & CAS Security & Access Management Support | PG21P03548 | Varadhappan, Venkatachalam | 21639464 | Mohan, Latha | L7 | L4 | India | 0.43 | 0.5 | 0.07 | 85.51% | 88.5 | 103.5 | 15 | 17.33 | 1533.705 | 1793.655 | 259.95 | On Track
CSD | Rehman, Abdul | Deliver_AMS_PG_APP_TMTL_CSD_30_PG21P03548_CFM & CAS Security & Access Management Support | PG21P03548 | Rehman, Abdul | 11552727 | Patel, Poojitha. | L7 | L4 | India | 0.87 | 1 | 0.13 | 86.96% | 180 | 207 | 27 | 17.33 | 3119.4 | 3587.31 | 467.91 | On Track
CSD | Romeyns, Bert | eCommerce Analytics | PG22P04851 | Kubijk-Koza, Ewelina | 60086420 | Ratynski, Tomasz | L9 | L6 | Poland | 0.043478 | 0 | -0.043478 | 0% | 8 | 0 | -8 | 70.57 | 564.56 | 0 | -564.56 | No Plan
CSD | Romeyns, Bert | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05232_eBusiness Launchpad | PG22P05232 | Andreev, Anton | 20397153 | Ongiro, Lilia | L7 | L4 | Bulgaria | 0.41 | 0.5 | 0.09 | 81.52% | 75 | 92 | 17 | 37.08 | 2781 | 3411.36 | 630.36 | On Track
CSD | Romeyns, Bert | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05232_eBusiness Launchpad | PG22P05232 | Toma, Andrei | 11583501 | Trinidad, Angeli Mae | L8 | L5 | United States | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 103.6 | 18233.6 | 19062.4 | 828.8 | On Track
CSD | Romeyns, Bert | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05232_eBusiness Launchpad | PG22P05232 | Kubijk-Koza, Ewelina | 60086420 | Ratynski, Tomasz | L9 | L6 | Poland | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 70.57 | 7903.84 | 12984.88 | 5081.04 | Undertracking
CSD | Romeyns, Bert | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05232_eBusiness Launchpad | PG22P05232 | Kubijk-Koza, Ewelina | 11569663 | Mac´kowska, Milena | L8 | L5 | Poland | 0.65 | 1 | 0.35 | 65.22% | 120 | 184 | 64 | 54.93 | 6591.6 | 10107.12 | 3515.52 | Undertracking
CSD | Waksmanska, Malgorzata | Payroll Error Dashboard | PG23P05549 | Teo, Jenny Anne T. | 21641598 | Gonzales, Lourdes Marie Clare | L8 | L5 | Philippines | 0.6087 | 0 | -0.6087 | 0% | 112 | 0 | -112 | 33.58 | 3760.96 | 0 | -3760.96 | No Plan
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05247_EASE development FY2223 | PG22P05247 | Bansal, Mukesh Kumar | 60029518 | Mishra, Sambit | L7 | L4 | India | 0 | 0.04 | 0.04 | 0% | 0 | 8.28 | 8.28 | 17.33 | 0 | 143.4924 | 143.4924 | No Tracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Andreev, Anton | 20416011 | Stoitsev, Mihail | L10 | L6 | Bulgaria | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 59.71 | 0 | 5493.32 | 5493.32 | No Tracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Andreev, Anton | 11762426 | Chalkanov, Nikolay | L9 | L6 | Bulgaria | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 59.71 | 0 | 5493.32 | 5493.32 | No Tracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Chatterjee, Samyak | 21759927 | Salla, Sreenath Reddy | L7 | L4 | India | 0.48 | 0.5 | 0.02 | 95.65% | 99 | 103.5 | 4.5 | 17.33 | 1715.67 | 1793.655 | 77.985 | On Track
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05247_EASE development FY2223 | PG22P05247 | Bordey-Choi, Iris O. | 21051361 | Nasayao, Je-Marie Sanchez | L8 | L5 | Philippines | 0.22 | 0.22 | 0 | 98.81% | 40 | 40.48 | 0.48 | 33.58 | 1343.2 | 1359.3184 | 16.1184 | On Track
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Andreev, Anton | 11717676 | Chalakov, Stanimir | L6 | L3 | Bulgaria | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 30.94 | 2351.44 | 2846.48 | 495.04 | On Track
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05477_Programmatic Shelf Analytics | PG23P05477 | Teo, Jenny Anne T. | 11617871 | Gozun, Katrina Camille | L10 | L6 | Philippines | 0.72 | 0.75 | 0.03 | 95.65% | 132 | 138 | 6 | 48.19 | 6361.08 | 6650.22 | 289.14 | On Track
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Radosz, Jacek T. | 23158101 | Celuch, Radoslaw | L0 | L1 | Poland | 0.57 | 2 | 1.43 | 28.26% | 104 | 368 | 264 | 0 | 0 | 0 | 0 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Teo, Jenny Anne T. | 21907300 | Paltao, Gilbert Pasco | L8 | L5 | Philippines | 0.39 | 0.5 | 0.11 | 78.26% | 72 | 92 | 20 | 33.58 | 2417.76 | 3089.36 | 671.6 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Andreev, Anton | 21606052 | Velinova, Emilia | L8 | L5 | Bulgaria | 0.35 | 0.5 | 0.15 | 69.57% | 64 | 92 | 28 | 49.91 | 3194.24 | 4591.72 | 1397.48 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Andreev, Anton | 21606052 | Velinova, Emilia | L8 | L5 | Bulgaria | 0.07 | 0.1 | 0.03 | 69.57% | 12.8 | 18.4 | 5.6 | 49.91 | 638.848 | 918.344 | 279.496 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05440_P&G Cloud Business Analyst and Documentation | PG23P05440 | Kozielski, Pawel | 11762164 | Cedrowski, Piotr | L7 | L4 | Poland | 0.49 | 0.75 | 0.26 | 65.22% | 90 | 138 | 48 | 40.45 | 3640.5 | 5582.1 | 1941.6 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05477_Programmatic Shelf Analytics | PG23P05477 | R, Annasamy | 11753061 | Kulkarni, Prasad | L8 | L5 | India | 0.61 | 1 | 0.39 | 60.87% | 126 | 207 | 81 | 26.59 | 3350.34 | 5504.13 | 2153.79 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Ciesielska, Ewelina | 11752733 | Grajaszek, Justyna | L6 | L3 | Poland | 0.48 | 1 | 0.52 | 47.83% | 88 | 184 | 96 | 28.11 | 2473.68 | 5172.24 | 2698.56 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Radosz, Jacek T. | 11746509 | Tyc, Jacek | L9 | L6 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 70.57 | 10162.08 | 12984.88 | 2822.8 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04875_FastMart Development | PG22P04875 | Golawski, Michal M. | 11740068 | Zwierzynski, Adrian | L7 | L4 | Poland | 0.39 | 1 | 0.61 | 39.13% | 72 | 184 | 112 | 40.45 | 2912.4 | 7442.8 | 4530.4 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG22P05247_EASE development FY2223 | PG22P05247 | Salvador, Juanito Jr Penalosa | 11739482 | Arayata, Karlo O. | L6 | L3 | Philippines | 0.17 | 0.22 | 0.05 | 79.05% | 32 | 40.48 | 8.48 | 14.53 | 464.96 | 588.1744 | 123.2144 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_SATM_CSD_30_PG22P04871_NA Data Hub Development | PG22P04871 | Andreev, Anton | 11572964 | Iliev, Valentinov Ivan | L7 | L4 | Bulgaria | 0.65 | 1 | 0.35 | 65.22% | 120 | 184 | 64 | 37.08 | 4449.6 | 6822.72 | 2373.12 | Undertracking
CSD | Waksmanska, Malgorzata | Deliver_AMS_PG_APP_TMTL_CSD_30_PG23P05440_P&G Cloud Business Analyst and Documentation | PG23P05440 | Malas, Radoslaw | 11569501 | Wódkowski, Lukasz | L8 | L5 | Poland | 0.48 | 1 | 0.52 | 47.83% | 88 | 184 | 96 | 54.93 | 4833.84 | 10107.12 | 5273.28 | Undertracking
FSC | Arias, Juan | B2G Service Transition Management & B2G Factory support for PO Dedicated Team (CCR-138) | PG22P04999 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.086793 | 0 | -0.086793 | 0% | 15.97 | 0 | -15.97 | 14.53 | 232.0441 | 0 | -232.0441 | No Plan
FSC | Arias, Juan | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P04999_B2G Service Transition Management & B2G Factory support for PO Dedicated Team (CCR-138) | PG22P04999 | Roa, Charles David A. | 60091229 | Alejandro, Rachelle C. | L7 | L4 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 20.51 | 0 | 377.384 | 377.384 | No Tracking
FSC | Arias, Juan | Deliver_AMS_PG_APP_TMTL_ESC_70_PG22P05327_JP Morgan Exit | PG22P05327 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 32.3 | 568.48 | 594.32 | 25.84 | On Track
FSC | Arias, Juan | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P04999_B2G Service Transition Management & B2G Factory support for PO Dedicated Team (CCR-138) | PG22P04999 | Mapua, Kristoferson Gopez | 21572433 | Antonio, Sarah Mangalinao | L14 | L6 | Philippines | 0.43 | 0.5 | 0.07 | 86.96% | 80 | 92 | 12 | 48.19 | 3855.2 | 4433.48 | 578.28 | On Track
FSC | Arias, Juan | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P04824_OTC SA Attachment B-3 – 5 – STM - AR SAP Factory | PG22P04824 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 92.28% | 16.98 | 18.4 | 1.42 | 14.53 | 246.7194 | 267.352 | 20.6326 | On Track
FSC | Arias, Juan | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P04999_B2G Service Transition Management & B2G Factory support for PO Dedicated Team (CCR-138) | PG22P04999 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.19 | 0.25 | 0.06 | 76.52% | 35.2 | 46 | 10.8 | 32.3 | 1136.96 | 1485.8 | 348.84 | Undertracking
FSC | Arias, Juan | Deliver_AMS_PG_APP_TMTL_ESC_70_PG21P03633_Service Transition Manager for Brazil Legal Requirements Project | PG21P03633 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.14 | 0.2 | 0.06 | 71.74% | 26.4 | 36.8 | 10.4 | 32.3 | 852.72 | 1188.64 | 335.92 | Undertracking
FSC | Beeckman, Guido | NA PrIME Box Elder - combined alternative | PG23P05456 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.19989 | 0 | -0.19989 | 0% | 36.78 | 0 | -36.78 | 14.53 | 534.4134 | 0 | -534.4134 | No Plan
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Del Rosario, Maria Katrina | 60074237 | Bacay, Jessica Mae R. | L8 | L5 | Philippines | 0 | 0.07 | 0.07 | 0% | 0 | 12.88 | 12.88 | 33.58 | 0 | 432.5104 | 432.5104 | No Tracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Salazar, Ruth Mary | 11772056 | Torrentes, Etty | L8 | L5 | Costa Rica | 0.25 | 0.23 | -0.02 | 108.7% | 46 | 42.32 | -3.68 | 45.58 | 2096.68 | 1928.9456 | -167.7344 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Mejia, Ervene Albert H. | 11717033 | Chua, Chester | L6 | L3 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 14.53 | 767.184 | 802.056 | 34.872 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Del Rosario, Maria Katrina | 11716206 | San Juan, Rosechel Joy | L6 | L3 | Philippines | 0.2 | 0.1 | -0.1 | 195.7% | 36 | 18.4 | -17.6 | 14.53 | 523.08 | 267.352 | -255.728 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Mendenueta, Ismael | 11580446 | Legaspi, Mark Cleo | L7 | L4 | Philippines | 0.25 | 0.3 | 0.05 | 83.33% | 46 | 55.2 | 9.2 | 20.51 | 943.46 | 1132.152 | 188.692 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Arce, Karla Patricia R. | 11551878 | Aquino, Anne Marinel | L8 | L5 | Philippines | 0.5 | 0.55 | 0.05 | 90.91% | 92 | 101.2 | 9.2 | 33.58 | 3089.36 | 3398.296 | 308.936 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Madrilejo, Nathaniel | 11551116 | Mones, Angelica | L7 | L4 | Philippines | 0.22 | 0.24 | 0.02 | 89.92% | 39.71 | 44.16 | 4.45 | 20.51 | 814.4521 | 905.7216 | 91.2695 | On Track
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Abutal, Joseph Ryan A. | 21963841 | Ortiz, Ronaline D. | L7 | L4 | Philippines | 0.06 | 0.1 | 0.04 | 56.52% | 10.4 | 18.4 | 8 | 20.51 | 213.304 | 377.384 | 164.08 | Undertracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Bonilla, Johan Stick | 21838027 | Roldan, Melania De Los Angeles | L8 | L5 | Costa Rica | 0.52 | 1 | 0.48 | 52.17% | 96 | 184 | 88 | 45.58 | 4375.68 | 8386.72 | 4011.04 | Undertracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Bordey-Choi, Iris O. | 21051361 | Nasayao, Je-Marie Sanchez | L8 | L5 | Philippines | 0.09 | 0.3 | 0.21 | 28.99% | 16 | 55.2 | 39.2 | 33.58 | 537.28 | 1853.616 | 1316.336 | Undertracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Caldez, Stan Steve Philip Sarmiento | 11745487 | Rosales, Angelica | L6 | L3 | Philippines | 0.14 | 0.3 | 0.16 | 47.83% | 26.4 | 55.2 | 28.8 | 14.53 | 383.592 | 802.056 | 418.464 | Undertracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Cua, Jon Russell T. | 11707516 | Buenafe, Steven Vincent | L6 | L3 | Philippines | 0.23 | 0.4 | 0.17 | 57.07% | 42 | 73.6 | 31.6 | 14.53 | 610.26 | 1069.408 | 459.148 | Undertracking
FSC | Beeckman, Guido | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05456_NA PrIME Box Elder - combined alternative offer | PG23P05456 | Abutal, Joseph Ryan A. | 11582299 | Kintanar, Kennard | L6 | L3 | Philippines | 0.06 | 0.1 | 0.04 | 56.52% | 10.4 | 18.4 | 8 | 14.53 | 151.112 | 267.352 | 116.24 | Undertracking
FSC | Burgess, Darren | SPPO Massive Change Tool – Purch Consultant | PG22P05322 | Yasay, Eugene Baldivino | 60094260 | Atacador Jr., Antonio | L9 | L6 | Philippines | 0.41304 | 0 | -0.41304 | 0% | 76 | 0 | -76 | 48.19 | 3662.44 | 0 | -3662.44 | No Plan
FSC | Burgess, Darren | R2R SCA Application Manager Base CFAL | PG22P04782 | Chua, Jan Charmaine Pe | 60023822 | Cruz, Paolo Raphael S. | L8 | L5 | Philippines | 0.035326 | 0 | -0.035326 | 0% | 6.5 | 0 | -6.5 | 33.58 | 218.27 | 0 | -218.27 | No Plan
FSC | Burgess, Darren | HP Export Warehouse Move to LG | PG23P05540 | Arce, Karla Patricia R. | 21744358 | Caballero, Chrina Angela Dimayuga | L8 | L5 | Philippines | 0.027174 | 0 | -0.027174 | 0% | 5 | 0 | -5 | 33.58 | 167.9 | 0 | -167.9 | No Plan
FSC | Burgess, Darren | R2R SCA Application Manager Base CFAL | PG22P04782 | Jarabelo, Angela Bernadette Santos | 11739084 | Maderal, Debbie | L6 | L3 | Philippines | 0.19565 | 0 | -0.19565 | 0% | 36 | 0 | -36 | 14.53 | 523.08 | 0 | -523.08 | No Plan
FSC | Burgess, Darren | Monorail Security Remediation in Louveira | PG23P05481 | Bonilla, Johan Stick | 11721629 | Ramirez, Melissa | L6 | L3 | Costa Rica | 0.043478 | 0 | -0.043478 | 0% | 8 | 0 | -8 | 25.31 | 202.48 | 0 | -202.48 | No Plan
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05578_PrIME WMS PP and SE Support | PG23P05578 | Arce, Karla Patricia R. | 21971943 | Nicolas, Jadea Ann | L13 | L5 | Philippines | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 33.58 | 0 | 926.808 | 926.808 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04948_Connectivity Application Managers – FY23 | PG22P04948 | Requesto, Ryann Escobido | 21825411 | Reburiano, Vicente Juvy M. | L7 | L4 | Philippines | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 20.51 | 0 | 3773.84 | 3773.84 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Muralidharan, Varadha Narayanan | 21777898 | Kumar P, Senthil | L5 | L2 | India | 0 | 1 | 1 | 0% | 0 | 207 | 207 |  | 0 | 0 | 0 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Rodriguez, Alphonse Joseph V. | 11705603 | Paulino, Spenzer | L6 | L3 | Philippines | 0 | 0.05 | 0.05 | 0% | 0 | 9.2 | 9.2 | 14.53 | 0 | 133.676 | 133.676 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05420_SCA Application Manager Turkey Variance Tools ABAP | PG23P05420 | Radam, Rodrigo D. | 11547419 | Palomo, Romlyn F. | L7 | L4 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 20.51 | 0 | 377.384 | 377.384 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Daley, Gary | 3068129 | Mckie, Joseph | L8 | L5 | United Kingdom | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 106.08 | 0 | 3903.744 | 3903.744 | No Tracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04948_Connectivity Application Managers – FY23 | PG22P04948 | Requesto, Ryann Escobido | 60026108 | Relosa, Rachel | L8 | L5 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 33.58 | 5104.16 | 6178.72 | 1074.56 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Chua, Jan Charmaine Pe | 60023822 | Cruz, Paolo Raphael S. | L8 | L5 | Philippines | 0.47 | 0.5 | 0.03 | 94.57% | 87 | 92 | 5 | 33.58 | 2921.46 | 3089.36 | 167.9 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05547_HGP Stabilization Project Manager | PG23P05547 | Williams, Andrew R. | 21727430 | Escover, Joanne Joble | L9 | L6 | United Kingdom | 0.19 | 0.14 | -0.05 | 137.8% | 35.5 | 25.76 | -9.74 | 130.01 | 4615.355 | 3349.0576 | -1266.2974 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04949_Connectivity ABAP Developers – FY23 | PG22P04949 | Aloba, Eugene J. | 21477052 | Macasaet, Geoffrey Gomez | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Agustin, Rommel Rye Penafiel | 20348560 | Novenario, Ricardo Cabatbat | L9 | L6 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 48.19 | 4240.72 | 4433.48 | 192.76 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Sandanasamy, Naveen | 20256614 | V, Ramya | L7 | L4 | India | 0.46 | 0.5 | 0.04 | 91.3% | 94.5 | 103.5 | 9 | 17.33 | 1637.685 | 1793.655 | 155.97 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05548_Digital Go to Market | PG23P05548 | Rubinkowska, Joanna | 11770024 | Puchalska, Gabriela | L6 | L3 | Poland | 0.68 | 0.15 | -0.53 | 456.5% | 126 | 27.6 | -98.4 | 28.11 | 3541.86 | 775.836 | -2766.024 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Mejia, Ervene Albert H. | 11765805 | Gumpal, Kennedy Klein | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 91.3% | 16.8 | 18.4 | 1.6 | 14.53 | 244.104 | 267.352 | 23.248 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05548_Digital Go to Market | PG23P05548 | Rubinkowska, Joanna | 11755591 | Kokoszkiewicz, Pawel | L7 | L4 | Poland | 0.46 | 0.15 | -0.31 | 304.3% | 84 | 27.6 | -56.4 | 40.45 | 3397.8 | 1116.42 | -2281.38 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Espino, Karen Joyce A. | 11754267 | Tan, John Denmar A. | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P05068_FPSS Invoice Workflow Transformation Incremental Resources | PG22P05068 | Annapareddy, Kalyan | 11751593 | Padigapati, Jaya Simha | L7 | L4 | India | 0.96 | 1 | 0.04 | 95.65% | 198 | 207 | 9 | 17.33 | 3431.34 | 3587.31 | 155.97 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Annapareddy, Kalyan | 11749857 | Giri, Sajal | L6 | L3 | India | 0.72 | 0.75 | 0.03 | 95.65% | 148.5 | 155.25 | 6.75 | 11.75 | 1744.875 | 1824.1875 | 79.3125 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Cipriano, John Henry | 11749185 | Monleon, Charles Darwin | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Cipriano, John Henry | 11747420 | Patrocinio, John Carlo | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P05322_SPPO Massive Change Tool – Purch Consultant | PG22P05322 | Mendenueta, Ismael | 11746864 | Abu, Aaron Christina | L6 | L3 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 14.53 | 511.456 | 534.704 | 23.248 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Dela Cruz, Christine Joy | 11745542 | Vida, Joshua | L6 | L3 | Philippines | 1.03 | 1 | -0.03 | 103.3% | 190 | 184 | -6 | 14.53 | 2760.7 | 2673.52 | -87.18 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Radam, Rodrigo D. | 11740458 | Ramos, Trizia Anne | L6 | L3 | Philippines | 0.61 | 0.49 | -0.12 | 124.2% | 112 | 90.16 | -21.84 | 14.53 | 1627.36 | 1310.0248 | -317.3352 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05540_HP Export Warehouse Move to LG | PG23P05540 | Castro, Francis D. | 11738677 | Guevarra, Cobe Bryan | L6 | L3 | Philippines | 0.08 | 0.06 | -0.02 | 137.7% | 15.2 | 11.04 | -4.16 | 14.53 | 220.856 | 160.4112 | -60.4448 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | Rivera, Rizelle Lian R. | 11738051 | Perfecto, Hazel Mitzi | L6 | L3 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 14.53 | 511.456 | 534.704 | 23.248 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Dela Cruz, Christine Joy | 11737529 | Mendoza, Coleen | L6 | L3 | Philippines | 0.95 | 1 | 0.05 | 94.84% | 174.5 | 184 | 9.5 | 14.53 | 2535.485 | 2673.52 | 138.035 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Pacheco, Paul Robert Pascual | 11735518 | Buan, Marinela | L6 | L3 | Philippines | 0.05 | 0.05 | 0 | 91.3% | 8.4 | 9.2 | 0.8 | 14.53 | 122.052 | 133.676 | 11.624 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05513_Group Reporting Change Owner | PG23P05513 | Mendenueta, Ismael | 11731167 | Sabater, Conrad James | L6 | L3 | Philippines | 0.53 | 0.5 | -0.03 | 105.2% | 96.8 | 92 | -4.8 | 14.53 | 1406.504 | 1336.76 | -69.744 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_SATM_FSS_40_PG22P05089_ER GPS TCO ABAP Developer (CCR-151-B) | PG22P05089 | Mendoza, Camille Chavez | 11729192 | Polan, Christine | L6 | L3 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 14.53 | 1278.64 | 1336.76 | 58.12 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05551_Manila PFinsol Web Development | PG23P05551 | Castro, Francis D. | 11729145 | Mauleon, Giles Andrew | L6 | L3 | Philippines | 0.04 | 0.03 | -0.01 | 144.9% | 8 | 5.52 | -2.48 | 14.53 | 116.24 | 80.2056 | -36.0344 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Castro, Francis D. | 11729145 | Mauleon, Giles Andrew | L6 | L3 | Philippines | 0.08 | 0.1 | 0.02 | 82.61% | 15.2 | 18.4 | 3.2 | 14.53 | 220.856 | 267.352 | 46.496 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | Siababa, Mary Grace O. | 11722644 | Comia, Nelriel | L7 | L4 | Philippines | 0.25 | 0.3 | 0.05 | 82.61% | 45.6 | 55.2 | 9.6 | 20.51 | 935.256 | 1132.152 | 196.896 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Del Rosario, Maria Katrina | 11722059 | Lirio, Ana Luisa | L7 | L4 | Philippines | 0.11 | 0.1 | -0.01 | 110.3% | 20.3 | 18.4 | -1.9 | 20.51 | 416.353 | 377.384 | -38.969 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05551_Manila PFinsol Web Development | PG23P05551 | De Leon, Sanielle Anne C. | 11720124 | Talampas, Julius | L7 | L4 | Philippines | 0.15 | 0.14 | -0.01 | 108.7% | 28 | 25.76 | -2.24 | 20.51 | 574.28 | 528.3376 | -45.9424 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Annapareddy, Kalyan | 11718416 | Nikhitha, Kommi | L6 | L3 | India | 0.96 | 1 | 0.04 | 95.65% | 198 | 207 | 9 | 11.75 | 2326.5 | 2432.25 | 105.75 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04605_Project Management Support for SAP Security Cleanup – FY23 | PG22P04605 | Fu, Rina Joyce | 11717223 | Quito, Mark Angelo G. | L9 | L6 | Philippines | 0.85 | 1 | 0.15 | 85.33% | 157 | 184 | 27 | 48.19 | 7565.83 | 8866.96 | 1301.13 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | Rivera, Stephanie R. | 11716952 | Flores, Nikka Agatha | L6 | L3 | Philippines | 0.23 | 0.2 | -0.03 | 113% | 41.6 | 36.8 | -4.8 | 14.53 | 604.448 | 534.704 | -69.744 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_SATM_FSS_40_PG22P05089_ER GPS TCO ABAP Developer (CCR-151-B) | PG22P05089 | De Villa, Fatima Suzanne G. | 11715812 | Aguilar, Jonnuelle | L7 | L4 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 20.51 | 1804.88 | 1886.92 | 82.04 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Navarro, Joycee E. | 11713448 | Jurilla, John Harvey | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 14.53 | 232.48 | 267.352 | 34.872 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05420_SCA Application Manager Turkey Variance Tools ABAP | PG23P05420 | Orillaza, Noreen Olea Prila | 11707618 | Ramosa, Shiela | L8 | L5 | Philippines | 0.12 | 0.15 | 0.03 | 82.61% | 22.8 | 27.6 | 4.8 | 33.58 | 765.624 | 926.808 | 161.184 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P05068_FPSS Invoice Workflow Transformation Incremental Resources | PG22P05068 | Annapareddy, Kalyan | 11706785 | Arangi, Reshma | L6 | L3 | India | 0.91 | 1 | 0.09 | 91.3% | 189 | 207 | 18 | 11.75 | 2220.75 | 2432.25 | 211.5 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05429_P&G GBS University – Engagement Improvement | PG23P05429 | Andres, Lester Bartolome | 11706005 | Añago, Shaira Mae | L6 | L3 | Philippines | 0.22 | 0.25 | 0.03 | 86.96% | 40 | 46 | 6 | 14.53 | 581.2 | 668.38 | 87.18 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Mendenueta, Ismael | 11704230 | Nery, Earl Jantzen | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | Mendenueta, Ismael | 11704230 | Nery, Earl Jantzen | L6 | L3 | Philippines | 0.29 | 0.3 | 0.01 | 96.56% | 53.3 | 55.2 | 1.9 | 14.53 | 774.449 | 802.056 | 27.607 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Em, Karen Desiree Tan | 11703213 | Moral, Jingky | L7 | L4 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 20.51 | 3281.6 | 3773.84 | 492.24 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | San Juan, Mylene M. | 11618839 | Villanueva, Shannen Mae | L6 | L3 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 14.53 | 767.184 | 802.056 | 34.872 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Cipriano, John Henry | 11584592 | Domagas, Rajel Delta | L6 | L3 | Philippines | 1 | 1 | 0 | 100% | 184 | 184 | 0 | 14.53 | 2673.52 | 2673.52 | 0 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05537_China CSO Automation enhancement FY23-24 | PG23P05537 | Li, Bin | 11576485 | Chen, Yao | L7 | L4 | P.R.C. | 0.33 | 0.4 | 0.07 | 81.52% | 60 | 73.6 | 13.6 | 39.08 | 2344.8 | 2876.288 | 531.488 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Annapareddy, Kalyan | 11559888 | Srinivasan, Santosh | L7 | L4 | India | 0.91 | 1 | 0.09 | 91.3% | 189 | 207 | 18 | 17.33 | 3275.37 | 3587.31 | 311.94 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04785_R2R SCA Application Manager Base Cost Accounting | PG22P04785 | Radam, Rodrigo D. | 11547419 | Palomo, Romlyn F. | L7 | L4 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 20.51 | 1722.84 | 1886.92 | 164.08 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04785_R2R SCA Application Manager Base Cost Accounting | PG22P04785 | Jarabelo, Angela Bernadette Santos | 11545382 | Tantengco, Patrick Adrian A. | L7 | L4 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 20.51 | 1722.84 | 1886.92 | 164.08 | On Track
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Daley, Gary | 80024695 | Bassett, Michael | L9 | L6 | United Kingdom | 0.15 | 0.2 | 0.05 | 74.78% | 27.52 | 36.8 | 9.28 | 130.01 | 3577.8752 | 4784.368 | 1206.4928 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04949_Connectivity ABAP Developers – FY23 | PG22P04949 | Annapareddy, Kalyan | 60044230 | Gr, Ramachandran | L7 | L4 | India | 0.78 | 1 | 0.22 | 78.26% | 162 | 207 | 45 | 17.33 | 2807.46 | 3587.31 | 779.85 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Narendra Kalyani, | 60013580 | Zameer, Mohamed G. | L8 | L5 | India | 0.3 | 0.7 | 0.4 | 43.48% | 63 | 144.9 | 81.9 | 26.59 | 1675.17 | 3852.891 | 2177.721 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05551_Manila PFinsol Web Development | PG23P05551 | Tirol, Jenelyn Jean Ramos | 21967999 | Chua, Jillian Yasmin Chua | L14 | L6 | Philippines | 0.06 | 0.14 | 0.08 | 42.7% | 11 | 25.76 | 14.76 | 48.19 | 530.09 | 1241.3744 | 711.2844 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Chua, Jan Charmaine Pe | 21753918 | Ilan, Laarni Dawn Roa | L8 | L5 | Philippines | 0.26 | 0.5 | 0.24 | 52.17% | 48 | 92 | 44 | 33.58 | 1611.84 | 3089.36 | 1477.52 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P05068_FPSS Invoice Workflow Transformation Incremental Resources | PG22P05068 | Verma, Rahul | 21658647 | Jha, Bandana | L8 | L5 | India | 0.78 | 1 | 0.22 | 78.26% | 162 | 207 | 45 | 26.59 | 4307.58 | 5504.13 | 1196.55 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Williams, Andrew R. | 20417047 | Holmes, Steve | L9 | L6 | United Kingdom | 0.07 | 0.3 | 0.23 | 21.74% | 12 | 55.2 | 43.2 | 130.01 | 1560.12 | 7176.552 | 5616.432 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05429_P&G GBS University – Engagement Improvement | PG23P05429 | Reyes, Roderick Francisco | 20294888 | Uy, Precious L. | L14 | L6 | Philippines | 0.11 | 0.3 | 0.19 | 36.23% | 20 | 55.2 | 35.2 | 48.19 | 963.8 | 2660.088 | 1696.288 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Hilton, Gary | 20000936 | Lewis, David | L8 | L5 | United Kingdom | 0.28 | 0.5 | 0.22 | 56.52% | 52 | 92 | 40 | 106.08 | 5516.16 | 9759.36 | 4243.2 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05420_SCA Application Manager Turkey Variance Tools ABAP | PG23P05420 | Orillaza, Noreen Olea Prila | 11765189 | Arguelles, Athena | L6 | L3 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 14.53 | 2092.32 | 2673.52 | 581.2 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04782_R2R SCA Application Manager Base CFAL | PG22P04782 | Jarabelo, Angela Bernadette Santos | 11729840 | Umali, Princess Joy | L6 | L3 | Philippines | 0.14 | 0.2 | 0.06 | 71.74% | 26.4 | 36.8 | 10.4 | 14.53 | 383.592 | 534.704 | 151.112 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04785_R2R SCA Application Manager Base Cost Accounting | PG22P04785 | Jarabelo, Angela Bernadette Santos | 11729840 | Umali, Princess Joy | L6 | L3 | Philippines | 0.33 | 0.7 | 0.37 | 47.83% | 61.6 | 128.8 | 67.2 | 14.53 | 895.048 | 1871.464 | 976.416 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04968_E2Open Sprint Team | PG22P04968 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.2 | 0.3 | 0.1 | 67.03% | 37 | 55.2 | 18.2 | 20.51 | 758.87 | 1132.152 | 373.282 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05561_CM India Softech T&M Project | PG23P05561 | Del Rosario, Maria Katrina | 11716206 | San Juan, Rosechel Joy | L6 | L3 | Philippines | 0.05 | 0.1 | 0.05 | 47.83% | 8.8 | 18.4 | 9.6 | 14.53 | 127.864 | 267.352 | 139.488 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Chua, Jan Charmaine Pe | 11714162 | Manabat, Katherine Joy | L7 | L4 | Philippines | 0.17 | 0.7 | 0.53 | 24.84% | 32 | 128.8 | 96.8 | 20.51 | 656.32 | 2641.688 | 1985.368 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04782_R2R SCA Application Manager Base CFAL | PG22P04782 | Chua, Jan Charmaine Pe | 11707499 | Trinidad, Archie | L7 | L4 | Philippines | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 20.51 | 2297.12 | 3773.84 | 1476.72 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05578_PrIME WMS PP and SE Support | PG23P05578 | Curio, Francine Nicole Macoy | 11616383 | Dequilla, Ronina | L7 | L4 | Philippines | 0.02 | 0.07 | 0.05 | 23.29% | 3 | 12.88 | 9.88 | 20.51 | 61.53 | 264.1688 | 202.6388 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04783_R2R SCA Application Manager Base Rev and COPA | PG22P04783 | Radam, Rodrigo D. | 11580448 | Magdamit, Lois Yvonne Faye | L7 | L4 | Philippines | 0.23 | 0.3 | 0.07 | 78.26% | 43.2 | 55.2 | 12 | 20.51 | 886.032 | 1132.152 | 246.12 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04785_R2R SCA Application Manager Base Cost Accounting | PG22P04785 | Chua, Jan Charmaine Pe | 11580447 | Sañosa, Marjorie | L8 | L5 | Philippines | 0.87 | 2 | 1.13 | 43.48% | 160 | 368 | 208 | 33.58 | 5372.8 | 12357.44 | 6984.64 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Hernandez, Geline Anne Tamayo | 11554932 | Manuel, Rai Ann L. | L8 | L5 | Philippines | 0.02 | 0.15 | 0.13 | 14.49% | 4 | 27.6 | 23.6 | 33.58 | 134.32 | 926.808 | 792.488 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Tirol, Jenelyn Jean Ramos | 11547420 | Palmero, Florante | L10 | L6 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 48.19 | 6939.36 | 8866.96 | 1927.6 | Undertracking
FSC | Burgess, Darren | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04774_MADF AppMan, SharePoint Development and Security Services | PG22P04774 | Prathyusha Rani Miriyala, | 1415789 | Karuppiah, Senthil Kumar | L8 | L5 | India | 0.52 | 1 | 0.48 | 52.17% | 108 | 207 | 99 | 26.59 | 2871.72 | 5504.13 | 2632.41 | Undertracking
FSC | Capati, Alvin Joh | GBW SRU Services FY22 | PG22P04603 | Gorospe, Akhina Kim Z. | 60009259 | Magdame, Christian Jurick D. | L7 | L4 | Philippines | 0.88043 | 0 | -0.88043 | 0% | 162 | 0 | -162 | 20.51 | 3322.62 | 0 | -3322.62 | No Plan
FSC | Capati, Alvin Joh | GBW SRU Services FY22 | PG22P04603 | Gorospe, Akhina Kim Z. | 11712827 | Epan, Alecxis Jane | L6 | L3 | Philippines | 1.087 | 0 | -1.087 | 0% | 200 | 0 | -200 | 14.53 | 2906 | 0 | -2906 | No Plan
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Aggarwal, Rochak K. | 60100077 | Santos, Christian H. | L8 | L5 | Philippines | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 33.58 | 0 | 6178.72 | 6178.72 | No Tracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Tirol, Jenelyn Jean Ramos | 60085229 | Gorospe, Akhina Kim Z. | L13 | L5 | Philippines | 0 | 1.15 | 1.15 | 0% | 0 | 211.6 | 211.6 | 33.58 | 0 | 7105.528 | 7105.528 | No Tracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Gorospe, Akhina Kim Z. | 60009259 | Magdame, Christian Jurick D. | L7 | L4 | Philippines | 0 | 0.61 | 0.61 | 0% | 0 | 112.24 | 112.24 | 20.51 | 0 | 2302.0424 | 2302.0424 | No Tracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Gorospe, Akhina Kim Z. | 11713116 | Mallare, John Cloie | L7 | L4 | Philippines | 0 | 0.61 | 0.61 | 0% | 0 | 112.24 | 112.24 | 20.51 | 0 | 2302.0424 | 2302.0424 | No Tracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Radosz, Jacek T. | 11708149 | Sadowski, Dariusz | L6 | L3 | Poland | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 28.11 | 0 | 2586.12 | 2586.12 | No Tracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Tirol, Jenelyn Jean Ramos | 60090251 | Estrada, Alvin G. | L13 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Dela Cruz, Honey Dianne P. | 60082822 | Balajadia, Nellyssa Marie T. | L7 | L4 | Philippines | 0.43 | 0.5 | 0.07 | 86.96% | 80 | 92 | 12 | 20.51 | 1640.8 | 1886.92 | 246.12 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 60038317 | Pangan, John Nicole T. | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11767256 | Chan, Danielle Rey | L6 | L3 | Philippines | 1.05 | 1 | -0.05 | 104.6% | 192.5 | 184 | -8.5 | 14.53 | 2797.025 | 2673.52 | -123.505 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Jakkam, Subrahmanyam | 11753728 | Sudhir Banode, Priyanka | L6 | L3 | India | 0.72 | 0.25 | -0.47 | 287% | 148.5 | 51.75 | -96.75 | 11.75 | 1744.875 | 608.0625 | -1136.8125 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Jakkam, Subrahmanyam | 11753725 | Ga, Majunu | L6 | L3 | India | 0.72 | 0.25 | -0.47 | 287% | 148.5 | 51.75 | -96.75 | 11.75 | 1744.875 | 608.0625 | -1136.8125 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Orillaza, Noreen Olea Prila | 11723210 | Sael, Stephanie Joyce | L6 | L3 | Philippines | 0.25 | 0.3 | 0.05 | 82.61% | 45.6 | 55.2 | 9.6 | 14.53 | 662.568 | 802.056 | 139.488 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Gorospe, Akhina Kim Z. | 11713670 | Mayrena, Kimberly Hester | L6 | L3 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 14.53 | 2324.8 | 2673.52 | 348.72 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11710914 | Equila, Camille Joglen U. | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Gorospe, Akhina Kim Z. | 11707616 | Hayen, Lyka Mae | L6 | L3 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 14.53 | 2324.8 | 2673.52 | 348.72 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Jakkam, Subrahmanyam | 11706623 | Naidu, Lakshmi Priyanka | L6 | L3 | India | 0.87 | 1 | 0.13 | 86.96% | 180 | 207 | 27 | 11.75 | 2115 | 2432.25 | 317.25 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11703124 | Libaton, Ellen Joyce L. | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11614726 | Chan, Karl Edwinson | L6 | L3 | Philippines | 1.08 | 1 | -0.08 | 107.6% | 198 | 184 | -14 | 14.53 | 2876.94 | 2673.52 | -203.42 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11595977 | Javier, Louis Jomari A. | L7 | L4 | Philippines | 0.85 | 1 | 0.15 | 84.78% | 156 | 184 | 28 | 20.51 | 3199.56 | 3773.84 | 574.28 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Tolentino, Ericka May Robles | 11584596 | Sequina, Honey Rizza | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Estrada, Alvin G. | 11547765 | Santos, Raphael Lester D. | L7 | L4 | Philippines | 0.89 | 1 | 0.11 | 89.13% | 164 | 184 | 20 | 20.51 | 3363.64 | 3773.84 | 410.2 | On Track
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Onggon, Ann Gellie Copiaco | 60042237 | Sta. Ana, Kevin Ramon A. | L8 | L5 | Philippines | 0.3 | 0.5 | 0.2 | 60.87% | 56 | 92 | 36 | 33.58 | 1880.48 | 3089.36 | 1208.88 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Eslabra, Giovanna Perez | 60023989 | Capati, Alvin J. | L9 | L6 | Philippines | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 48.19 | 5011.76 | 8866.96 | 3855.2 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Onggon, Ann Gellie Copiaco | 21771026 | Harlea, Maria Cecilia V. | L8 | L5 | Philippines | 0.35 | 0.5 | 0.15 | 69.57% | 64 | 92 | 28 | 33.58 | 2149.12 | 3089.36 | 940.24 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Brodeth, Carlo Hipolito | 21600742 | Lademora, Domingo D. | L8 | L5 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 33.58 | 4835.52 | 6178.72 | 1343.2 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Jakkam, Subrahmanyam | 20377927 | Marrikunta, Venkata | L8 | L5 | India | 0.7 | 1 | 0.3 | 69.57% | 144 | 207 | 63 | 26.59 | 3828.96 | 5504.13 | 1675.17 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Onggon, Ann Gellie Copiaco | 11748981 | Alviar, Sheila Marie | L7 | L4 | Philippines | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 20.51 | 2789.36 | 3773.84 | 984.48 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04603_GBW SRU Services FY22 | PG22P04603 | Jakkam, Subrahmanyam | 11706512 | A, Nimisha | L6 | L3 | India | 0.78 | 1 | 0.22 | 78.26% | 162 | 207 | 45 | 11.75 | 1903.5 | 2432.25 | 528.75 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Tolentino, Ericka May Robles | 11584434 | Cancino, Gerric Bonn | L6 | L3 | Philippines | 0.5 | 1.5 | 1 | 33.33% | 92 | 276 | 184 | 14.53 | 1336.76 | 4010.28 | 2673.52 | Undertracking
FSC | Capati, Alvin Joh | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04808_SPO Deployment & Operations Services FY22 | PG22P04808 | Tadakaluri, Vijay Kumar | 1513166 | Kamalapuram, Anil K. | L7 | L4 | India | 0.43 | 1 | 0.57 | 43.48% | 90 | 207 | 117 | 17.33 | 1559.7 | 3587.31 | 2027.61 | Undertracking
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Reyes, Roderick Francisco | 20369409 | Desengano, Lester U. | L9 | L6 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 48.19 | 0 | 886.696 | 886.696 | No Tracking
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Crucena, Mark Jayson S. | 11617650 | Santos, Joshua | L6 | L3 | Philippines | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 14.53 | 0 | 668.38 | 668.38 | No Tracking
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Brodeth, Carlo Hipolito | 60105048 | Alcanar, Ronalyn A. | L8 | L5 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 33.58 | 2552.08 | 3089.36 | 537.28 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04821_OTC SA Attachment B.2.3 C- 5- OTC ASIA RPA | PG22P04821 | Gonzales, Melvin Katigbak | 21379594 | Dumalaon, Anthony Luego | L8 | L5 | Philippines | 0.5 | 0.5 | 0 | 100.5% | 92.5 | 92 | -0.5 | 33.58 | 3106.15 | 3089.36 | -16.79 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Teo, Jenny Anne T. | 20309183 | Taborda, Juan Jason Sevilla | L9 | L6 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 48.19 | 7324.88 | 8866.96 | 1542.08 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04821_OTC SA Attachment B.2.3 C- 5- OTC ASIA RPA | PG22P04821 | Marana, Brian Diamante | 11752323 | Sarte, John Davis | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 96.47% | 177.5 | 184 | 6.5 | 20.51 | 3640.525 | 3773.84 | 133.315 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Mendenueta, Ismael | 11719965 | Manalo, Alyssa Gia | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 91.3% | 16.8 | 18.4 | 1.6 | 14.53 | 244.104 | 267.352 | 23.248 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Onggon, Ann Gellie Copiaco | 11616262 | Butay, Christian | L7 | L4 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 20.51 | 1804.88 | 1886.92 | 82.04 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_TMTL_AUT_74_PG22P04807_ DXC KNIME - OM Application Project FY22-23 | PG22P04807 | Ediga, Chandra | 11606668 | M, Deepika | L7 | L4 | India | 0.96 | 1 | 0.04 | 95.65% | 198 | 207 | 9 | 17.33 | 3431.34 | 3587.31 | 155.97 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Yasay, Eugene Baldivino | 11596006 | Marasigan, Ma. Lois Celine | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Crucena, Mark Jayson S. | 11591632 | Salazar, Arjan Russel V. | L7 | L4 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 20.51 | 861.42 | 943.46 | 82.04 | On Track
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Radosz, Jacek T. | 20411550 | Wójcik, Dariusz R. | L8 | L5 | Poland | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 54.93 | 7470.48 | 10107.12 | 2636.64 | Undertracking
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Onggon, Ann Gellie Copiaco | 11732061 | Tulop, Christian Rey | L7 | L4 | Philippines | 0.37 | 0.5 | 0.13 | 73.91% | 68 | 92 | 24 | 20.51 | 1394.68 | 1886.92 | 492.24 | Undertracking
FSC | Castillo, Andres | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04454_SCV and VSA Service | PG22P04454 | Onggon, Ann Gellie Copiaco | 11610606 | De Jesus, Roni Rose | L8 | L5 | Philippines | 0.46 | 1 | 0.54 | 46.47% | 85.5 | 184 | 98.5 | 33.58 | 2871.09 | 6178.72 | 3307.63 | Undertracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Anguiano, Rodolfo | 81093825 | Siefritz, Michael | L9 | L6 | United States | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 130.7 | 0 | 6012.2 | 6012.2 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Hernandez, Geline Anne Tamayo | 75010535 | Oribello, John V. | L9 | L6 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 48.19 | 0 | 886.696 | 886.696 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gogulamatham, Raju | 75003675 | Malagaveli Vankadari, Sricharan | L14 | L6 | India | 0 | 0.25 | 0.25 | 0% | 0 | 51.75 | 51.75 | 38.22 | 0 | 1977.885 | 1977.885 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Anguiano, Rodolfo | 21619448 | Arab, Imran M. | L9 | L6 | United States | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 130.7 | 0 | 6012.2 | 6012.2 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Hernandez, Geline Anne Tamayo | 20397638 | Recto, Alvin Bernal | L9 | L6 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 48.19 | 0 | 886.696 | 886.696 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gerolaga, Kirstie Ida May Espiritu Santo | 20239826 | Verzosa, Mark Jhamil Jimenea | L9 | L6 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 48.19 | 0 | 886.696 | 886.696 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Lecuyer, Alexandra | 20037606 | Lips, Franky | L8 | L5 | Belgium | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 136.55 | 0 | 6281.3 | 6281.3 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Ozkan, Onur | 20013558 | Chakkoria, Shibu | L15 | L6 | United Kingdom | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 130.01 | 0 | 5980.46 | 5980.46 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gali, Bapavani | 11715307 | Sharma, Somya | L6 | L3 | India | 0 | 1 | 1 | 0% | 0 | 207 | 207 | 11.75 | 0 | 2432.25 | 2432.25 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Melvin, Presencia Malathi | 11712877 | Srinivas, Uppari | L6 | L3 | India | 0 | 1 | 1 | 0% | 0 | 207 | 207 | 11.75 | 0 | 2432.25 | 2432.25 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Melvin, Presencia Malathi | 11703582 | C S, Divyashree | L6 | L3 | India | 0 | 1 | 1 | 0% | 0 | 207 | 207 | 11.75 | 0 | 2432.25 | 2432.25 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gogulamatham, Raju | 11613596 | Kumar, Shobha Nand | L8 | L5 | India | 0 | 0.25 | 0.25 | 0% | 0 | 51.75 | 51.75 | 26.59 | 0 | 1376.0325 | 1376.0325 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gali, Bapavani | 11591840 | Vasudevan, Swaroop | L8 | L5 | India | 0 | 0.25 | 0.25 | 0% | 0 | 51.75 | 51.75 | 26.59 | 0 | 1376.0325 | 1376.0325 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Castro, Francis D. | 11578970 | Fonacier, Santiago Luis Iii | L9 | L6 | Philippines | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 48.19 | 0 | 8866.96 | 8866.96 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Orillaza, Noreen Olea Prila | 11567108 | Eugenio, Marc Vincent | L8 | L5 | Philippines | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 33.58 | 0 | 1544.68 | 1544.68 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Alam, Badre | 11557377 | D, Shivaprasad | L8 | L5 | India | 0 | 0.1 | 0.1 | 0% | 0 | 20.7 | 20.7 | 26.59 | 0 | 550.413 | 550.413 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Hernandez, Geline Anne Tamayo | 11549881 | Gumarang, Jerome | L8 | L5 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 33.58 | 0 | 617.872 | 617.872 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Ozkan, Onur | 671741 | Knox, Steven R. | L10 | L6 | United States | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 130.7 | 0 | 6012.2 | 6012.2 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Op De Beeck, Jan | 449008 | Cabouctzis, Nektarios | L9 | L6 | Belgium | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 153.18 | 0 | 7046.28 | 7046.28 | No Tracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Fu, Rina Joyce | 21761653 | Rivera, Stephanie R. | L13 | L5 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 33.58 | 2820.72 | 3089.36 | 268.64 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Karababa, Ceyhun | 21754186 | Cipkova, Miriama | L8 | L5 | Slovakia | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 59.8 | 5262.4 | 5501.6 | 239.2 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Orillaza, Noreen Olea Prila | 21647428 | Agner, Mary Joy Jallorina | L7 | L4 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 20.51 | 3281.6 | 3773.84 | 492.24 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Nella, Naveen Kumar | 11754329 | Thummala, Vivek | L8 | L5 | India | 0.96 | 0.91 | -0.05 | 105.1% | 198 | 188.37 | -9.63 | 26.59 | 5264.82 | 5008.7583 | -256.0617 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gali, Bapavani | 11753678 | Malli Reddy, Vamsidhar Reddy | L6 | L3 | India | 0.46 | 0.5 | 0.04 | 91.3% | 94.5 | 103.5 | 9 | 11.75 | 1110.375 | 1216.125 | 105.75 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gogulamatham, Raju | 11745140 | Chalumuri, Raghubabu | L8 | L5 | India | 0.96 | 0.25 | -0.71 | 382.6% | 198 | 51.75 | -146.25 | 26.59 | 5264.82 | 1376.0325 | -3888.7875 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Rivera, Rizelle Lian R. | 11738598 | Lopez, Dominic Joshua | L7 | L4 | Philippines | 0.48 | 0.5 | 0.02 | 95.11% | 87.5 | 92 | 4.5 | 20.51 | 1794.625 | 1886.92 | 92.295 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Durandar, Janelle M. | 11729926 | Bugaoan, Gerald M. | L7 | L4 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 20.51 | 721.952 | 754.768 | 32.816 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Siababa, Mary Grace O. | 11722644 | Comia, Nelriel | L7 | L4 | Philippines | 0.17 | 0.2 | 0.03 | 82.61% | 30.4 | 36.8 | 6.4 | 20.51 | 623.504 | 754.768 | 131.264 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Mondarte, Lloyd | 11706970 | Llorente, Mark Jason | L7 | L4 | Philippines | 0.22 | 0.2 | -0.02 | 108.7% | 40 | 36.8 | -3.2 | 20.51 | 820.4 | 754.768 | -65.632 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Durandar, Janelle M. | 11582329 | Trinidad, Leo Anthony A. | L7 | L4 | Philippines | 0.21 | 0.25 | 0.04 | 82.61% | 38 | 46 | 8 | 20.51 | 779.38 | 943.46 | 164.08 | On Track
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Orillaza, Noreen Olea Prila | 60089255 | Derramas Jr., Antonio | L9 | L6 | Philippines | 0.07 | 0.25 | 0.18 | 26.09% | 12 | 46 | 34 | 48.19 | 578.28 | 2216.74 | 1638.46 | Undertracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Gali, Bapavani | 20366659 | Jogu, Siddivinesh | L8 | L5 | India | 0.12 | 0.2 | 0.08 | 60.87% | 25.2 | 41.4 | 16.2 | 26.59 | 670.068 | 1100.826 | 430.758 | Undertracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Brunn, Michael | 20001037 | Ahuchogu, Chukwuma | L9 | L6 | Germany | 0.35 | 0.55 | 0.2 | 63.24% | 64 | 101.2 | 37.2 | 164.31 | 10515.84 | 16628.172 | 6112.332 | Undertracking
FSC | Chakkoria, Shibu | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05439_H1P Version Upgrade | PG23P05439 | Antonio, Sarah Mangalinao | 11717449 | Acapulco, Niko | L8 | L5 | Philippines | 0.13 | 0.5 | 0.37 | 26.09% | 24 | 92 | 68 | 33.58 | 805.92 | 3089.36 | 2283.44 | Undertracking
FSC | Desengano, Lester | Deliver_AMS_PG_APP_TMTL_ESC_70_PG23P05459_Service Management Support for ALOHA LIGHT | PG23P05459 | Crucena, Mark Jayson S. | 11582038 | Bajan, Earl | L7 | L4 | Philippines | 0.22 | 0.25 | 0.03 | 86.96% | 40 | 46 | 6 | 20.51 | 820.4 | 943.46 | 123.06 | On Track
FSC | Desengano, Lester | Deliver_AMS_PG_APP_TMTL_ESC_70_PG23P05459_Service Management Support for ALOHA LIGHT | PG23P05459 | Yasay, Eugene Baldivino | 20339024 | David, Kristine Lauren Silvallana | L8 | L5 | Philippines | 0.27 | 0.35 | 0.08 | 77.64% | 50 | 64.4 | 14.4 | 33.58 | 1679 | 2162.552 | 483.552 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04195_TS Product Support - TCF | PG22P04195 | Ong, Maurice Edison L. | 60071614 | Cua, Jon Russell T. | L13 | L5 | Philippines | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 33.58 | 0 | 3089.36 | 3089.36 | No Tracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Ozkan, Onur | 21648136 | Patron, Tomer | L14 | L6 | Israel | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 141.11 | 0 | 6491.06 | 6491.06 | No Tracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05039_SAP PO RFC support | PG22P05039 | Kalinin, Sergey | 11739148 | Gordienko, Vlada | L7 | L4 | Serbia | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 35.66 | 0 | 1640.36 | 1640.36 | No Tracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Tadakaluri, Vijay Kumar | 11599706 | Chakraborty, Ashim | L7 | L4 | India | 0 | 0.25 | 0.25 | 0% | 0 | 51.75 | 51.75 | 17.33 | 0 | 896.8275 | 896.8275 | No Tracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04640_JENGA TS Extreme support | PG22P04640 | Sande, Arden Paul E. | 11597109 | Barrion, Mariz | L7 | L4 | Philippines | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 20.51 | 0 | 566.076 | 566.076 | No Tracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05039_SAP PO RFC support | PG22P05039 | Wu, Qiang | 75008297 | Li, Jing | L7 | L4 | P.R.C. | 0.26 | 0.3 | 0.04 | 86.96% | 48 | 55.2 | 7.2 | 39.08 | 1875.84 | 2157.216 | 281.376 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Orillaza, Noreen Olea Prila | 70001199 | Panlilio, Harold B. | L9 | L6 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 48.19 | 4240.72 | 4433.48 | 192.76 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Ong, Maurice Edison L. | 60071614 | Cua, Jon Russell T. | L13 | L5 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 33.58 | 2955.04 | 3089.36 | 134.32 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04199_ JENGA TS Product Support - TMS | PG22P04199 | Antonio, Sarah Mangalinao | 21963630 | Tan, Charles Clinton Basilio | L8 | L5 | Philippines | 0.25 | 0.25 | 0 | 100% | 46 | 46 | 0 | 33.58 | 1544.68 | 1544.68 | 0 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04187_TS Product Support - Atlas (CCR-134) | PG22P04187 | Maulbetsch, Douglas W. | 21373559 | Arguedas, Jose Guillermo | L14 | L6 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 61.48 | 5410.24 | 5656.16 | 245.92 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04199_ JENGA TS Product Support - TMS | PG22P04199 | Ong, Maurice Edison L. | 20351673 | Custodio, Adrian Agustin Romero | L9 | L6 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 48.19 | 4240.72 | 4433.48 | 192.76 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04179_TS Product Support OBLB (CCR-134) | PG22P04179 | Heglas, Ivan | 20140432 | Adamik, Norbert | L10 | L6 | Slovakia | 0.88 | 1 | 0.13 | 87.5% | 161 | 184 | 23 | 73.02 | 11756.22 | 13435.68 | 1679.46 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04202_ JENGA TS Product Support Customs FY2021 | PG22P04202 | Brunn, Michael | 20078172 | Zimmermann, Marcus | L8 | L5 | Germany | 0.21 | 0.25 | 0.04 | 82.61% | 38 | 46 | 8 | 139.48 | 5300.24 | 6416.08 | 1115.84 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04202_ JENGA TS Product Support Customs FY2021 | PG22P04202 | Shelar, Pandit | 20001029 | Thieme, Chad | L8 | L5 | United States | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 103.6 | 1823.36 | 1906.24 | 82.88 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04653_JENGA TS Product Support SHX FY22231 | PG22P04653 | Shelar, Pandit | 20001029 | Thieme, Chad | L8 | L5 | United States | 0.86 | 0.7 | -0.16 | 123% | 158.4 | 128.8 | -29.6 | 103.6 | 16410.24 | 13343.68 | -3066.56 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04187_TS Product Support - Atlas (CCR-134) | PG22P04187 | Brunn, Michael | 20000574 | Biegel, Jochen | L10 | L6 | Germany | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 164.31 | 7229.64 | 7558.26 | 328.62 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04195_TS Product Support - TCF | PG22P04195 | Salazar, Ruth Mary | 11757356 | Arrieta, Esteban | L9 | L6 | Costa Rica | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 61.48 | 5656.16 | 5656.16 | 0 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04202_ JENGA TS Product Support Customs FY2021 | PG22P04202 | Madrilejo, Nathaniel | 11748408 | Lindog, Nikki | L7 | L4 | Philippines | 0.21 | 0.25 | 0.04 | 84.78% | 39 | 46 | 7 | 20.51 | 799.89 | 943.46 | 143.57 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04640_JENGA TS Extreme support | PG22P04640 | Farrales, Meryll Bernadette R. | 11727802 | Talens, Justin Rustan | L6 | L3 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 14.53 | 1104.28 | 1336.76 | 232.48 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04199_ JENGA TS Product Support - TMS | PG22P04199 | Madrilejo, Nathaniel | 11709310 | Fabia, Jerica Mae M. | L7 | L4 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 20.51 | 1804.88 | 1886.92 | 82.04 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04640_JENGA TS Extreme support | PG22P04640 | Farrales, Meryll Bernadette R. | 11620826 | Encarnacion, Blu | L6 | L3 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 14.53 | 1104.28 | 1336.76 | 232.48 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04179_TS Product Support OBLB (CCR-134) | PG22P04179 | Bansal, Mukesh Kumar | 11603174 | C, Kavya Janardhanan | L7 | L4 | India | 0.43 | 0.5 | 0.07 | 86.96% | 90 | 103.5 | 13.5 | 17.33 | 1559.7 | 1793.655 | 233.955 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04202_ JENGA TS Product Support Customs FY2021 | PG22P04202 | Bansal, Mukesh Kumar | 11603174 | C, Kavya Janardhanan | L7 | L4 | India | 0.43 | 0.5 | 0.07 | 86.96% | 90 | 103.5 | 13.5 | 17.33 | 1559.7 | 1793.655 | 233.955 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04187_TS Product Support - Atlas (CCR-134) | PG22P04187 | Mendenueta, Ismael | 11582115 | Kimberly, Madera | L7 | L4 | Philippines | 0.62 | 0.6 | -0.02 | 103.8% | 114.6 | 110.4 | -4.2 | 20.51 | 2350.446 | 2264.304 | -86.142 | On Track
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05257_Customs Digitization Wave 2 T&M | PG22P05257 | Castro, Francis D. | 60033345 | Bitantes, Kristen-Ann K. | L13 | L5 | Philippines | 0.06 | 0.15 | 0.09 | 39.13% | 10.8 | 27.6 | 16.8 | 33.58 | 362.664 | 926.808 | 564.144 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04199_ JENGA TS Product Support - TMS | PG22P04199 | Ong, Maurice Edison L. | 20371837 | So, Richardson Nehemiah Chua | L9 | L6 | Philippines | 0.26 | 0.5 | 0.24 | 52.17% | 48 | 92 | 44 | 48.19 | 2313.12 | 4433.48 | 2120.36 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05257_Customs Digitization Wave 2 T&M | PG22P05257 | Brunn, Michael | 20078172 | Zimmermann, Marcus | L8 | L5 | Germany | 0.39 | 0.5 | 0.11 | 78.26% | 72 | 92 | 20 | 139.48 | 10042.56 | 12832.16 | 2789.6 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04187_TS Product Support - Atlas (CCR-134) | PG22P04187 | Postic, Mihajlo | 20006708 | Psarras, Yannis | L8 | L5 | Greece | 0.07 | 0.15 | 0.08 | 48.91% | 13.5 | 27.6 | 14.1 | 98.9 | 1335.15 | 2729.64 | 1394.49 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05039_SAP PO RFC support | PG22P05039 | Postic, Mihajlo | 20006708 | Psarras, Yannis | L8 | L5 | Greece | 0.17 | 0.75 | 0.58 | 22.83% | 31.5 | 138 | 106.5 | 98.9 | 3115.35 | 13648.2 | 10532.85 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Ong, Maurice Edison L. | 20001119 | Baldric, Edward Gene Osi | L9 | L6 | Philippines | 0.3 | 0.5 | 0.2 | 60.87% | 56 | 92 | 36 | 48.19 | 2698.64 | 4433.48 | 1734.84 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04640_JENGA TS Extreme support | PG22P04640 | Farrales, Meryll Bernadette R. | 11739099 | Politico, Jejomar | L6 | L3 | Philippines | 0.63 | 0.8 | 0.17 | 78.26% | 115.2 | 147.2 | 32 | 14.53 | 1673.856 | 2138.816 | 464.96 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05039_SAP PO RFC support | PG22P05039 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.14 | 0.2 | 0.06 | 71.74% | 26.4 | 36.8 | 10.4 | 14.53 | 383.592 | 534.704 | 151.112 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04179_TS Product Support OBLB (CCR-134) | PG22P04179 | Agrawal, Ashish K. | 11594037 | Borade, Siddhesh | L7 | L4 | India | 0.3 | 0.5 | 0.2 | 60.87% | 63 | 103.5 | 40.5 | 17.33 | 1091.79 | 1793.655 | 701.865 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04653_JENGA TS Product Support SHX FY22231 | PG22P04653 | Agrawal, Ashish K. | 11594037 | Borade, Siddhesh | L7 | L4 | India | 0.3 | 0.5 | 0.2 | 60.87% | 63 | 103.5 | 40.5 | 17.33 | 1091.79 | 1793.655 | 701.865 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04640_JENGA TS Extreme support | PG22P04640 | Rayo, Anthony Vizmanos | 11571145 | Dacalcap, Dannierose Z. | L6 | L3 | Philippines | 0.07 | 0.2 | 0.13 | 35.87% | 13.2 | 36.8 | 23.6 | 14.53 | 191.796 | 534.704 | 342.908 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04199_ JENGA TS Product Support - TMS | PG22P04199 | Antonio, Sarah Mangalinao | 11557181 | Gutierrez, Kristine | L13 | L5 | Philippines | 0.15 | 0.25 | 0.1 | 60.87% | 28 | 46 | 18 | 33.58 | 940.24 | 1544.68 | 604.44 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04188_ TS Product Support - LM (CCR-134) | PG22P04188 | Gliewe, Lars | 2701038 | Zwama, Cornelis | L10 | L6 | Germany | 0.17 | 0.5 | 0.33 | 34.78% | 32 | 92 | 60 | 164.31 | 5257.92 | 15116.52 | 9858.6 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04653_JENGA TS Product Support SHX FY22231 | PG22P04653 | Shelar, Pandit | 170042 | Fan, Zheng Ping | L9 | L6 | Canada | 0.65 | 1 | 0.35 | 65.22% | 120 | 184 | 64 | 100.6 | 12072 | 18510.4 | 6438.4 | Undertracking
FSC | Kalinin, Sergey | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05321_ Gen Lanes SME support | PG22P05321 | Brunn, Michael | 128981 | Sommer, Ariane | L9 | L6 | Germany | 0.39 | 0.5 | 0.11 | 78.26% | 72 | 92 | 20 | 164.31 | 11830.32 | 15116.52 | 3286.2 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Li, Bin | 60076050 | Xu, Yi-Yao | L7 | L4 | P.R.C. | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 39.08 | 0 | 7190.72 | 7190.72 | No Tracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Pacheco, Paul Robert Pascual | 60026262 | O, Krista Mae G. | L7 | L4 | Philippines | 0 | 0.6 | 0.6 | 0% | 0 | 110.4 | 110.4 | 20.51 | 0 | 2264.304 | 2264.304 | No Tracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Salazar, Ruth Mary | 11551598 | Benavides, Esteban Rodolfo | L7 | L4 | Costa Rica | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 32.3 | 0 | 5943.2 | 5943.2 | No Tracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Li, Bin | 11543060 | Gao, Amanda | L7 | L4 | P.R.C. | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 39.08 | 0 | 7190.72 | 7190.72 | No Tracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05428_Rulex programming support | PG23P05428 | Bonilla, Johan Stick | 81149941 | Rivera, Marco | L8 | L5 | Costa Rica | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 45.58 | 3828.72 | 4193.36 | 364.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.2 | 0.2 | 0 | 100% | 36.8 | 36.8 | 7.1054e-15 | 20.51 | 754.768 | 754.768 | 1.1369e-13 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Rogando, Walter Ericson Tan | 70001189 | Espiritu, Joana Marie S. | L8 | L5 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 33.58 | 2820.72 | 3089.36 | 268.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Salazar, Ruth Mary | 60102461 | Salazar, Guzman Liany Pamela | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Li, Bin | 60099682 | Huang, Rong | L7 | L4 | P.R.C. | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 39.08 | 6252.8 | 7190.72 | 937.92 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Salazar, Ruth Mary | 60098707 | Gomez, Jeison Steven | L8 | L5 | Costa Rica | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 45.58 | 6928.16 | 8386.72 | 1458.56 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Bonilla, Johan Stick | 60083411 | Castro, Esteban | L7 | L4 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 32.3 | 2842.4 | 2971.6 | 129.2 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Rogando, Walter Ericson Tan | 60074239 | Salazar, Ralph Rendell A. | L8 | L5 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 33.58 | 1477.52 | 1544.68 | 67.16 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Gali, Bapavani | 60074201 | Venkatraman, Vedachalam | L8 | L5 | India | 0.48 | 0.5 | 0.02 | 95.65% | 99 | 103.5 | 4.5 | 26.59 | 2632.41 | 2752.065 | 119.655 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Orillaza, Noreen Olea Prila | 60034064 | Salvador, Geoffrey B. | L8 | L5 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 33.58 | 3089.36 | 3089.36 | 0 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Del Rosario, Maria Katrina | 60025466 | Sy, Neil Ryan Y. | L8 | L5 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 33.58 | 5372.8 | 6178.72 | 805.92 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Salazar, Ruth Mary | 60020000 | Artavia, William | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04840_ Wpi & DDSi Consulting Service | PG22P04840 | Dela Cruz, Honey Dianne P. | 60013555 | Baroña, Gerald Lorenzo B. | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Chua, Jeremiah Nathaniel | 21958589 | Nobleza, Cyrile G. | L7 | L4 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 20.51 | 902.44 | 943.46 | 41.02 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Rogando, Walter Ericson Tan | 21956230 | Dela Cruz, Lady Kristel Ventura | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Camaclang, Mikel Carlo Ramos | 21828670 | Cimara, Mary Grace Catan | L8 | L5 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 33.58 | 2955.04 | 3089.36 | 134.32 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05428_Rulex programming support | PG23P05428 | Yasay, Eugene Baldivino | 21767256 | Lat, Jose Antonio Atienza | L7 | L4 | Philippines | 0.76 | 0.36 | -0.4 | 211.4% | 140 | 66.24 | -73.76 | 20.51 | 2871.4 | 1358.5824 | -1512.8176 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Del Rosario, Maria Katrina | 21730452 | Alawas, Ayree L. | L8 | L5 | Philippines | 0.6 | 0.5 | -0.1 | 120.7% | 111 | 92 | -19 | 33.58 | 3727.38 | 3089.36 | -638.02 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Flores-Leano, Christine Marie T. | 21645741 | Gonzales, Freddie Lou Ann M. | L13 | L5 | Philippines | 0.85 | 1 | 0.15 | 84.78% | 156 | 184 | 28 | 33.58 | 5238.48 | 6178.72 | 940.24 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Chua, Jeremiah Nathaniel | 21604418 | Tan, Kathleen Anne Belonio | L7 | L4 | Philippines | 0.57 | 0.39 | -0.18 | 147.2% | 105.6 | 71.76 | -33.84 | 20.51 | 2165.856 | 1471.7976 | -694.0584 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Orillaza, Noreen Olea Prila | 21578974 | Mendoza, Camille Chavez | L13 | L5 | Philippines | 0.97 | 1 | 0.03 | 96.74% | 178 | 184 | 6 | 33.58 | 5977.24 | 6178.72 | 201.48 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04185_JENGA MIO, CSP BW, VOY, WPI, DDSi | PG22P04185 | Yasay, Eugene Baldivino | 21475425 | Cadiente, Madel Lizza Torres | L8 | L5 | Philippines | 0.49 | 0.5 | 0.01 | 97.83% | 90 | 92 | 2 | 33.58 | 3022.2 | 3089.36 | 67.16 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Brodeth, Carlo Hipolito | 21474079 | Apostol, Roberto E. | L8 | L5 | Philippines | 0.43 | 0.5 | 0.07 | 86.96% | 80 | 92 | 12 | 33.58 | 2686.4 | 3089.36 | 402.96 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Tolentino, Ericka May Robles | 21441423 | Barbosa, Aurora Cadiz | L7 | L4 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 20.51 | 3281.6 | 3773.84 | 492.24 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Maulbetsch, Douglas W. | 21373559 | Arguedas, Jose Guillermo | L14 | L6 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 61.48 | 5410.24 | 5656.16 | 245.92 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Brunn, Michael | 20247270 | Kraus, Rene | L10 | L6 | Germany | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 164.31 | 24975.12 | 30233.04 | 5257.92 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04185_JENGA MIO, CSP BW, VOY, WPI, DDSi | PG22P04185 | Flores-Leano, Christine Marie T. | 20202423 | Cambe, Herbert S. | L9 | L6 | Philippines | 0.43 | 0.5 | 0.07 | 86.96% | 80 | 92 | 12 | 48.19 | 3855.2 | 4433.48 | 578.28 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Scott, Keesha M. | 20001571 | Braddix, Talita M. | L8 | L5 | United States | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 103.6 | 7873.6 | 9531.2 | 1657.6 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05428_Rulex programming support | PG23P05428 | Cipriano, John Henry | 11761041 | Sante, Cedrick | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11748842 | Diaz, Antonio Altreo | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Chua, Jeremiah Nathaniel | 11735928 | Latina, Christine Grace | L6 | L3 | Philippines | 0.37 | 0.4 | 0.03 | 91.3% | 67.2 | 73.6 | 6.4 | 14.53 | 976.416 | 1069.408 | 92.992 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11735528 | Pahati, Chester | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11730361 | Jamir, Lance Jocef | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11729566 | Cabuhat, Camille | L7 | L4 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 20.51 | 3117.52 | 3773.84 | 656.32 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11726515 | Adefuin, Jeiel B. | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Flores-Leano, Christine Marie T. | 11706034 | Calimag, Geneva | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04185_JENGA MIO, CSP BW, VOY, WPI, DDSi | PG22P04185 | Uy, Precious L. | 11618765 | Diño, Jhondell Alcantara | L7 | L4 | Philippines | 0.1 | 0.05 | -0.05 | 200% | 18.4 | 9.2 | -9.2 | 20.51 | 377.384 | 188.692 | -188.692 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Mendenueta, Ismael | 11582328 | Magtulis, Mark | L7 | L4 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 20.51 | 1082.928 | 1132.152 | 49.224 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Olan, Jomar O. | 11563810 | Anda, John John | L7 | L4 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 20.51 | 902.44 | 943.46 | 41.02 | On Track
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04183_ Iplanning Rapid Response (CCR-124) | PG22P04183 | Yasay, Eugene Baldivino | 75015567 | Lee, John Roland G. | L8 | L5 | Philippines | 0.52 | 1 | 0.48 | 52.17% | 96 | 184 | 88 | 33.58 | 3223.68 | 6178.72 | 2955.04 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Del Rosario, Maria Katrina | 60073537 | De Chavez, Mark Anthony D. | L8 | L5 | Philippines | 0.16 | 0.25 | 0.09 | 65.22% | 30 | 46 | 16 | 33.58 | 1007.4 | 1544.68 | 537.28 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Del Rosario, Maria Katrina | 60027986 | Jabilona, Rachelle Ann C. | L7 | L4 | Philippines | 0.16 | 0.25 | 0.09 | 65.22% | 30 | 46 | 16 | 20.51 | 615.3 | 943.46 | 328.16 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Yasay, Eugene Baldivino | 60026421 | Sarmenta, Clarissa Marie H. | L8 | L5 | Philippines | 0.7 | 1 | 0.3 | 69.57% | 128 | 184 | 56 | 33.58 | 4298.24 | 6178.72 | 1880.48 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Tolentino, Ericka May Robles | 60016734 | Pacayra, Maricar B. | L8 | L5 | Philippines | 0.96 | 2 | 1.04 | 47.83% | 176 | 368 | 192 | 33.58 | 5910.08 | 12357.44 | 6447.36 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Zajac, Krzysztof | 21804828 | Kozak, Konrad | L8 | L5 | Poland | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 54.93 | 5712.72 | 10107.12 | 4394.4 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Jakkam, Subrahmanyam | 21650856 | Muruganandham, Kalpana | L7 | L4 | India | 0.37 | 0.5 | 0.13 | 73.91% | 76.5 | 103.5 | 27 | 17.33 | 1325.745 | 1793.655 | 467.91 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04839_ CS BW Consulting Service | PG22P04839 | Jakkam, Subrahmanyam | 21650856 | Muruganandham, Kalpana | L7 | L4 | India | 0.37 | 0.5 | 0.13 | 73.91% | 76.5 | 103.5 | 27 | 17.33 | 1325.745 | 1793.655 | 467.91 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Li, Bin | 20416193 | Yu, Zheng | L7 | L4 | P.R.C. | 0.5 | 1 | 0.5 | 50% | 92 | 184 | 92 | 39.08 | 3595.36 | 7190.72 | 3595.36 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Heglas, Ivan | 20297003 | Ziakova, Helena | L8 | L5 | Slovakia | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 59.8 | 6219.2 | 11003.2 | 4784 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Verma, Rahul | 20169721 | Jakkam, Subrahmanyam | L14 | L6 | India | 0.78 | 2 | 1.22 | 39.13% | 162 | 414 | 252 | 38.22 | 6191.64 | 15823.08 | 9631.44 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Miller, Anna | 20064994 | Niemiec, Grzegorz | L9 | L6 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 70.57 | 10162.08 | 12984.88 | 2822.8 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Kalinin, Sergey | 20035006 | Ulianova, Irina | L8 | L5 | Serbia | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 43.05 | 4477.2 | 7921.2 | 3444 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Brunn, Michael | 20000583 | Jungkenn, Rainer | L9 | L6 | Germany | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 164.31 | 23660.64 | 30233.04 | 6572.4 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Castro, Francis D. | 11742213 | Yu, Brian | L6 | L3 | Philippines | 0.43 | 0.65 | 0.22 | 66.89% | 80 | 119.6 | 39.6 | 14.53 | 1162.4 | 1737.788 | 575.388 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Miller, Anna | 11728554 | Szczepaniec, Krzysztof Piotr | L9 | L6 | Poland | 0.22 | 0.5 | 0.28 | 43.48% | 40 | 92 | 52 | 70.57 | 2822.8 | 6492.44 | 3669.64 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Jakkam, Subrahmanyam | 11718537 | Paramashetti, Vanishree | L6 | L3 | India | 0.35 | 0.5 | 0.15 | 69.57% | 72 | 103.5 | 31.5 | 11.75 | 846 | 1216.125 | 370.125 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04839_ CS BW Consulting Service | PG22P04839 | Jakkam, Subrahmanyam | 11718537 | Paramashetti, Vanishree | L6 | L3 | India | 0.35 | 0.5 | 0.15 | 69.57% | 72 | 103.5 | 31.5 | 11.75 | 846 | 1216.125 | 370.125 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04196_JENGA Supply Planning Consulting Service | PG22P04196 | Flores-Leano, Christine Marie T. | 11707015 | Tumulak, Amery Kirstie | L8 | L5 | Philippines | 0.39 | 0.5 | 0.11 | 78.26% | 72 | 92 | 20 | 33.58 | 2417.76 | 3089.36 | 671.6 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Gonzales, Freddie Lou Ann M. | 11705770 | Matic, Angel Grace | L6 | L3 | Philippines | 0.7 | 1 | 0.3 | 69.57% | 128 | 184 | 56 | 14.53 | 1859.84 | 2673.52 | 813.68 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04198_ APO Demand Planning Consulting service | PG22P04198 | Rogando, Walter Ericson Tan | 11611262 | Uy, Jeremiah | L8 | L5 | Philippines | 0.75 | 1.75 | 1 | 42.86% | 138 | 322 | 184 | 33.58 | 4634.04 | 10812.76 | 6178.72 | Undertracking
FSC | Lee, Graeme | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04201_JENGA OMP Implementation Service | PG22P04201 | Rayo, Anthony Vizmanos | 11564761 | Musni, Renjo Reniel | L8 | L5 | Philippines | 0.7 | 1.8 | 1.1 | 39.13% | 129.6 | 331.2 | 201.6 | 33.58 | 4351.968 | 11121.696 | 6769.728 | Undertracking
FSC | Obiniana, Ria | FMDS STM FY2223 | PG22P04802 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.20467 | 0 | -0.20467 | 0% | 37.66 | 0 | -37.66 | 20.51 | 772.4066 | 0 | -772.4066 | No Plan
FSC | Obiniana, Ria | Russia New Bank Project | PG23P05445 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.14348 | 0 | -0.14348 | 0% | 26.4 | 0 | -26.4 | 14.53 | 383.592 | 0 | -383.592 | No Plan
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04802_FMDS STM FY2223 | PG22P04802 | Tuazon, Darlene May V. | 11545403 | Danseco, Jose Antonio | L8 | L5 | Philippines | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 33.58 | 0 | 1235.744 | 1235.744 | No Tracking
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04914_BP&A CIs (Profit Forecasting/OSCAR) | PG22P04914 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.11 | 0.1 | -0.01 | 105.2% | 19.35 | 18.4 | -0.95 | 20.51 | 396.8685 | 377.384 | -19.4845 | On Track
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04899_Veritas FY2223 | PG22P04899 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 32.3 | 568.48 | 594.32 | 25.84 | On Track
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04812_Auto-post Continuous Improvement | PG22P04812 | Bonilla, Johan Stick | 21635114 | Hernández, Ronald | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04715_Capital Systems Project - Twenty5 | PG22P04715 | Uy, Precious L. | 11754281 | Bustamante, Jay Ruel | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 94.62% | 17.41 | 18.4 | 0.99 | 14.53 | 252.9673 | 267.352 | 14.3847 | On Track
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04812_Auto-post Continuous Improvement | PG22P04812 | Arguedas, Jose Guillermo | 11743204 | Luna, Jose Arturo | L7 | L4 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 32.3 | 5684.8 | 5943.2 | 258.4 | On Track
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG21P03467_FPSS STM Americas Product Teams Regional Projects | PG21P03467 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.24 | 0.3 | 0.06 | 79.71% | 44 | 55.2 | 11.2 | 32.3 | 1421.2 | 1782.96 | 361.76 | Undertracking
FSC | Obiniana, Ria | Deliver_AMS_PG_APP_TMTL_FSS_40_PG21P03576_FPT FMR and OSCAR STM | PG21P03576 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.13 | 0.2 | 0.08 | 62.5% | 23 | 36.8 | 13.8 | 20.51 | 471.73 | 754.768 | 283.038 | Undertracking
FSC | Panaligan, Jezalin | SDM-SAP M&S Integration | PG22P04534 | Orillaza, Noreen Olea Prila | 11723210 | Sael, Stephanie Joyce | L6 | L3 | Philippines | 0.03913 | 0 | -0.03913 | 0% | 7.2 | 0 | -7.2 | 14.53 | 104.616 | 0 | -104.616 | No Plan
FSC | Quesada, Raul | NA St Louis Park PrIME | PG23P05394 | Bordey-Choi, Iris O. | 21051361 | Nasayao, Je-Marie Sanchez | L8 | L5 | Philippines | 0.25 | 0 | -0.25 | 0% | 46 | 0 | -46 | 33.58 | 1544.68 | 0 | -1544.68 | No Plan
FSC | Quesada, Raul | NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Del Rosario, Maria Katrina | 11722059 | Lirio, Ana Luisa | L7 | L4 | Philippines | 0.0065217 | 0 | -0.0065217 | 0% | 1.2 | 0 | -1.2 | 20.51 | 24.612 | 0 | -24.612 | No Plan
FSC | Quesada, Raul | NA TMS CI FY22-23 | PG22P05300 | Bonilla, Johan Stick | 11721629 | Ramirez, Melissa | L6 | L3 | Costa Rica | 0.076087 | 0 | -0.076087 | 0% | 14 | 0 | -14 | 25.31 | 354.34 | 0 | -354.34 | No Plan
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Diaz Maag, Javier | 21681888 | Recondo, Eduardo | L9 | L6 | Spain | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 82.43 | 0 | 15167.12 | 15167.12 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Nepomuceno, Anna Grace Fullon | 21602121 | Dee, Gian Taylor Co | L9 | L6 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 48.19 | 0 | 886.696 | 886.696 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Postic, Mihajlo | 20006708 | Psarras, Yannis | L8 | L5 | Greece | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 98.9 | 0 | 3639.52 | 3639.52 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Salazar, Ruth Mary | 11722513 | Hernandez, Fabiana Angelica | L6 | L3 | Costa Rica | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 25.31 | 0 | 1164.26 | 1164.26 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Mejia, Ervene Albert H. | 11717033 | Chua, Chester | L6 | L3 | Philippines | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 14.53 | 0 | 401.028 | 401.028 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Gonzales, Francis C. | 11713223 | Toral, Justin Francis | L7 | L4 | Philippines | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 20.51 | 0 | 943.46 | 943.46 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Rogando, Walter Ericson Tan | 11611262 | Uy, Jeremiah | L8 | L5 | Philippines | 0 | 0.25 | 0.25 | 0% | 0 | 46 | 46 | 33.58 | 0 | 1544.68 | 1544.68 | No Tracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Hatama, Eduardo | 81155324 | Nagamine, Celia Kiyomi | L9 | L6 | Brazil | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 52.97 | 4661.36 | 4873.24 | 211.88 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Salazar, Ruth Mary | 75015259 | Campos, Arlensiú | L8 | L5 | Costa Rica | 0.22 | 0.25 | 0.03 | 86.96% | 40 | 46 | 6 | 45.58 | 1823.2 | 2096.68 | 273.48 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Nicolas, Jadea Ann | 75012013 | Factur, Crisell F. | L7 | L4 | Philippines | 0.09 | 0.11 | 0.02 | 83.99% | 17 | 20.24 | 3.24 | 20.51 | 348.67 | 415.1224 | 66.4524 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Abutal, Joseph Ryan A. | 60095386 | Silvestre, John Emmanuel D. | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Abutal, Joseph Ryan A. | 60095386 | Silvestre, John Emmanuel D. | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Abutal, Joseph Ryan A. | 60095386 | Silvestre, John Emmanuel D. | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Abutal, Joseph Ryan A. | 60095386 | Silvestre, John Emmanuel D. | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Bonilla, Johan Stick | 60093290 | Ulate, Jorge Luis | L9 | L6 | Costa Rica | 1.06 | 1 | -0.06 | 106% | 195 | 184 | -11 | 61.48 | 11988.6 | 11312.32 | -676.28 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Nicolas, Jadea Ann | 60083915 | Dean, Dianne Kimberly C. | L7 | L4 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 20.51 | 1886.92 | 1886.92 | 0 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Nicolas, Jadea Ann | 60083915 | Dean, Dianne Kimberly C. | L7 | L4 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 20.51 | 1886.92 | 1886.92 | 0 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Bonilla, Johan Stick | 60023169 | Mora, Natalia M. | L7 | L4 | Costa Rica | 1.05 | 1 | -0.05 | 104.9% | 193 | 184 | -9 | 32.3 | 6233.9 | 5943.2 | -290.7 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Vieira, Marcos Miranda | 60001053 | Zocaratto, Vanessa | L9 | L6 | Brazil | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 52.97 | 2330.68 | 2436.62 | 105.94 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Ong, Maurice Edison L. | 21723978 | Quiogue, Jasmine Dimalanta | L9 | L6 | Philippines | 0.3 | 0.3 | 0 | 101.4% | 56 | 55.2 | -0.8 | 48.19 | 2698.64 | 2660.088 | -38.552 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Hatama, Eduardo | 21720704 | Guedes, Carlos Alberto | L9 | L6 | Brazil | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 52.97 | 4661.36 | 4873.24 | 211.88 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Dejaeghere, Ruben | 21711620 | Intia, Joker Reyes | L9 | L6 | Belgium | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 153.18 | 2450.88 | 2818.512 | 367.632 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Agustin, Rommel Rye Penafiel | 21694157 | Torralba, Brenda Jezza Balangue | L9 | L6 | Philippines | 0.12 | 0.1 | -0.02 | 119.6% | 22 | 18.4 | -3.6 | 48.19 | 1060.18 | 886.696 | -173.484 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Salazar, Ruth Mary | 21658996 | Fonseca, Maria Fernanda | L8 | L5 | Costa Rica | 0.44 | 0.5 | 0.06 | 88.59% | 81.5 | 92 | 10.5 | 45.58 | 3714.77 | 4193.36 | 478.59 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05541_GIA RPA Update 6.10 | PG23P05541 | Avellan, Ruiz Jose Gerardo | 21356270 | Solano, Elguer | L8 | L5 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 45.58 | 4011.04 | 4193.36 | 182.32 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Bonilla, Johan Stick | 20346173 | Duarte, Alexander | L8 | L5 | Costa Rica | 0.95 | 0.8 | -0.15 | 119.2% | 175.5 | 147.2 | -28.3 | 45.58 | 7999.29 | 6709.376 | -1289.914 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Bonilla, Johan Stick | 20283148 | Jimenez, Carolina | L9 | L6 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 61.48 | 10820.48 | 11312.32 | 491.84 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Salazar, Ruth Mary | 20240557 | Sagas, Edith Vanessa | L9 | L6 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 61.48 | 5410.24 | 5656.16 | 245.92 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Salazar, Ruth Mary | 20240557 | Sagas, Edith Vanessa | L9 | L6 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 61.48 | 5410.24 | 5656.16 | 245.92 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Bonilla, Johan Stick | 20185794 | Artavia, Tracy | L9 | L6 | Costa Rica | 0.99 | 1 | 0.01 | 98.91% | 182 | 184 | 2 | 61.48 | 11189.36 | 11312.32 | 122.96 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Hatama, Eduardo | 20001208 | Dembinski, Maria Paula | L9 | L6 | Argentina | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 44.38 | 7100.8 | 8165.92 | 1065.12 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Salazar, Ruth Mary | 11768506 | Vásquez, José F. | L6 | L3 | Costa Rica | 0.21 | 0.2 | -0.01 | 103.3% | 38 | 36.8 | -1.2 | 25.31 | 961.78 | 931.408 | -30.372 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Navarro, Joycee E. | 11765896 | Jumaquio, Jennifer | L6 | L3 | Philippines | 0.25 | 0.25 | 0 | 100% | 46 | 46 | 0 | 14.53 | 668.38 | 668.38 | 0 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Mejia, Ervene Albert H. | 11765805 | Gumpal, Kennedy Klein | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Abutal, Joseph Ryan A. | 11761047 | Lee, Kevin Ryan | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 91.3% | 16.8 | 18.4 | 1.6 | 14.53 | 244.104 | 267.352 | 23.248 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Abutal, Joseph Ryan A. | 11761047 | Lee, Kevin Ryan | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 91.3% | 16.8 | 18.4 | 1.6 | 14.53 | 244.104 | 267.352 | 23.248 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Abutal, Joseph Ryan A. | 11761047 | Lee, Kevin Ryan | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Abutal, Joseph Ryan A. | 11754289 | Roque, Yrene | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 14.53 | 267.352 | 267.352 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Caldez, Stan Steve Philip Sarmiento | 11745468 | Bihis, Kevin Richardson | L6 | L3 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 14.53 | 767.184 | 802.056 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Mejia, Ervene Albert H. | 11742820 | Espiritu, John Harold Y. | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Morong, Jann Angelo U. | 11740431 | Batingan, Julian Patrick | L6 | L3 | Philippines | 0.3 | 0.35 | 0.05 | 85.56% | 55.1 | 64.4 | 9.3 | 14.53 | 800.603 | 935.732 | 135.129 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Gutierrez, Kristine | 11739094 | Go, Michael Anthony | L6 | L3 | Philippines | 0.33 | 0.1 | -0.23 | 334.8% | 61.6 | 18.4 | -43.2 | 14.53 | 895.048 | 267.352 | -627.696 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Del Barrio-Alejo, Karla Jean | 11738825 | Señar, Aaron Joshua | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Odulio, Andria | 11738592 | Pidor, Christy May | L7 | L4 | Philippines | 0.23 | 0.2 | -0.03 | 114.1% | 42 | 36.8 | -5.2 | 20.51 | 861.42 | 754.768 | -106.652 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Odulio, Andria | 11738592 | Pidor, Christy May | L7 | L4 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 20.51 | 861.42 | 943.46 | 82.04 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Del Rosario, Maria Katrina | 11738383 | Anunciado, Joy Ann | L6 | L3 | Philippines | 0.3 | 0.3 | 0 | 100% | 55.2 | 55.2 | -7.1054e-15 | 14.53 | 802.056 | 802.056 | -1.1369e-13 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Valerio, Von Alvin M. | 11736630 | Balatong, Jayson | L6 | L3 | Philippines | 0.38 | 0.15 | -0.23 | 250% | 69 | 27.6 | -41.4 | 14.53 | 1002.57 | 401.028 | -601.542 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Morong, Jann Angelo U. | 11733977 | Saludes, Andrew | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 14.53 | 383.592 | 401.028 | 17.436 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Morong, Jann Angelo U. | 11733977 | Saludes, Andrew | L6 | L3 | Philippines | 0.33 | 0.2 | -0.13 | 167.4% | 61.6 | 36.8 | -24.8 | 14.53 | 895.048 | 534.704 | -360.344 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Del Rosario, Maria Katrina | 11733419 | Mauricio, Rem Lester | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 14.53 | 383.592 | 401.028 | 17.436 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Rogando, Walter Ericson Tan | 11726744 | Malong, Jose Mari | L7 | L4 | Philippines | 0.52 | 0.5 | -0.02 | 104.3% | 96 | 92 | -4 | 20.51 | 1968.96 | 1886.92 | -82.04 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Crucena, Mark Jayson S. | 11724809 | Lazatin, Bradley | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 14.53 | 232.48 | 267.352 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Bonilla, Johan Stick | 11722514 | Cordero, Claudio Jose | L6 | L3 | Costa Rica | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 25.31 | 1113.64 | 1164.26 | 50.62 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Bonilla, Johan Stick | 11721629 | Ramirez, Melissa | L6 | L3 | Costa Rica | 0.08 | 0.04 | -0.04 | 190.2% | 14 | 7.36 | -6.64 | 25.31 | 354.34 | 186.2816 | -168.0584 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Bonilla, Johan Stick | 11721629 | Ramirez, Melissa | L6 | L3 | Costa Rica | 0.08 | 0.02 | -0.06 | 380.4% | 14 | 3.68 | -10.32 | 25.31 | 354.34 | 93.1408 | -261.1992 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Navarro, Joycee E. | 11721548 | Espina, Alexis | L6 | L3 | Philippines | 0.6 | 0.5 | -0.1 | 120.7% | 111 | 92 | -19 | 14.53 | 1612.83 | 1336.76 | -276.07 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Mendenueta, Ismael | 11719965 | Manalo, Alyssa Gia | L6 | L3 | Philippines | 0.37 | 0.4 | 0.03 | 91.3% | 67.2 | 73.6 | 6.4 | 14.53 | 976.416 | 1069.408 | 92.992 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Mejia, Ervene Albert H. | 11717048 | Balbada, Joan | L6 | L3 | Philippines | 0.14 | 0.12 | -0.02 | 119.6% | 26.4 | 22.08 | -4.32 | 14.53 | 383.592 | 320.8224 | -62.7696 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Curio, Francine Nicole Macoy | 11716271 | Blue, Julius Caesar | L7 | L4 | Philippines | 0.17 | 0.2 | 0.03 | 82.88% | 30.5 | 36.8 | 6.3 | 20.51 | 625.555 | 754.768 | 129.213 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Curio, Francine Nicole Macoy | 11716271 | Blue, Julius Caesar | L7 | L4 | Philippines | 0.25 | 0.25 | 0 | 100% | 46 | 46 | 0 | 20.51 | 943.46 | 943.46 | 0 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Borja, Olivia B. | 11715705 | Alfaro, Jayson | L6 | L3 | Philippines | 0.62 | 0.65 | 0.03 | 95.65% | 114.4 | 119.6 | 5.2 | 14.53 | 1662.232 | 1737.788 | 75.556 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Castro, Francis D. | 11715400 | Redulla, Mary Aileen | L10 | L6 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 48.19 | 7324.88 | 8866.96 | 1542.08 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Del Rosario, Maria Katrina | 11714294 | Tanglao, Erin Jasse | L6 | L3 | Philippines | 0.13 | 0.15 | 0.02 | 86.96% | 24 | 27.6 | 3.6 | 14.53 | 348.72 | 401.028 | 52.308 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Mendenueta, Ismael | 11711729 | Vallespin, Christian Gabriel | L6 | L3 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 14.53 | 767.184 | 802.056 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.3 | 0.25 | -0.05 | 119.6% | 55 | 46 | -9 | 14.53 | 799.15 | 668.38 | -130.77 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Nicolas, Jadea Ann | 11708607 | Fidelson, Hannah Joy | L7 | L4 | Philippines | 0.66 | 0.5 | -0.16 | 131.5% | 121 | 92 | -29 | 20.51 | 2481.71 | 1886.92 | -594.79 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Nicolas, Jadea Ann | 11708607 | Fidelson, Hannah Joy | L7 | L4 | Philippines | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 20.51 | 1804.88 | 1886.92 | 82.04 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Rodriguez, Alphonse Joseph V. | 11705603 | Paulino, Spenzer | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 104.3% | 19.2 | 18.4 | -0.8 | 14.53 | 278.976 | 267.352 | -11.624 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Del Rosario, Maria Katrina | 11705149 | Castañeda, John Michael | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Borja, Olivia B. | 11621764 | Pajes Iii, Ramon Alfredo I. | L6 | L3 | Philippines | 0.59 | 0.65 | 0.06 | 91.3% | 109.2 | 119.6 | 10.4 | 14.53 | 1586.676 | 1737.788 | 151.112 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Nicolas, Jadea Ann | 11618913 | Ortiz, Raymond Brian | L6 | L3 | Philippines | 0.24 | 0.17 | -0.07 | 140.7% | 44 | 31.28 | -12.72 | 14.53 | 639.32 | 454.4984 | -184.8216 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Uy, Precious L. | 11618765 | Diño, Jhondell Alcantara | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100.1% | 18.41 | 18.4 | -0.01 | 20.51 | 377.5891 | 377.384 | -0.2051 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Gonzalez, Ropero Arantxa | 11612401 | Alvarez, Rocio | L9 | L6 | Spain | 0.25 | 0.25 | 0 | 100% | 46 | 46 | 0 | 82.43 | 3791.78 | 3791.78 | 0 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Abutal, Joseph Ryan A. | 11582386 | Lupos, Julie Ann | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Abutal, Joseph Ryan A. | 11582344 | Tumulak Jr., Eugene | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 14.53 | 267.352 | 267.352 | 5.6843e-14 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Bonilla, Johan Stick | 11581387 | Velez Paiz, Fernando Antonio | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Mendenueta, Ismael | 11580446 | Legaspi, Mark Cleo | L7 | L4 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 20.51 | 541.464 | 566.076 | 24.612 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Mendenueta, Ismael | 11580446 | Legaspi, Mark Cleo | L7 | L4 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 20.51 | 721.952 | 754.768 | 32.816 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05530_MH Plant RPA (Bluezone) | PG23P05530 | Li, Bin | 11576485 | Chen, Yao | L7 | L4 | P.R.C. | 0.09 | 0.06 | -0.03 | 144.9% | 16 | 11.04 | -4.96 | 39.08 | 625.28 | 431.4432 | -193.8368 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Madrilejo, Nathaniel | 11551116 | Mones, Angelica | L7 | L4 | Philippines | 0.21 | 0.25 | 0.04 | 82.61% | 38 | 46 | 8 | 20.51 | 779.38 | 943.46 | 164.08 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Madrilejo, Nathaniel | 11551116 | Mones, Angelica | L7 | L4 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 20.51 | 1558.76 | 1886.92 | 328.16 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Madrilejo, Nathaniel | 11551116 | Mones, Angelica | L7 | L4 | Philippines | 0.21 | 0.25 | 0.04 | 82.61% | 38 | 46 | 8 | 20.51 | 779.38 | 943.46 | 164.08 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Uy, Precious L. | 11543197 | Mendenueta, Ismael | L13 | L5 | Philippines | 0.15 | 0.15 | 0 | 101.4% | 28 | 27.6 | -0.4 | 33.58 | 940.24 | 926.808 | -13.432 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Shelar, Pandit | 171862 | Zhu, Tao | L9 | L6 | Canada | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 100.6 | 15291.2 | 18510.4 | 3219.2 | On Track
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Hatama, Eduardo | 81002920 | Aranda, Clarisa | L8 | L5 | Argentina | 0.79 | 1 | 0.21 | 79.35% | 146 | 184 | 38 | 32.23 | 4705.58 | 5930.32 | 1224.74 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Junior, Ricardo De Almeida Rego | 60113410 | Ocampo, Hillary Michelle | L7 | L4 | Costa Rica | 0.1 | 0.15 | 0.05 | 63.77% | 17.6 | 27.6 | 10 | 32.3 | 568.48 | 891.48 | 323 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Gandhi Senthil Kumar, | 21661187 | Rodriguez, Melvin C. | L8 | L5 | United Arab Emirates | 0.43 | 1 | 0.57 | 43.48% | 80 | 184 | 104 | 115.58 | 9246.4 | 21266.72 | 12020.32 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Bordey-Choi, Iris O. | 21051361 | Nasayao, Je-Marie Sanchez | L8 | L5 | Philippines | 0.2 | 0.25 | 0.05 | 78.26% | 36 | 46 | 10 | 33.58 | 1208.88 | 1544.68 | 335.8 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Salazar, Ruth Mary | 20336648 | Rodriguez, Diego | L9 | L6 | Costa Rica | 0.15 | 0.25 | 0.1 | 60.87% | 28 | 46 | 18 | 61.48 | 1721.44 | 2828.08 | 1106.64 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Salazar, Ruth Mary | 20333201 | Rojas, Harry | L8 | L5 | Costa Rica | 0.02 | 0.25 | 0.23 | 8.696% | 4 | 46 | 42 | 45.58 | 182.32 | 2096.68 | 1914.36 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Arguedas, Jose Guillermo | 20006940 | Rojas, Victor Manuel | L8 | L5 | Costa Rica | 0.76 | 1 | 0.24 | 76.09% | 140 | 184 | 44 | 45.58 | 6381.2 | 8386.72 | 2005.52 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Vargas, Claudia Priscila | 11752050 | David, Jay | L8 | L5 | Canada | 0.65 | 1 | 0.35 | 65.22% | 120 | 184 | 64 | 82.64 | 9916.8 | 15205.76 | 5288.96 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Morong, Jann Angelo U. | 11740756 | Magaso, Veronicka Nina M. | L6 | L3 | Philippines | 0.05 | 0.07 | 0.02 | 69.88% | 9 | 12.88 | 3.88 | 14.53 | 130.77 | 187.1464 | 56.3764 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Gutierrez, Kristine | 11739094 | Go, Michael Anthony | L6 | L3 | Philippines | 0.33 | 0.7 | 0.37 | 47.83% | 61.6 | 128.8 | 67.2 | 14.53 | 895.048 | 1871.464 | 976.416 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Del Rosario, Maria Katrina | 11738383 | Anunciado, Joy Ann | L6 | L3 | Philippines | 0.35 | 0.8 | 0.45 | 43.75% | 64.4 | 147.2 | 82.8 | 14.53 | 935.732 | 2138.816 | 1203.084 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04373_Brantford PrIME | PG22P04373 | Gutierrez, Kristine | 11732238 | Camarce, Von Ryan | L6 | L3 | Philippines | 0.28 | 0.35 | 0.07 | 79.19% | 51 | 64.4 | 13.4 | 14.53 | 741.03 | 935.732 | 194.702 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Navarro, Joycee E. | 11725490 | Morales, Rainalene | L6 | L3 | Philippines | 0.24 | 0.4 | 0.16 | 59.78% | 44 | 73.6 | 29.6 | 14.53 | 639.32 | 1069.408 | 430.088 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04998_Brazil Legal and Tax Dedicated Team (CCR-138) | PG22P04998 | Bonilla, Johan Stick | 11722512 | Ocampo, Maria Melina | L6 | L3 | Costa Rica | 0.16 | 0.25 | 0.09 | 65.22% | 30 | 46 | 16 | 25.31 | 759.3 | 1164.26 | 404.96 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05085_NA PrIME Boombox Greenfield | PG22P05085 | Bonilla, Johan Stick | 11722512 | Ocampo, Maria Melina | L6 | L3 | Costa Rica | 0.15 | 0.2 | 0.05 | 76.09% | 28 | 36.8 | 8.8 | 25.31 | 708.68 | 931.408 | 222.728 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05300_NA TMS CI FY22-23 | PG22P05300 | Bonilla, Johan Stick | 11722512 | Ocampo, Maria Melina | L6 | L3 | Costa Rica | 0.17 | 0.3 | 0.13 | 55.29% | 30.52 | 55.2 | 24.68 | 25.31 | 772.4612 | 1397.112 | 624.6508 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05394_ NA St Louis Park PrIME | PG23P05394 | Curio, Francine Nicole Macoy | 11716271 | Blue, Julius Caesar | L7 | L4 | Philippines | 0.21 | 0.6 | 0.39 | 34.87% | 38.5 | 110.4 | 71.9 | 20.51 | 789.635 | 2264.304 | 1474.669 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05417_NA PrIME Andover Rhodonite FY2223 | PG23P05417 | Del Rosario, Maria Katrina | 11716206 | San Juan, Rosechel Joy | L6 | L3 | Philippines | 0.1 | 0.15 | 0.05 | 65.22% | 18 | 27.6 | 9.6 | 14.53 | 261.54 | 401.028 | 139.488 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04819_OTC SA Attachment B.2.3 C- 4 - NALA SAP CI | PG22P04819 | Vargas, Claudia Priscila | 11584440 | Liu, Lie | L8 | L5 | Canada | 0.72 | 1 | 0.28 | 71.74% | 132 | 184 | 52 | 82.64 | 10908.48 | 15205.76 | 4297.28 | Undertracking
FSC | Quesada, Raul | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05530_MH Plant RPA (Bluezone) | PG23P05530 | Wu, Qiang | 11547824 | Lu, Na | L7 | L4 | P.R.C. | 0.78 | 2 | 1.22 | 39.13% | 144 | 368 | 224 | 39.08 | 5627.52 | 14381.44 | 8753.92 | Undertracking
FSC | Quesada, Raul - FPSS | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04909_DXC Functional support for Brazil SATI/SPED FY 22 23 | PG22P04909 | Arguedas, Jose Guillermo | 60083899 | Alfaro, Andrea | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Quesada, Raul - FPSS | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04714_Brazil Compliance Modernization FY22/23 | PG22P04714 | Vieira, Marcos Miranda | 60001053 | Zocaratto, Vanessa | L9 | L6 | Brazil | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 52.97 | 2330.68 | 2436.62 | 105.94 | On Track
FSC | Quesada, Raul - RPA | Automation FactoryFY22-23 | PG22P04848 | Teo, Jenny Anne T. | 21641598 | Gonzales, Lourdes Marie Clare | L8 | L5 | Philippines | 0.086957 | 0 | -0.086957 | 0% | 16 | 0 | -16 | 33.58 | 537.28 | 0 | -537.28 | No Plan
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Marana, Brian Diamante | 60084366 | Abinales, Michael Angelo A. | L8 | L5 | Philippines | 0.93 | 1 | 0.07 | 93.48% | 172 | 184 | 12 | 33.58 | 5775.76 | 6178.72 | 402.96 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Pe, John Paul Tan | 60061482 | Puno, Ever Lynde D. | L8 | L5 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 33.58 | 2552.08 | 3089.36 | 537.28 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05350_AR DevOps BluePrism | PG23P05350 | Avellan, Ruiz Jose Gerardo | 21356270 | Solano, Elguer | L8 | L5 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 45.58 | 4011.04 | 4193.36 | 182.32 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG22P04848_Automation FactoryFY22-23 | PG22P04848 | Marana, Brian Diamante | 11745517 | Siena, Tristan James | L7 | L4 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 20.51 | 3445.68 | 3773.84 | 328.16 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG22P04848_Automation FactoryFY22-23 | PG22P04848 | Marana, Brian Diamante | 11742861 | Guiruela, Abegail | L7 | L4 | Philippines | 1 | 1 | 0 | 100% | 184 | 184 | 0 | 20.51 | 3773.84 | 3773.84 | 0 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_FSS_40_PG23P05410_Azure Application Improvements | PG23P05410 | Torres, Von Russell | 11722617 | Hular, John Ivan | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Biasbas, Christopher B. | 11617547 | Palisoc, Reden | L13 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG22P05273_ RPA developer for NA | PG22P05273 | Avellan, Ruiz Jose Gerardo | 11611299 | Fernandez, Franklin Gerardo | L8 | L5 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 45.58 | 4011.04 | 4193.36 | 182.32 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05350_AR DevOps BluePrism | PG23P05350 | Avellan, Ruiz Jose Gerardo | 11611299 | Fernandez, Franklin Gerardo | L8 | L5 | Costa Rica | 0.48 | 0.5 | 0.02 | 95.65% | 88 | 92 | 4 | 45.58 | 4011.04 | 4193.36 | 182.32 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Li, Bin | 11576485 | Chen, Yao | L7 | L4 | P.R.C. | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 39.08 | 3595.36 | 3595.36 | 0 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05374_Singapore Pioneer Plant | PG23P05374 | Li, Bin | 11576485 | Chen, Yao | L7 | L4 | P.R.C. | 0.25 | 0.25 | 0 | 100% | 46 | 46 | 0 | 39.08 | 1797.68 | 1797.68 | 0 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Yasay, Eugene Baldivino | 11564915 | Mangalindan, Eduard Ray | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05413_dComm LA PHC | PG23P05413 | Rubinkowska, Joanna | 11743574 | Matusik, Joanna | L6 | L3 | Poland | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 28.11 | 4047.84 | 5172.24 | 1124.4 | Undertracking
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Marana, Brian Diamante | 11742174 | Gerona, Carlo | L7 | L4 | Philippines | 0.8 | 1 | 0.2 | 80.43% | 148 | 184 | 36 | 20.51 | 3035.48 | 3773.84 | 738.36 | Undertracking
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_TMTL_AUT_74_PG23P05374_Singapore Pioneer Plant | PG23P05374 | Le, Thi Minh Tam | 11721934 | Le, Trung Kien | L6 | L3 | Vietnam | 0.52 | 1 | 0.48 | 52.17% | 96 | 184 | 88 |  | 0 | 0 | 0 | Undertracking
FSC | Quesada, Raul - RPA | Deliver_AMS_PG_APP_SATM_AUT_74_PG22P04453_RPA Core Service | PG22P04453 | Yasay, Eugene Baldivino | 11720160 | Villa, John Michael | L7 | L4 | Philippines | 0.65 | 1 | 0.35 | 65.22% | 120 | 184 | 64 | 20.51 | 2461.2 | 3773.84 | 1312.64 | Undertracking
FSC | Quito, Nelson - Projects | EAIMON DevOps 2023 | PG23P05369 | Rivera, Rizelle Lian R. | 11738051 | Perfecto, Hazel Mitzi | L6 | L3 | Philippines | 0.12609 | 0 | -0.12609 | 0% | 23.2 | 0 | -23.2 | 14.53 | 337.096 | 0 | -337.096 | No Plan
FSC | Quito, Nelson - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG23P05369_EAIMON DevOps 2023 | PG23P05369 | Antonio, Sarah Mangalinao | 21708745 | Ong, Timothy-Michael Keh | L9 | L6 | Philippines | 0 | 0.35 | 0.35 | 0% | 0 | 64.4 | 64.4 | 48.19 | 0 | 3103.436 | 3103.436 | No Tracking
FSC | Quito, Nelson - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG23P05369_EAIMON DevOps 2023 | PG23P05369 | Brunn, Michael | 20000493 | Kislian, Viktor | L10 | L6 | Germany | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 164.31 | 0 | 4534.956 | 4534.956 | No Tracking
FSC | Quito, Nelson - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG23P05369_EAIMON DevOps 2023 | PG23P05369 | Fu, Rina Joyce | 11541644 | Casareo, Mark | L8 | L5 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 33.58 | 1477.52 | 1544.68 | 67.16 | On Track
FSC | Quito, Nelson - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG23P05369_EAIMON DevOps 2023 | PG23P05369 | Karababa, Ceyhun | 20000543 | Gardelein, Rudy | L10 | L6 | Belgium | 0.09 | 0.4 | 0.31 | 21.74% | 16 | 73.6 | 57.6 | 153.18 | 2450.88 | 11274.048 | 8823.168 | Undertracking
FSC | Radaza, Gerald | FPSS SAP Roadmap Resources | PG21P03587 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.10707 | 0 | -0.10707 | 0% | 19.7 | 0 | -19.7 | 20.51 | 404.047 | 0 | -404.047 | No Plan
FSC | Radaza, Gerald | FPT External Reporting STM FY23 | PG22P04800 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.038043 | 0 | -0.038043 | 0% | 7 | 0 | -7 | 20.51 | 143.57 | 0 | -143.57 | No Plan
FSC | Radaza, Gerald | FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Radam, Rodrigo D. | 11547419 | Palomo, Romlyn F. | L7 | L4 | Philippines | 0.091304 | 0 | -0.091304 | 0% | 16.8 | 0 | -16.8 | 20.51 | 344.568 | 0 | -344.568 | No Plan
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04768_Brazil Localization Master Data Resource | PG22P04768 | Salazar, Ruth Mary | 75015259 | Campos, Arlensiú | L8 | L5 | Costa Rica | 0.41 | 0.43 | 0.02 | 96.06% | 76 | 79.12 | 3.12 | 45.58 | 3464.08 | 3606.2896 | 142.2096 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04773_IT Services for FPSS Banking Global Team FY23 | PG22P04773 | Bonilla, Johan Stick | 60093144 | Chacon, Natalia | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Bernardino, Roderick Magtalas | 60091236 | Opiana, Josephine F. | L8 | L5 | Philippines | 0.23 | 0.04 | -0.19 | 563.9% | 41.5 | 7.36 | -34.14 | 33.58 | 1393.57 | 247.1488 | -1146.4212 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Gubat, Sayine S. | 60043587 | Sularte, Bagani J. | L8 | L5 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 33.58 | 886.512 | 926.808 | 40.296 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04773_IT Services for FPSS Banking Global Team FY23 | PG22P04773 | Bonilla, Johan Stick | 20282686 | Ramirez, Maria Mercedes | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04772_DXC Global AP Application Management Team FY23 | PG22P04772 | Bonilla, Johan Stick | 20242204 | Solano, Wendy | L8 | L5 | Costa Rica | 1 | 1 | 0 | 100% | 184 | 184 | 0 | 45.58 | 8386.72 | 8386.72 | 0 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | San Juan, Mylene M. | 11765424 | De Chavez, Yasmin Yvonne | L6 | L3 | Philippines | 0.24 | 0.16 | -0.08 | 149.5% | 44 | 29.44 | -14.56 | 14.53 | 639.32 | 427.7632 | -211.5568 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Uy, Precious L. | 11754281 | Bustamante, Jay Ruel | L6 | L3 | Philippines | 0.23 | 0.12 | -0.11 | 187.8% | 41.47 | 22.08 | -19.39 | 14.53 | 602.5591 | 320.8224 | -281.7367 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | De Villa, Fatima Suzanne G. | 11754264 | Vargas, Calvin Karlo | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Mejia, Ervene Albert H. | 11742820 | Espiritu, John Harold Y. | L6 | L3 | Philippines | 0.32 | 0.35 | 0.03 | 91.3% | 58.8 | 64.4 | 5.6 | 14.53 | 854.364 | 935.732 | 81.368 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04772_DXC Global AP Application Management Team FY23 | PG22P04772 | Mendoza, Camille Chavez | 11742348 | Avellaneda, Marynel | L7 | L4 | Philippines | 0.73 | 0.8 | 0.07 | 91.3% | 134.4 | 147.2 | 12.8 | 20.51 | 2756.544 | 3019.072 | 262.528 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Mendoza, Camille Chavez | 11742348 | Avellaneda, Marynel | L7 | L4 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 20.51 | 861.42 | 943.46 | 82.04 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04588_SBM Jaggaer DevOps Resources | PG22P04588 | Torres, Von Russell | 11742208 | Domingo, Denver D. | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04588_SBM Jaggaer DevOps Resources | PG22P04588 | Torres, Von Russell | 11740166 | Igpuara, Louiella | L6 | L3 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 14.53 | 2208.56 | 2673.52 | 464.96 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Chua, Jeremiah Nathaniel | 11736422 | Macawili, Maryjho Arrace M. | L6 | L3 | Philippines | 0.19 | 0.09 | -0.1 | 212.6% | 35.2 | 16.56 | -18.64 | 14.53 | 511.456 | 240.6168 | -270.8392 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Chua, Jeremiah Nathaniel | 11735928 | Latina, Christine Grace | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Mendoza, Camille Chavez | 11734704 | Rodil, John Darryl | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04723_FPSS Access Management BW Developer | PG22P04723 | Annapareddy, Kalyan | 11732222 | Balasubramanian, Vijaya Sankar Vignesh | L7 | L4 | India | 0.96 | 1 | 0.04 | 95.65% | 198 | 207 | 9 | 17.33 | 3431.34 | 3587.31 | 155.97 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.08 | 0.04 | -0.04 | 190.2% | 14 | 7.36 | -6.64 | 20.51 | 287.14 | 150.9536 | -136.1864 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Uy, Precious L. | 11719199 | Agustin, Jelbert | L7 | L4 | Philippines | 0.18 | 0.2 | 0.02 | 91.3% | 33.6 | 36.8 | 3.2 | 20.51 | 689.136 | 754.768 | 65.632 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Radam, Rodrigo D. | 11717047 | Apolonia, Earl Patrick | L6 | L3 | Philippines | 0.32 | 0.15 | -0.17 | 213% | 58.8 | 27.6 | -31.2 | 14.53 | 854.364 | 401.028 | -453.336 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Mejia, Ervene Albert H. | 11717033 | Chua, Chester | L6 | L3 | Philippines | 0.29 | 0.13 | -0.16 | 220.7% | 52.8 | 23.92 | -28.88 | 14.53 | 767.184 | 347.5576 | -419.6264 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | De Villa, Fatima Suzanne G. | 11715812 | Aguilar, Jonnuelle | L7 | L4 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 20.51 | 721.952 | 754.768 | 32.816 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Gali, Bapavani | 11715310 | B, Raghu Praneeth | L6 | L3 | India | 0.09 | 0.09 | 0 | 96.62% | 18 | 18.63 | 0.63 | 11.75 | 211.5 | 218.9025 | 7.4025 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Gonzales, Francis C. | 11713223 | Toral, Justin Francis | L7 | L4 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 20.51 | 721.952 | 754.768 | 32.816 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.19 | 0.1 | -0.09 | 191.3% | 35.2 | 18.4 | -16.8 | 14.53 | 511.456 | 267.352 | -244.104 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04772_DXC Global AP Application Management Team FY23 | PG22P04772 | Radam, Rodrigo D. | 11707290 | Bautista, Marijo | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Pacheco, Paul Robert Pascual | 11621845 | Muros, Honey Grace | L6 | L3 | Philippines | 0.08 | 0.04 | -0.04 | 206.5% | 15.2 | 7.36 | -7.84 | 14.53 | 220.856 | 106.9408 | -113.9152 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Uy, Precious L. | 11618765 | Diño, Jhondell Alcantara | L7 | L4 | Philippines | 0.12 | 0.14 | 0.02 | 86.68% | 22.33 | 25.76 | 3.43 | 20.51 | 457.9883 | 528.3376 | 70.3493 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Mendenueta, Ismael | 11617008 | Lomiguen, Carl Benedict | L7 | L4 | Philippines | 0.41 | 0.45 | 0.04 | 91.3% | 75.6 | 82.8 | 7.2 | 20.51 | 1550.556 | 1698.228 | 147.672 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Sandanasamy, Naveen | 11604107 | Sutar, Priyanka | L7 | L4 | India | 0.11 | 0.1 | -0.01 | 106.3% | 22 | 20.7 | -1.3 | 17.33 | 381.26 | 358.731 | -22.529 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04773_IT Services for FPSS Banking Global Team FY23 | PG22P04773 | Chua, Jan Charmaine Pe | 11601478 | Chua, Kristine Lorren | L9 | L6 | Philippines | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 48.19 | 7324.88 | 8866.96 | 1542.08 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04772_DXC Global AP Application Management Team FY23 | PG22P04772 | Bonilla, Johan Stick | 11595455 | Bejarano, Elizabeth | L7 | L4 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 32.3 | 5684.8 | 5943.2 | 258.4 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Radam, Rodrigo D. | 11582379 | Lim, Michael Oliver | L7 | L4 | Philippines | 0.36 | 0.13 | -0.23 | 274.2% | 65.6 | 23.92 | -41.68 | 20.51 | 1345.456 | 490.5992 | -854.8568 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04772_DXC Global AP Application Management Team FY23 | PG22P04772 | Moldogo, Richardson Baet | 11577985 | Bersabal, Sean | L7 | L4 | Philippines | 0.5 | 0.5 | 0 | 100.5% | 92.5 | 92 | -0.5 | 20.51 | 1897.175 | 1886.92 | -10.255 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Orillaza, Noreen Olea Prila | 11550165 | Faustino, Gizelle Angela | L8 | L5 | Philippines | 0.12 | 0.15 | 0.03 | 82.61% | 22.8 | 27.6 | 4.8 | 33.58 | 765.624 | 926.808 | 161.184 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04588_SBM Jaggaer DevOps Resources | PG22P04588 | Agustin, Rommel Rye Penafiel | 11548262 | Arrieta, Justin | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Uy, Precious L. | 11543197 | Mendenueta, Ismael | L13 | L5 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 33.58 | 1182.016 | 1235.744 | 53.728 | On Track
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Polamraju, Bharani Kumar | 60105280 | Tholasiraman, Kumaraguru | L8 | L5 | India | 0.15 | 0.2 | 0.05 | 73.91% | 30.6 | 41.4 | 10.8 | 26.59 | 813.654 | 1100.826 | 287.172 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04773_IT Services for FPSS Banking Global Team FY23 | PG22P04773 | Chua, Jan Charmaine Pe | 21787986 | Costales, Christian Piang | L9 | L6 | Philippines | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 48.19 | 5397.28 | 8866.96 | 3469.68 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Orillaza, Noreen Olea Prila | 11765257 | Abando, Jerald | L6 | L3 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 14.53 | 2092.32 | 2673.52 | 581.2 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04838_FAR OPEX Portfolio Resources | PG22P04838 | Tagle, Julio Enrico | 11761694 | Borromeo, Lenen Mark | L6 | L3 | Philippines | 0.61 | 1 | 0.39 | 60.87% | 112 | 184 | 72 | 14.53 | 1627.36 | 2673.52 | 1046.16 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Uy, Precious L. | 11757137 | Yee, Kevin Glenn | L6 | L3 | Philippines | 0.06 | 0.14 | 0.08 | 43.48% | 11.2 | 25.76 | 14.56 | 14.53 | 162.736 | 374.2928 | 211.5568 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04768_Brazil Localization Master Data Resource | PG22P04768 | Salazar, Ruth Mary | 11722513 | Hernandez, Fabiana Angelica | L6 | L3 | Costa Rica | 0.3 | 0.5 | 0.2 | 60.87% | 56 | 92 | 36 | 25.31 | 1417.36 | 2328.52 | 911.16 | Undertracking
FSC | Radaza, Gerald | Deliver_AMS_PG_APP_TMTL_FSS_40_PG22P04753_FPSS Regional Projects IT Delivery FY23 | PG22P04753 | Requesto, Ryann Escobido | 11706423 | Calulo, Maria Veronica | L7 | L4 | Philippines | 0.11 | 0.2 | 0.09 | 57.34% | 21.1 | 36.8 | 15.7 | 20.51 | 432.761 | 754.768 | 322.007 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Sarkar, Moloy | 11752396 | Sahu, Amrit | L7 | L4 | India | 0 | 0.16 | 0.16 | 0% | 0 | 33.12 | 33.12 | 17.33 | 0 | 573.9696 | 573.9696 | No Tracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Sarkar, Moloy | 1511448 | Giridhar, Mullapudi | L8 | L5 | India | 0 | 0.44 | 0.44 | 0% | 0 | 91.08 | 91.08 | 26.59 | 0 | 2421.8172 | 2421.8172 | No Tracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Nicolas, Jadea Ann | 75012013 | Factur, Crisell F. | L7 | L4 | Philippines | 0.26 | 0.25 | -0.01 | 105.4% | 48.5 | 46 | -2.5 | 20.51 | 994.735 | 943.46 | -51.275 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05516_Python Developer to support PrIME COE Team | PG23P05516 | Ramalingam, Murali | 22015343 | Priya, L | L7 | L4 | India | 0.83 | 1 | 0.17 | 82.61% | 171 | 207 | 36 | 17.33 | 2963.43 | 3587.31 | 623.88 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Arce, Karla Patricia R. | 21971943 | Nicolas, Jadea Ann | L13 | L5 | Philippines | 0.14 | 0.12 | -0.02 | 115.5% | 25.5 | 22.08 | -3.42 | 33.58 | 856.29 | 741.4464 | -114.8436 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Nepomuceno, Anna Grace Fullon | 21912775 | Curio, Francine Nicole Macoy | L13 | L5 | Philippines | 0.89 | 1 | 0.11 | 89.13% | 164 | 184 | 20 | 33.58 | 5507.12 | 6178.72 | 671.6 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Nepomuceno, Anna Grace Fullon | 20257958 | Tan, Bailey Martin Remulta | L9 | L6 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 48.19 | 8481.44 | 8866.96 | 385.52 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05516_Python Developer to support PrIME COE Team | PG23P05516 | Ogoy, Rhodalie Kaye A. | 11764903 | Padida Jr., Rogelio | L9 | L6 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 48.19 | 7710.4 | 8866.96 | 1156.56 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Curio, Francine Nicole Macoy | 11716271 | Blue, Julius Caesar | L7 | L4 | Philippines | 0.25 | 0.2 | -0.05 | 125% | 46 | 36.8 | -9.2 | 20.51 | 943.46 | 754.768 | -188.692 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Nicolas, Jadea Ann | 11618913 | Ortiz, Raymond Brian | L6 | L3 | Philippines | 0.26 | 0.25 | -0.01 | 104.3% | 48 | 46 | -2 | 14.53 | 697.44 | 668.38 | -29.06 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Gonzalez, Ropero Arantxa | 11612401 | Alvarez, Rocio | L9 | L6 | Spain | 0.64 | 0.75 | 0.11 | 85.2% | 117.58 | 138 | 20.42 | 82.43 | 9692.1194 | 11375.34 | 1683.2206 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Nepomuceno, Anna Grace Fullon | 11591386 | Dimzon, Brandon Alan | L9 | L6 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 48.19 | 8095.92 | 8866.96 | 771.04 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Gonzalez, Ropero Arantxa | 11573842 | Osuna, Oubiña Mariela Sabrina | L6 | L3 | Spain | 0.49 | 0.5 | 0.01 | 97.59% | 89.78 | 92 | 2.22 | 49.36 | 4431.5408 | 4541.12 | 109.5792 | On Track
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Laguardia, Francis Ervin Ilao | 60080376 | Datu, Ronnie C. | L9 | L6 | Philippines | 0.24 | 0.5 | 0.26 | 47.83% | 44 | 92 | 48 | 48.19 | 2120.36 | 4433.48 | 2313.12 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Castro, Francis D. | 21825405 | Rodriguez, Yroe Legaspi | L9 | L6 | Philippines | 0.74 | 1 | 0.26 | 73.91% | 136 | 184 | 48 | 48.19 | 6553.84 | 8866.96 | 2313.12 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Salazar, Ruth Mary | 20336648 | Rodriguez, Diego | L9 | L6 | Costa Rica | 0.46 | 0.75 | 0.29 | 60.87% | 84 | 138 | 54 | 61.48 | 5164.32 | 8484.24 | 3319.92 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Pacheco, Paul Robert Pascual | 11731393 | Alonsagay, Regina | L6 | L3 | Philippines | 0.39 | 0.5 | 0.11 | 78.37% | 72.1 | 92 | 19.9 | 14.53 | 1047.613 | 1336.76 | 289.147 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Curio, Francine Nicole Macoy | 11616383 | Dequilla, Ronina | L7 | L4 | Philippines | 0.8 | 1 | 0.2 | 80.43% | 148 | 184 | 36 | 20.51 | 3035.48 | 3773.84 | 738.36 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04995_PrIME custom mod upgrade RFI | PG22P04995 | Curio, Francine Nicole Macoy | 11596202 | Camacho, Christian | L7 | L4 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 20.51 | 2953.44 | 3773.84 | 820.4 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Venkateswaran, Suresh Kumar | 11589108 | Selvam, Nanthakumar | L8 | L5 | India | 0.07 | 0.1 | 0.03 | 67.63% | 14 | 20.7 | 6.7 | 26.59 | 372.26 | 550.413 | 178.153 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Arce, Karla Patricia R. | 11551119 | Mallari, Angelica Camille | L8 | L5 | Philippines | 0.22 | 0.5 | 0.28 | 43.48% | 40 | 92 | 52 | 33.58 | 1343.2 | 3089.36 | 1746.16 | Undertracking
FSC | Regueiro Lozano, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05488_PrIME Zero Downtime | PG23P05488 | Lubaton, Katrina Gail O. | 11550531 | Joson, May Fe | L8 | L5 | Philippines | 0.28 | 0.5 | 0.22 | 56.52% | 52 | 92 | 40 | 33.58 | 1746.16 | 3089.36 | 1343.2 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Li, Bin | 60075473 | Xu, Ying | L7 | L4 | P.R.C. | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 39.08 | 0 | 7190.72 | 7190.72 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Li, Bin | 21649570 | Shen, Chong | L8 | L5 | P.R.C. | 0 | 1 | 1 | 0% | 0 | 184 | 184 | 56.36 | 0 | 10370.24 | 10370.24 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11737849 | Darantinao, Justine Jane | L6 | L3 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 14.53 | 0 | 80.2056 | 80.2056 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11729926 | Bugaoan, Gerald M. | L7 | L4 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 20.51 | 0 | 113.2152 | 113.2152 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11727091 | Lovino, Joebert | L6 | L3 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 14.53 | 0 | 80.2056 | 80.2056 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11621649 | Mencias, Danniele Christian | L6 | L3 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 14.53 | 0 | 80.2056 | 80.2056 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11620004 | Belocura, Angelomie | L6 | L3 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 14.53 | 0 | 80.2056 | 80.2056 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Durandar, Janelle M. | 11582329 | Trinidad, Leo Anthony A. | L7 | L4 | Philippines | 0 | 0.03 | 0.03 | 0% | 0 | 5.52 | 5.52 | 20.51 | 0 | 113.2152 | 113.2152 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Bednarczyk, Marek | 11580391 | Frysz, Piotr | L8 | L5 | Poland | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 54.93 | 0 | 1516.068 | 1516.068 | No Tracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Gonzalez, Ropero Arantxa | 80166523 | Lorenzo Martinez, Fernando | L7 | L4 | Spain | 0.89 | 1 | 0.11 | 89.13% | 164 | 184 | 20 | 56.04 | 9190.56 | 10311.36 | 1120.8 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 75005153 | Trinidad, Karen Crystel D. | L9 | L6 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 48.19 | 8481.44 | 8866.96 | 385.52 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nicolas, Jadea Ann | 60108423 | Losloso, Wilfredo B. | L7 | L4 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 20.51 | 3281.6 | 3773.84 | 492.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 60091017 | Mateo, Patrick Wrayne Martin L. | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Arce, Karla Patricia R. | 22014997 | Repasa, Randy Calma | L8 | L5 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 33.58 | 2552.08 | 3089.36 | 537.28 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Diaz Maag, Javier | 21991419 | Cuevas, Alejandra Isabel | L8 | L5 | Spain | 0.98 | 1 | 0.02 | 98.37% | 181 | 184 | 3 | 75.52 | 13669.12 | 13895.68 | 226.56 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 21973938 | San Diego, Sabrina Encarnacion | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Arce, Karla Patricia R. | 21971943 | Nicolas, Jadea Ann | L13 | L5 | Philippines | 0.51 | 0.5 | -0.01 | 101.6% | 93.5 | 92 | -1.5 | 33.58 | 3139.73 | 3089.36 | -50.37 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 21667649 | Ison, Amabel D. | L9 | L6 | Philippines | 0.98 | 1 | 0.02 | 97.55% | 179.5 | 184 | 4.5 | 48.19 | 8650.105 | 8866.96 | 216.855 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Salazar, Ruth Mary | 21560225 | Delgado, Juan Carlos | L8 | L5 | Costa Rica | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 45.58 | 6928.16 | 8386.72 | 1458.56 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 21454514 | Villanueva, Maria Kristine B. | L9 | L6 | Philippines | 0.93 | 1 | 0.07 | 93.48% | 172 | 184 | 12 | 48.19 | 8288.68 | 8866.96 | 578.28 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Nepomuceno, Anna Grace Fullon | 20261515 | Cheng, Jim Sherwon C. | L9 | L6 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 48.19 | 8095.92 | 8866.96 | 771.04 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nepomuceno, Anna Grace Fullon | 20001124 | Lopez, Percival Iii Bargamento | L9 | L6 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 48.19 | 2544.432 | 2660.088 | 115.656 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Castro, Francis D. | 11759573 | Co, Aldrick Dexter | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 20.51 | 360.976 | 377.384 | 16.408 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Castro, Francis D. | 11759573 | Co, Aldrick Dexter | L7 | L4 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 20.51 | 541.464 | 566.076 | 24.612 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Castro, Francis D. | 11759573 | Co, Aldrick Dexter | L7 | L4 | Philippines | 0.14 | 0.15 | 0.01 | 95.65% | 26.4 | 27.6 | 1.2 | 20.51 | 541.464 | 566.076 | 24.612 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Castro, Francis D. | 11759573 | Co, Aldrick Dexter | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 20.51 | 360.976 | 377.384 | 16.408 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05361_ITC Rollout Support for Warehousing | PG23P05361 | Nepomuceno, Anna Grace Fullon | 11754937 | Galang, Patrick James | L8 | L5 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 33.58 | 5641.44 | 6178.72 | 537.28 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nicolas, Jadea Ann | 11738519 | Arca, Jemar | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04680_ Warehousing RTCIS Security Remediation FY2223 | PG22P04680 | Nicolas, Jadea Ann | 11738519 | Arca, Jemar | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04680_ Warehousing RTCIS Security Remediation FY2223 | PG22P04680 | Nicolas, Jadea Ann | 11732640 | Villanueva, Bency Ray | L6 | L3 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 14.53 | 1336.76 | 1336.76 | 0 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Arce, Karla Patricia R. | 11707347 | Rico, April | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Curio, Francine Nicole Macoy | 11705905 | Gomez, John Robert | L7 | L4 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 20.51 | 3281.6 | 3773.84 | 492.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05024_Warehousing Wave RO FY2223 | PG22P05024 | Mendenueta, Ismael | 11704230 | Nery, Earl Jantzen | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nicolas, Jadea Ann | 11621233 | Gaddafi, Steven | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nicolas, Jadea Ann | 11618553 | Cillo, Christine Joyce | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04680_ Warehousing RTCIS Security Remediation FY2223 | PG22P04680 | Nicolas, Jadea Ann | 11618553 | Cillo, Christine Joyce | L6 | L3 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 14.53 | 1220.52 | 1336.76 | 116.24 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Arce, Karla Patricia R. | 11600242 | Supe, Johann Francis Abamongaa | L9 | L6 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 48.19 | 8481.44 | 8866.96 | 385.52 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Arce, Karla Patricia R. | 11597924 | Padilla, Nikolai | L8 | L5 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 33.58 | 5910.08 | 6178.72 | 268.64 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Gonzalez, Ropero Arantxa | 11592430 | Serrano De Marta, Lucía | L6 | L3 | Spain | 0.94 | 1 | 0.06 | 93.88% | 172.74 | 184 | 11.26 | 49.36 | 8526.4464 | 9082.24 | 555.7936 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Antonio, Sarah Mangalinao | 11589411 | Del Barrio-Alejo, Karla Jean | L13 | L5 | Philippines | 1.02 | 0.5 | -0.52 | 203.3% | 187 | 92 | -95 | 33.58 | 6279.46 | 3089.36 | -3190.1 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Nicolas, Jadea Ann | 11587323 | Mejorada, Mark Nikko | L7 | L4 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 20.51 | 3609.76 | 3773.84 | 164.08 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 11586860 | Yoldi, Kristian | L7 | L4 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 20.51 | 3445.68 | 3773.84 | 328.16 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04682_Warehousing Product Team Librarian | PG22P04682 | Cipriano, John Henry | 11584432 | Tan, Johann Patrick | L6 | L3 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 14.53 | 1336.76 | 1336.76 | 0 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05024_Warehousing Wave RO FY2223 | PG22P05024 | Borja, Olivia B. | 11570918 | Pacheco, Andrea Jheremy | L7 | L4 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 20.51 | 861.42 | 943.46 | 82.04 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05361_ITC Rollout Support for Warehousing | PG23P05361 | Borja, Olivia B. | 11570918 | Pacheco, Andrea Jheremy | L7 | L4 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 20.51 | 1722.84 | 1886.92 | 164.08 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | De Villa, Fatima Suzanne G. | 11559941 | Llanes, Wilson Francis | L7 | L4 | Philippines | 0.08 | 0.07 | -0.01 | 111.8% | 14.4 | 12.88 | -1.52 | 20.51 | 295.344 | 264.1688 | -31.1752 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05361_ITC Rollout Support for Warehousing | PG23P05361 | Borja, Olivia B. | 11543116 | Red, Kylle Nicole | L7 | L4 | Philippines | 0.41 | 0.5 | 0.09 | 82.61% | 76 | 92 | 16 | 20.51 | 1558.76 | 1886.92 | 328.16 | On Track
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Diaz Maag, Javier | 80152265 | Vera, Angelica | L7 | L4 | Spain | 0.78 | 1 | 0.22 | 77.72% | 143 | 184 | 41 | 56.04 | 8013.72 | 10311.36 | 2297.64 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Li, Bin | 60067716 | Wang, Chen | L7 | L4 | P.R.C. | 1.07 | 2 | 0.93 | 53.26% | 196 | 368 | 172 | 39.08 | 7659.68 | 14381.44 | 6721.76 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04180_JENGA Warehousing Product Team for PrIME | PG22P04180 | Arce, Karla Patricia R. | 21825170 | Ty, Michelle Catherine Panganiban | L8 | L5 | Philippines | 0.57 | 1 | 0.43 | 56.52% | 104 | 184 | 80 | 33.58 | 3492.32 | 6178.72 | 2686.4 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Arce, Karla Patricia R. | 21630215 | Dizon, Ana Katrina P. | L9 | L6 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 48.19 | 6939.36 | 8866.96 | 1927.6 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Arce, Karla Patricia R. | 20347984 | Nepomuceno, Anna Grace Fullon | L14 | L6 | Philippines | 0.56 | 0.75 | 0.19 | 74.64% | 103 | 138 | 35 | 48.19 | 4963.57 | 6650.22 | 1686.65 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Shelar, Pandit | 20000246 | Li, Haihuan | L8 | L5 | Canada | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 82.64 | 11900.16 | 15205.76 | 3305.6 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Mendoza, Camille Chavez | 11744019 | Quisaba, Ralph | L7 | L4 | Philippines | 0.02 | 0.1 | 0.08 | 17.39% | 3.2 | 18.4 | 15.2 | 20.51 | 65.632 | 377.384 | 311.752 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05024_Warehousing Wave RO FY2223 | PG22P05024 | Castro, Francis D. | 11736443 | Capalad Tomagan, Rogene | L8 | L5 | Philippines | 0.07 | 0.1 | 0.03 | 65.22% | 12 | 18.4 | 6.4 | 33.58 | 402.96 | 617.872 | 214.912 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P05024_Warehousing Wave RO FY2223 | PG22P05024 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.08 | 0.1 | 0.02 | 76.09% | 14 | 18.4 | 4.4 | 20.51 | 287.14 | 377.384 | 90.244 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Nepomuceno, Anna Grace Fullon | 11600907 | Siasoco, Kiel | L8 | L5 | Philippines | 1 | 2 | 1 | 50% | 184 | 368 | 184 | 33.58 | 6178.72 | 12357.44 | 6178.72 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04203_JENGA DXC PrIME Center of Excellence | PG22P04203 | Gonzalez, Ropero Arantxa | 11573842 | Osuna, Oubiña Mariela Sabrina | L6 | L3 | Spain | 0.49 | 2 | 1.51 | 24.4% | 89.78 | 368 | 278.22 | 49.36 | 4431.5408 | 18164.48 | 13732.9392 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04197_JENGA Warehousing Product Team for RTCIS | PG22P04197 | Nicolas, Jadea Ann | 11571416 | Muñiz, Isabelle | L7 | L4 | Philippines | 0.78 | 1 | 0.22 | 78.26% | 144 | 184 | 40 | 20.51 | 2953.44 | 3773.84 | 820.4 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04895_ RTCIS Server Upgrade FY2223 | PG22P04895 | Nicolas, Jadea Ann | 11562754 | Villanueva, Jan Marion S. | L7 | L4 | Philippines | 0.96 | 2 | 1.04 | 47.83% | 176 | 368 | 192 | 20.51 | 3609.76 | 7547.68 | 3937.92 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04178_IT Warehousing Solution Team - SAP / 3PL Connect | PG22P04178 | Antonio, Sarah Mangalinao | 11557181 | Gutierrez, Kristine | L13 | L5 | Philippines | 0.3 | 0.5 | 0.2 | 60.87% | 56 | 92 | 36 | 33.58 | 1880.48 | 3089.36 | 1208.88 | Undertracking
FSC | Regueiro, Ainhoa | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04679_ Warehousing Solution team Loftware FY222 | PG22P04679 | Pszczólkowski, Piotr A. | 540653 | Wozniak, Agnieszka | L8 | L5 | Poland | 0.2 | 0.5 | 0.3 | 39.13% | 36 | 92 | 56 | 54.93 | 1977.48 | 5053.56 | 3076.08 | Undertracking
FSC | Tecson, Jacqueline | PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Curio, Francine Nicole Macoy | 11584435 | Coralde, Nelson | L7 | L4 | Philippines | 0.034783 | 0 | -0.034783 | 0% | 6.4 | 0 | -6.4 | 20.51 | 131.264 | 0 | -131.264 | No Plan
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Li, Bin | 60070576 | Chai, Ya-Fang | L6 | L3 | P.R.C. | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 28.33 | 0 | 2606.36 | 2606.36 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05345_Xiqing AGVs Implementation | PG23P05345 | Arce, Karla Patricia R. | 21971943 | Nicolas, Jadea Ann | L13 | L5 | Philippines | 0 | 0.06 | 0.06 | 0% | 0 | 11.04 | 11.04 | 33.58 | 0 | 370.7232 | 370.7232 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Li, Bin | 20333904 | Zhang, Yu-Xin | L9 | L6 | P.R.C. | 0 | 0.2 | 0.2 | 0% | 0 | 36.8 | 36.8 | 80.17 | 0 | 2950.256 | 2950.256 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Crucena, Mark Jayson S. | 11755600 | Caraos, Abbygaile | L6 | L3 | Philippines | 0 | 0.07 | 0.07 | 0% | 0 | 12.88 | 12.88 | 14.53 | 0 | 187.1464 | 187.1464 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Crucena, Mark Jayson S. | 11745462 | Albarico, John Paul | L6 | L3 | Philippines | 0 | 0.08 | 0.08 | 0% | 0 | 14.72 | 14.72 | 14.53 | 0 | 213.8816 | 213.8816 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Rodriguez, Alphonse Joseph V. | 11736431 | Baniquet, Zyra Mae V. | L6 | L3 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 14.53 | 0 | 267.352 | 267.352 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Rodriguez, Alphonse Joseph V. | 11723726 | Onato, Lara Jahzeel | L6 | L3 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 14.53 | 0 | 267.352 | 267.352 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Rodriguez, Alphonse Joseph V. | 11723726 | Onato, Lara Jahzeel | L6 | L3 | Philippines | 0 | 0.05 | 0.05 | 0% | 0 | 9.2 | 9.2 | 14.53 | 0 | 133.676 | 133.676 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Crucena, Mark Jayson S. | 11708606 | Barro, Mary Joy | L6 | L3 | Philippines | 0 | 0.02 | 0.02 | 0% | 0 | 3.68 | 3.68 | 14.53 | 0 | 53.4704 | 53.4704 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11707516 | Buenafe, Steven Vincent | L6 | L3 | Philippines | 0 | 0.11 | 0.11 | 0% | 0 | 20.24 | 20.24 | 14.53 | 0 | 294.0872 | 294.0872 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Rodriguez, Alphonse Joseph V. | 11705603 | Paulino, Spenzer | L6 | L3 | Philippines | 0 | 0.1 | 0.1 | 0% | 0 | 18.4 | 18.4 | 14.53 | 0 | 267.352 | 267.352 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11618845 | Lim, Gene Ericka Franz | L6 | L3 | Philippines | 0 | 0.07 | 0.07 | 0% | 0 | 12.88 | 12.88 | 14.53 | 0 | 187.1464 | 187.1464 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11616942 | Villanueva, Alren Tristan S. | L6 | L3 | Philippines | 0 | 0.17 | 0.17 | 0% | 0 | 31.28 | 31.28 | 14.53 | 0 | 454.4984 | 454.4984 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Borja, Olivia B. | 11598516 | Santos, Mushienne Mari | L7 | L4 | Philippines | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 20.51 | 0 | 566.076 | 566.076 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11582298 | Martelino, Samantha | L7 | L4 | Philippines | 0 | 0.09 | 0.09 | 0% | 0 | 16.56 | 16.56 | 20.51 | 0 | 339.6456 | 339.6456 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Li, Bin | 11580851 | Liu, Lei | L7 | L4 | P.R.C. | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 39.08 | 0 | 3595.36 | 3595.36 | No Tracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 20.51 | 377.384 | 377.384 | 5.6843e-14 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 75006494 | Sacdalan, Lucky Rushty C. | L7 | L4 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 20.51 | 861.42 | 943.46 | 82.04 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Li, Bin | 75002554 | Mao, Likun | L7 | L4 | P.R.C. | 0.6 | 0.6 | 0 | 100% | 110.4 | 110.4 | -1.4211e-14 | 39.08 | 4314.432 | 4314.432 | 0 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Del Rosario, Maria Katrina | 60074237 | Bacay, Jessica Mae R. | L8 | L5 | Philippines | 0.09 | 0.07 | -0.02 | 130.4% | 16.8 | 12.88 | -3.92 | 33.58 | 564.144 | 432.5104 | -131.6336 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Bantang, Selwyn Ralph Selva | 60041315 | Calicdan, Maria Krizelle B. | L7 | L4 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 20.51 | 902.44 | 943.46 | 41.02 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Del Rosario, Maria Katrina | 60027986 | Jabilona, Rachelle Ann C. | L7 | L4 | Philippines | 0.07 | 0.04 | -0.03 | 163% | 12 | 7.36 | -4.64 | 20.51 | 246.12 | 150.9536 | -95.1664 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05345_Xiqing AGVs Implementation | PG23P05345 | Arce, Karla Patricia R. | 21744358 | Caballero, Chrina Angela Dimayuga | L8 | L5 | Philippines | 0.25 | 0.28 | 0.03 | 89.29% | 46 | 51.52 | 5.52 | 33.58 | 1544.68 | 1730.0416 | 185.3616 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Li, Bin | 21557794 | Ting, Xu | L6 | L3 | P.R.C. | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 28.33 | 4759.44 | 5212.72 | 453.28 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mejia, Ervene Albert H. | 11765805 | Gumpal, Kennedy Klein | L6 | L3 | Philippines | 0.5 | 0.44 | -0.06 | 114.1% | 92.4 | 80.96 | -11.44 | 14.53 | 1342.572 | 1176.3488 | -166.2232 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Uy, Precious L. | 11757137 | Yee, Kevin Glenn | L6 | L3 | Philippines | 0.41 | 0.5 | 0.09 | 82.17% | 75.6 | 92 | 16.4 | 14.53 | 1098.468 | 1336.76 | 238.292 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Uy, Precious L. | 11754281 | Bustamante, Jay Ruel | L6 | L3 | Philippines | 0.23 | 0.23 | 0 | 101.1% | 42.77 | 42.32 | -0.45 | 14.53 | 621.4481 | 614.9096 | -6.5385 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 11754281 | Bustamante, Jay Ruel | L6 | L3 | Philippines | 0.19 | 0.2 | 0.01 | 93.53% | 34.42 | 36.8 | 2.38 | 14.53 | 500.1226 | 534.704 | 34.5814 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Mendenueta, Ismael | 11746864 | Abu, Aaron Christina | L6 | L3 | Philippines | 0.24 | 0.2 | -0.04 | 117.7% | 43.33 | 36.8 | -6.53 | 14.53 | 629.5849 | 534.704 | -94.8809 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Caldez, Stan Steve Philip Sarmiento | 11745820 | Benasa, Angelica G. | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Navarro, Joycee E. | 11744386 | Tuzon, Darvin Carl | L6 | L3 | Philippines | 0.41 | 0.11 | -0.3 | 375.5% | 76 | 20.24 | -55.76 | 14.53 | 1104.28 | 294.0872 | -810.1928 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mejia, Ervene Albert H. | 11742820 | Espiritu, John Harold Y. | L6 | L3 | Philippines | 0.14 | 0.13 | -0.01 | 105.4% | 25.2 | 23.92 | -1.28 | 14.53 | 366.156 | 347.5576 | -18.5984 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Morong, Jann Angelo U. | 11740756 | Magaso, Veronicka Nina M. | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Chua, Jeremiah Nathaniel | 11739701 | Bejo, Christine Mae | L6 | L3 | Philippines | 0.19 | 0.2 | 0.01 | 95.65% | 35.2 | 36.8 | 1.6 | 14.53 | 511.456 | 534.704 | 23.248 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05345_Xiqing AGVs Implementation | PG23P05345 | Chua, Jeremiah Nathaniel | 11739654 | De Lumban, Dorothy | L6 | L3 | Philippines | 0.12 | 0.06 | -0.06 | 195.7% | 21.6 | 11.04 | -10.56 | 14.53 | 313.848 | 160.4112 | -153.4368 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Del Barrio-Alejo, Karla Jean | 11738825 | Señar, Aaron Joshua | L6 | L3 | Philippines | 0.22 | 0.25 | 0.03 | 86.96% | 40 | 46 | 6 | 14.53 | 581.2 | 668.38 | 87.18 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05345_Xiqing AGVs Implementation | PG23P05345 | Castro, Francis D. | 11738677 | Guevarra, Cobe Bryan | L6 | L3 | Philippines | 0.08 | 0.06 | -0.02 | 137.7% | 15.2 | 11.04 | -4.16 | 14.53 | 220.856 | 160.4112 | -60.4448 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Del Rosario, Maria Katrina | 11738383 | Anunciado, Joy Ann | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 100% | 18.4 | 18.4 | 3.5527e-15 | 14.53 | 267.352 | 267.352 | 5.6843e-14 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Del Barrio-Alejo, Karla Jean | 11738300 | Javier, Francis Anjo | L6 | L3 | Philippines | 0.42 | 0.5 | 0.08 | 84.78% | 78 | 92 | 14 | 14.53 | 1133.34 | 1336.76 | 203.42 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Pacheco, Paul Robert Pascual | 11735518 | Buan, Marinela | L6 | L3 | Philippines | 0.27 | 0.3 | 0.03 | 91.3% | 50.4 | 55.2 | 4.8 | 14.53 | 732.312 | 802.056 | 69.744 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Pacheco, Paul Robert Pascual | 11735518 | Buan, Marinela | L6 | L3 | Philippines | 0.18 | 0.2 | 0.02 | 91.3% | 33.6 | 36.8 | 3.2 | 14.53 | 488.208 | 534.704 | 46.496 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11730193 | Diamante, Sharmaine Imari | L6 | L3 | Philippines | 0.53 | 0.45 | -0.08 | 116.9% | 96.8 | 82.8 | -14 | 14.53 | 1406.504 | 1203.084 | -203.42 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mejia, Ervene Albert H. | 11729561 | Gonzales, Carl Rhaniel | L6 | L3 | Philippines | 0.65 | 0.8 | 0.15 | 81.52% | 120 | 147.2 | 27.2 | 14.53 | 1743.6 | 2138.816 | 395.216 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Rogando, Walter Ericson Tan | 11727094 | De Guzman, Rovee Ken | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Caldez, Stan Steve Philip Sarmiento | 11726139 | Lajo, Rovee Celino Filoteo | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG21P04065_P&G Schrems II Project | PG21P04065 | De Villa, Fatima Suzanne G. | 11725494 | Boniao, Ren Michael | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG21P04065_P&G Schrems II Project | PG21P04065 | Ng, Sheila Regine Siy | 11725482 | Dimapilis, Michael Andrei | L6 | L3 | Philippines | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 14.53 | 2557.28 | 2673.52 | 116.24 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Jarabelo, Angela Bernadette Santos | 11723752 | Sala, Janelle | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05363_Generic Lanes Support T&M Project | PG23P05363 | Jarabelo, Angela Bernadette Santos | 11723752 | Sala, Janelle | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Navarro, Joycee E. | 11721548 | Espina, Alexis | L6 | L3 | Philippines | 0.26 | 0.2 | -0.06 | 130.4% | 48 | 36.8 | -11.2 | 14.53 | 697.44 | 534.704 | -162.736 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mendoza, Camille Chavez | 11721142 | Aloba, Alberto | L6 | L3 | Philippines | 0.14 | 0.15 | 0.01 | 91.3% | 25.2 | 27.6 | 2.4 | 14.53 | 366.156 | 401.028 | 34.872 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.07 | 0.07 | 0 | 93.17% | 12 | 12.88 | 0.88 | 20.51 | 246.12 | 264.1688 | 18.0488 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mejia, Ervene Albert H. | 11717048 | Balbada, Joan | L6 | L3 | Philippines | 0.48 | 0.3 | -0.18 | 159.4% | 88 | 55.2 | -32.8 | 14.53 | 1278.64 | 802.056 | -476.584 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Crucena, Mark Jayson S. | 11716457 | Sanchez, John Conrad | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 14.53 | 232.48 | 267.352 | 34.872 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | De Villa, Fatima Suzanne G. | 11715812 | Aguilar, Jonnuelle | L7 | L4 | Philippines | 0.2 | 0.2 | 0 | 100% | 36.8 | 36.8 | 7.1054e-15 | 20.51 | 754.768 | 754.768 | 1.1369e-13 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Navarro, Joycee E. | 11713448 | Jurilla, John Harvey | L6 | L3 | Philippines | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 14.53 | 232.48 | 267.352 | 34.872 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Castro, Francis D. | 11712632 | Urcia, Joanna Isabelle | L7 | L4 | Philippines | 0.09 | 0.1 | 0.01 | 86.96% | 16 | 18.4 | 2.4 | 20.51 | 328.16 | 377.384 | 49.224 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Castro, Francis D. | 11712632 | Urcia, Joanna Isabelle | L7 | L4 | Philippines | 0.07 | 0.05 | -0.02 | 139.1% | 12.8 | 9.2 | -3.6 | 20.51 | 262.528 | 188.692 | -73.836 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mendenueta, Ismael | 11711729 | Vallespin, Christian Gabriel | L6 | L3 | Philippines | 0.38 | 0.37 | -0.01 | 103.4% | 70.4 | 68.08 | -2.32 | 14.53 | 1022.912 | 989.2024 | -33.7096 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05363_Generic Lanes Support T&M Project | PG23P05363 | Cua, Jon Russell T. | 11707516 | Buenafe, Steven Vincent | L6 | L3 | Philippines | 0.46 | 0.35 | -0.11 | 130.4% | 84 | 64.4 | -19.6 | 14.53 | 1220.52 | 935.732 | -284.788 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11707512 | Rodriguez, Christian | L6 | L3 | Philippines | 0.56 | 0.37 | -0.19 | 151.6% | 103.2 | 68.08 | -35.12 | 14.53 | 1499.496 | 989.2024 | -510.2936 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG21P04065_P&G Schrems II Project | PG21P04065 | De Villa, Fatima Suzanne G. | 11705484 | Hidalgo, Rachel Mae O. | L6 | L3 | Philippines | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 14.53 | 2324.8 | 2673.52 | 348.72 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Mendenueta, Ismael | 11704230 | Nery, Earl Jantzen | L6 | L3 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 14.53 | 639.32 | 668.38 | 29.06 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Del Barrio-Alejo, Karla Jean | 11703658 | Teves, Kathlyn | L6 | L3 | Philippines | 0.24 | 0.1 | -0.14 | 239.1% | 44 | 18.4 | -25.6 | 14.53 | 639.32 | 267.352 | -371.968 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Del Barrio-Alejo, Karla Jean | 11703658 | Teves, Kathlyn | L6 | L3 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 14.53 | 2441.04 | 2673.52 | 232.48 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Borja, Olivia B. | 11621764 | Pajes Iii, Ramon Alfredo I. | L6 | L3 | Philippines | 0.5 | 0.55 | 0.05 | 91.3% | 92.4 | 101.2 | 8.8 | 14.53 | 1342.572 | 1470.436 | 127.864 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Durandar, Janelle M. | 11621649 | Mencias, Danniele Christian | L6 | L3 | Philippines | 0.2 | 0.18 | -0.02 | 108.7% | 36 | 33.12 | -2.88 | 14.53 | 523.08 | 481.2336 | -41.8464 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11619099 | Mamaradlo, John Paul Azanza | L6 | L3 | Philippines | 0.55 | 0.44 | -0.11 | 124.5% | 100.8 | 80.96 | -19.84 | 14.53 | 1464.624 | 1176.3488 | -288.2752 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Morong, Jann Angelo U. | 11616365 | Licong, Philbert Rey Reyes | L7 | L4 | Philippines | 0.46 | 0.5 | 0.04 | 91.3% | 84 | 92 | 8 | 20.51 | 1722.84 | 1886.92 | 164.08 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11616224 | Alvarez, Mark Rafael | L6 | L3 | Philippines | 0.26 | 0.3 | 0.04 | 86.96% | 48 | 55.2 | 7.2 | 14.53 | 697.44 | 802.056 | 104.616 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 11588574 | Nofuente, Maria Kate | L7 | L4 | Philippines | 0.15 | 0.1 | -0.05 | 152.2% | 28 | 18.4 | -9.6 | 20.51 | 574.28 | 377.384 | -196.896 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG23P05345_Xiqing AGVs Implementation | PG23P05345 | Curio, Francine Nicole Macoy | 11584435 | Coralde, Nelson | L7 | L4 | Philippines | 0.06 | 0.06 | 0 | 94.2% | 10.4 | 11.04 | 0.64 | 20.51 | 213.304 | 226.4304 | 13.1264 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Caldez, Stan Steve Philip Sarmiento | 11584293 | Gempes, Glorie Anne | L7 | L4 | Philippines | 0.24 | 0.25 | 0.01 | 95.65% | 44 | 46 | 2 | 20.51 | 902.44 | 943.46 | 41.02 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Abet Pabalate, | 11582385 | Marino, Nessan | L6 | L3 | Philippines | 0.23 | 0.25 | 0.02 | 91.3% | 42 | 46 | 4 | 14.53 | 610.26 | 668.38 | 58.12 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11578470 | Gonzales, Rencie Mae | L7 | L4 | Philippines | 0.24 | 0.13 | -0.11 | 183.9% | 44 | 23.92 | -20.08 | 20.51 | 902.44 | 490.5992 | -411.8408 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Borja, Olivia B. | 11570918 | Pacheco, Andrea Jheremy | L7 | L4 | Philippines | 0.09 | 0.05 | -0.04 | 182.6% | 16.8 | 9.2 | -7.6 | 20.51 | 344.568 | 188.692 | -155.876 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Borja, Olivia B. | 11547747 | Cacatian, Edmund | L7 | L4 | Philippines | 0.29 | 0.3 | 0.01 | 95.65% | 52.8 | 55.2 | 2.4 | 20.51 | 1082.928 | 1132.152 | 49.224 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Caldez, Stan Steve Philip Sarmiento | 11545630 | Atienza, Carlove Gerard M. | L8 | L5 | Philippines | 0.17 | 0.2 | 0.03 | 86.96% | 32 | 36.8 | 4.8 | 33.58 | 1074.56 | 1235.744 | 161.184 | On Track
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 11757137 | Yee, Kevin Glenn | L6 | L3 | Philippines | 0.14 | 0.3 | 0.16 | 45.65% | 25.2 | 55.2 | 30 | 14.53 | 366.156 | 802.056 | 435.9 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Bantang, Selwyn Ralph Selva | 11745505 | Avisa, Marianne Grace | L6 | L3 | Philippines | 0.51 | 0.65 | 0.14 | 78.26% | 93.6 | 119.6 | 26 | 14.53 | 1360.008 | 1737.788 | 377.78 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | RodriguezRegalado Jr., A | 11738065 | Española, Jeptha Mathan | L6 | L3 | Philippines | 0.04 | 0.1 | 0.06 | 43.48% | 8 | 18.4 | 10.4 | 14.53 | 116.24 | 267.352 | 151.112 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11735572 | Bernardo, Paul Wilson | L6 | L3 | Philippines | 0.1 | 0.12 | 0.02 | 79.71% | 17.6 | 22.08 | 4.48 | 14.53 | 255.728 | 320.8224 | 65.0944 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Pacheco, Paul Robert Pascual | 11731393 | Alonsagay, Regina | L6 | L3 | Philippines | 0.22 | 0.4 | 0.18 | 54.69% | 40.25 | 73.6 | 33.35 | 14.53 | 584.8325 | 1069.408 | 484.5755 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Uy, Precious L. | 11720158 | Ausa, Mariane | L7 | L4 | Philippines | 0.03 | 0.07 | 0.04 | 46.58% | 6 | 12.88 | 6.88 | 20.51 | 123.06 | 264.1688 | 141.1088 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Gonzales, Francis C. | 11713223 | Toral, Justin Francis | L7 | L4 | Philippines | 0.1 | 0.49 | 0.39 | 19.52% | 17.6 | 90.16 | 72.56 | 20.51 | 360.976 | 1849.1816 | 1488.2056 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04618_PS Projects T&M for Greater China FY22-23 | PG22P04618 | Uy, Precious L. | 11710438 | Viola, Jennielyn | L6 | L3 | Philippines | 0.05 | 0.1 | 0.05 | 47.83% | 8.8 | 18.4 | 9.6 | 14.53 | 127.864 | 267.352 | 139.488 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Angeles, Rouen Francis Simeon Rafols | 11703628 | Blacer, Celestine Antoinette | L6 | L3 | Philippines | 0.14 | 0.2 | 0.06 | 69.57% | 25.6 | 36.8 | 11.2 | 14.53 | 371.968 | 534.704 | 162.736 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Cua, Jon Russell T. | 11616305 | Asanza, Desmond Christian T. | L6 | L3 | Philippines | 0.11 | 0.15 | 0.04 | 73.91% | 20.4 | 27.6 | 7.2 | 14.53 | 296.412 | 401.028 | 104.616 | Undertracking
FSC | Tecson, Jacqueline | Deliver_AMS_PG_APP_TMTL_ESC_71_PG22P04616_PS Projects T&M for AMA and Europe FY22-23 | PG22P04616 | Ong, Jacqueline P. | 11569974 | Barretto, Eula Mae | L7 | L4 | Philippines | 0.28 | 0.37 | 0.09 | 76.38% | 52 | 68.08 | 16.08 | 20.51 | 1066.52 | 1396.3208 | 329.8008 | Undertracking
FSC | Vargas, Claudia | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P05047_Adhoc security requests for RTCIS and PrIME systems (CCR-143) | PG22P05047 | Banaria, Loreen | 11712614 | Reynancia, Angelica | L6 | L3 | Philippines | 0 | 0.5 | 0.5 | 0% | 0 | 92 | 92 | 14.53 | 0 | 1336.76 | 1336.76 | No Tracking
FSC | Vargas, Claudia | Deliver_AMS_PG_APP_SATM_ESC_70_PG22P05047_Adhoc security requests for RTCIS and PrIME systems (CCR-143) | PG22P05047 | Tayag, Ros Vergel M. | 11707502 | Go, Mark Renzon | L6 | L3 | Philippines | 0.42 | 1 | 0.58 | 41.85% | 77 | 184 | 107 | 14.53 | 1118.81 | 2673.52 | 1554.71 | Undertracking
FSC | Vermunicht, Guido - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG22P04273_Harmony Project | PG22P04273 | Durandar, Janelle M. | 11582329 | Trinidad, Leo Anthony A. | L7 | L4 | Philippines | 0 | 0.15 | 0.15 | 0% | 0 | 27.6 | 27.6 | 20.51 | 0 | 566.076 | 566.076 | No Tracking
FSC | Vermunicht, Guido - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG22P04273_Harmony Project | PG22P04273 | Durandar, Janelle M. | 11620004 | Belocura, Angelomie | L6 | L3 | Philippines | 0.1 | 0.1 | 0 | 95.65% | 17.6 | 18.4 | 0.8 | 14.53 | 255.728 | 267.352 | 11.624 | On Track
FSC | Vermunicht, Guido - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG21P04082_MES Connect Deployment Requests | PG21P04082 | Antonio, Sarah Mangalinao | 11589411 | Del Barrio-Alejo, Karla Jean | L13 | L5 | Philippines | 0.5 | 0.5 | 0 | 100% | 92 | 92 | 0 | 33.58 | 3089.36 | 3089.36 | 0 | On Track
FSC | Vermunicht, Guido - Projects | Deliver_AMS_PG_APP_TMTL_HRZ_50_PG22P04273_Harmony Project | PG22P04273 | Lacaba, Justine Enide | 11618134 | Maganes, Julius | L6 | L3 | Philippines | 0.13 | 0.5 | 0.37 | 26.09% | 24 | 92 | 68 | 14.53 | 348.72 | 1336.76 | 988.04 | Undertracking
FSC | Villuendas, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04822_OTC SA Attachment B-3 - 2- Accounts Receivable Application Manager | PG22P04822 | Bonilla, Johan Stick | 60083273 | Monestel, Daniel Gerardo | L8 | L5 | Costa Rica | 0.96 | 1 | 0.04 | 95.65% | 176 | 184 | 8 | 45.58 | 8022.08 | 8386.72 | 364.64 | On Track
FSC | Villuendas, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04820_OTC SA Attachment B-3 - 1 - Accounts Receivables SAP Factory PG | PG22P04820 | Arguedas, Jose Guillermo | 20006940 | Rojas, Victor Manuel | L8 | L5 | Costa Rica | 0.29 | 0.25 | -0.04 | 115.2% | 53 | 46 | -7 | 45.58 | 2415.74 | 2096.68 | -319.06 | On Track
FSC | Villuendas, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04820_OTC SA Attachment B-3 - 1 - Accounts Receivables SAP Factory PG | PG22P04820 | Mendoza, Camille Chavez | 11614575 | Yango, Nicole Ann Bernardine | L7 | L4 | Philippines | 0.91 | 1 | 0.09 | 91.3% | 168 | 184 | 16 | 20.51 | 3445.68 | 3773.84 | 328.16 | On Track
FSC | Villuendas, Raul | Deliver_AMS_PG_APP_SATM_ESC_71_PG22P04820_OTC SA Attachment B-3 - 1 - Accounts Receivables SAP Factory PG | PG22P04820 | Rvss, Sasidhar Murthy | 11728198 | Endla, Vijaykumar | L7 | L4 | India | 0.7 | 1 | 0.3 | 69.57% | 144 | 207 | 63 | 17.33 | 2495.52 | 3587.31 | 1091.79 | Undertracking
Infra | Manalac, Von Xavier | Deliver_AMS_PG_ITO_TMTL_INF_12_PG23P05411_IT Data Cataloging and Data Architecture | PG23P05411 | Radosz, Jacek T. | 75013236 | Rzepka, Monika | L8 | L5 | Poland | 0.33 | 0.2 | -0.13 | 163% | 60 | 36.8 | -23.2 | 54.93 | 3295.8 | 2021.424 | -1274.376 | On Track
Infra | Manalac, Von Xavier | Deliver_AMS_PG_ITO_TMTL_INF_12_PG23P05411_IT Data Cataloging and Data Architecture | PG23P05411 | Andreev, Anton | 60054935 | Hariskov, Dimitar | L8 | L5 | Bulgaria | 0.83 | 1 | 0.17 | 82.61% | 152 | 184 | 32 | 49.91 | 7586.32 | 9183.44 | 1597.12 | On Track
Infra | Manalac, Von Xavier | Deliver_AMS_PG_ITO_TMTL_INF_12_PG21P03659_MEGA Application Manager_Ext | PG21P03659 | Tadmari, Srinivasa | 20118981 | Bansal, Mukesh Kumar | L8 | L5 | India | 0.91 | 1 | 0.09 | 91.3% | 189 | 207 | 18 | 26.59 | 5025.51 | 5504.13 | 478.62 | On Track
Infra | Manalac, Von Xavier | Deliver_AMS_PG_ITO_TMTL_INF_12_PG23P05411_IT Data Cataloging and Data Architecture | PG23P05411 | Chorbanov, Nikolay | 11572761 | Dolutarov, Simeonov Hristo | L9 | L6 | Bulgaria | 0.87 | 1 | 0.13 | 86.96% | 160 | 184 | 24 | 59.71 | 9553.6 | 10986.64 | 1433.04 | On Track
Infra | Manalac, Von Xavier | Deliver_AMS_PG_ITO_TMTL_INF_12_PG22P05298_ITSM Enhancements ServiceNow | PG22P05298 | Sudhir Ojha, | 11738478 | Roy, Priyobroto | L6 | L3 | India | 0.61 | 1 | 0.39 | 60.87% | 126 | 207 | 81 | 11.75 | 1480.5 | 2432.25 | 951.75 | Undertracking
Voice | Arevalo, Milton | AMA-West Network CaaS Technical Project Manager Delivery | PG20P25038 | Goel, Manish | 20379992 | Karupiah, Selvapandi | L14 | L6 | INDIA | 0.086957 | 0 | -0.086957 | 0% | 18 | 0 | -18 |  | 0 | 0 | 0 | No Plan
VOICE | Arevalo, Milton | Deliver_AMS_PG_ITO_TMTL_VOI_12_PG20P25038_AMA-West Network CaaS Technical Project Manager Delivery | PG20P25038 | Karupiah, Selvapandi | 75004713 | Chouhan, Sadiq | L8 | L5 | India | 0.39 | 1 | 0.61 | 39.13% | 81 | 207 | 126 | 26.59 | 2153.79 | 5504.13 | 3350.34 | Undertracking
VOICE | Arevalo, Milton | Deliver_AMS_PG_ITO_TMTL_VOI_12_PG20P23934_AMA-East Network CaaS Technical Project Manager Delivery | PG20P23934 | Diaz, Pamela Ambagan | 11550233 | Velarde, Lalaine | L8 | L5 | Philippines | 0.7 | 1 | 0.3 | 69.57% | 128 | 184 | 56 | 33.58 | 4298.24 | 6178.72 | 1880.48 | Undertracking